## Slide 1: May 25, 2022 Work Group Update

## Slide 2: Fire & Smoke Work Group Accomplishments (May 2022)
Tasks / Coordination / Meetings
May 16, 2022 meeting postponed. Next meeting June 13, 2022.
May 31, 2022: Joint meeting between FSWG and National Wildfire Coordinating Group (NWCG) Smoke Managers Subcommittee (https://www.nwcg.gov/committees/smoke-managers-subcommittee).
  Agenda:
    Introduction and ideas around collaboration of the two groups – Pete Lahm (USFS)
    US EPA regulatory update and discussion around impact of the 2020 NAAQS design values/potential new Non-Attainment Areas – Rick Gillam (US EPA)
    USFS 10 Year Strategy and the Smoke/Land Management Challenge – Pete Lahm (USFS)
    2022 National Fire Season Outlook - Basil Newmerzhycky (Great Basin Coordination Center)
In-person meeting in San Diego, Nov. 16 (afternoon) & Nov. 17 (all day). Topic: ‘Western US Smoke Management Programs’. Themes include smoke impact coordination, discussion of SMPs, and communication between SLTs, FLMs and the public.
EE team met May 18, 2022. Materials posted on FSWG page. Next meeting July 20th.

## Slide 3: Oil & Gas Work Group Accomplishments (May 2022)
  Actions
  Distributed OGWG 2022 Annual O&G Survey (online and *.xlsx formats)
      Responses due June 24th;
      Compile results and distribute draft report July 29th for review and comment;
      Brief TSC on final report Aug. 31st; Present at WESTAR/WRAP Fall meeting Sept. 7, 2022
  Recruited WRAP Tribal member agency as 3rd OGWG co-chair.
    Welcome Matt Wampler – Southern Ute Indian Tribe
  Meetings
  April 28, 2022 – Met with OGWG participants to finalize survey implementation logistics
  May 24/25, 2022 – Meetings with FLMs and EPA
    Discuss and get feedback from federal agencies on OGWG 2022 Annual O&G Survey
  Up Next
  OGWG Survey: Data Collection, Analysis, and Reporting: May – September 2022
    Assistance and coordination with federal/state/local/tribal agencies as needed
  Next OGWG Call – August 16, 2022 – 12:30 p.m. (MDT)
  OGWG Website – www.wrapair2.org/OGWG.aspx

## Slide 4: Regional Technical Operations Work Group Accomplishments (May 2022)
Tasks / Coordination / Meetings
  RTOWG call scheduled for 6/1/22
    Presentations from EPA on their ‘good neighbor’ plan for addressing 2015 ozone NAAQS
    https://www.epa.gov/csapr/good-neighbor-plan-2015-ozone-naaqs
  Manuscript for EM on nitrogen deposition modeling using WRAP CAMx results
  RTOWG co-chairs coordination calls
  In-person RTOWG co-chair meeting in Lyons (actually a send-off for Pat Brewer, who left CO for NC)

## Slide 5: Tribal Data Work Group Accomplishments (May 2022)
Tasks / Coordination / Meetings

## Slide 6: Regional Haze Planning Work Group Accomplishments (May 2022)
Tasks / Coordination / Meetings
  In lieu of 2nd Quarter meeting - Regional Haze SIP progress State spreadsheet