## Slide 1: May 26, 2021 Work Group Update

## Slide 2: Fire & Smoke Work Group Progress Update 12/1/2020 Board Approved Work Topics
May 2021
  1), 2)  SMP Mapping Tool Team:
  Initial email sent to participants interested in the project team
  3)  Exceptional Events Support Team:
  Initial email sent to interested participants; expanded to other EE groups.
  Updating EE Data Resources List - in progress
  Scoping out first meeting topics
  4)  Conceptual Model for Fire Data:
  Reviewed the Data Warehouse Implementation of the CMFD
  Planning stakeholder workshops
  5)  Wildland/Rx Fire Nexus Team: Set to simmer until RH SIPs are done.
  5)  AZ wildfire smoke forecasting presentation at last meeting
  Next call – Monday June 28

## Slide 3: Oil & Gas Work Group Progress Update 12/1/2020 Board Approved Work Topics
May 2021
  May 20: Co-chairs met to discuss draft scope from Ramboll.
  May 28: Co-chairs reconvening to discuss potential additions to scope.
  Early June (to be scheduled): limited state-only meeting with inventory staff to discuss wants vs. needs for updated oil and gas operators survey
  Mid-Late June (to be scheduled): 2021 OGWG Workplan Scope meeting with full workgroup
    Draft Workplan Scope posted following meeting

## Slide 4: Regional Technical Operations Work Group Status Update May 2021
Tasks / Coordination / Meetings
  Coordination calls with co-chairs
  Continued updates to TSS

## Slide 5: 12/1/2020 Board Approved Work Topics RTO Work Group Progress Update
#10 – 2017 modeling platform
  GEOS-Chem and WRF simulations completed
    Reports to be circulated for review in June
    Ramboll to deliver these data to IWDW in June
  Discussion of options for emissions
    Start with 2017 NEI
    Consider sector-specific EI updates (e.g., oil & gas)
    Any subsequent SMOKE emissions processing for O&G or other emissions sectors would require decisions about doing additional work to define the air quality modeling platform
      Speciation, source apportionment, sensitivity analyses
      Projections - assumptions about future activity and control effectiveness

## Slide 6: Regional Haze Planning Work Group Status Update May 2021
Modeling Results Meetings
  May 5th
    US Anthropogenic Results
  Upcoming in June
    TSSv2 Deliverables
No RHPWG specific meeting planned

## Slide 7: WESTAR/WRAP Progress Update 12/1/2020 Board Approved Work Topics
May 2021
#12-13 – to be combined under 2 3 project funding proposals to NASA
NNH21ZDA001N-HAQ:A.37 Earth Science Applications: Health and Air Quality
  Notice of Intent (not required, 1-2 paragraphs) for 1 and 2 completed April 30th
  Full proposal due June 18th
  Potential funding up to $250-$300k/year/project for 3 years (2022-24)
    Applying Remote Sensing Data to construct a Wildland Smoke Emissions Data Warehouse (WSEDW)
      To build / implement FSWG Conceptual Model for Fire Data
      WESTAR-WRAP managed, work by Air Sciences (science data design), Michigan Tech Research Institute (emissions tools), and CSU-CIRA (warehouse)
    Tailoring Science Data from High-resolution Satellites and Models to Improve Decision Support Systems for Air Quality Management Applications
      Address gaps between Earth Science data and routine evaluation and application by air quality management agencies for regulatory analysis and decision-making activities
      Co-managed by University of Alabama in Huntsville and WESTAR-WRAP, leveraging inputs from experts at air agencies in the West and WESTAR-WRAP Work groups
    Dan Jaffe with post-docs for western U.S. ozone photochemistry data analysis, method development, research needs, and use of remote sensing as identified by WESTAR-WRAP members
      WESTAR agrees to take results and tools/methods and apply them, WESTAR letter of support
      Periodic briefings by Jaffe team during project, post-docs resident at CIRA one month/year
#14 – no change, awaiting policy / implementation strategies from Biden EPA
#16 – plan is to have Tom and Jay Baker help states with questions in SIP submittal and EPA review process, no plans for other contracted support
  WESTAR-WRAP will maintain operating agreement with CSU-CIRA for TSS / IWDW