## Slide 1: WRAP TSC/Co-Chairs Call Workplan Progress Update December 19, 2018
Tribal Data WG
Fire and Smoke WG
Oil and Gas WG
Regional Technical Operations WG
Regional Haze Planning WG

## Slide 2
Tribal Data Work Group

## Slide 3: Tribal Data Work Group
Co-Chairs: Kris Ray (Colville Tribes) and Emma Ruppell (Bishop Paiute Tribe)
Call Schedule: Monthly updates with committee and contractors
Website: http://www.wrapair2.org/tdwg.aspx (under development)
Current Tasks/Projects
  Working on the Tasks in the 2018 to 19 workplan
  Data analysis
  Outreach

## Slide 4: Tribal Data Work Group Work Products and Next Steps
Contract with the Institute of Tribal Environmental Professional at Norther Arizona University; EN3 Professionals LLC
  General WRAP outreach for RH
  Contact list for Tribes in the WRAP area
  Map updating – create interactive maps and bring in new layers of information
  Tribal AQS data gap study – which Tribes submit data and identification of issues
  Tribal NEI data gap study – Identification of Tribes submitting to the NEI, Tribes conducting EI but not submitting
  Tribal oil and gas EI studies – in coordination with OGWG
  Consultation Protocol – process and timing of Consultation opportunities
  WRAP webinars - Two or three planned, regional haze, WRAP tools, AQS or EI data
Next Steps
  Monthly progress calls

## Slide 5
Fire and Smoke Work Group
and

## Slide 6: Fire & Smoke Work Group
Co-Chairs: Sara Strachan, Josh Hall (on detail, raking)
Call Schedule: monthly or as needed
Website: http://www.wrapair2.org/FSWG.aspx
Current Tasks/Projects
  2014 WRAP FNEI data review
  Workplan revision

## Slide 7: Status Report for Fire & Smoke Work Group
2014 WRAP FNEI data review
  Approach
    Revise the fire portion of the 2014 Base Year inventory
  Status
    Contractor, Matt Mavko, needs about 40 hours to complete revisions
    Still on track to have it completed and passed to modelers by end of year/early 2019
  Milestones
    Discussed task during 12/13/18 workgroup call
  Coordination and Next Steps
    Matt will keep group notified when he completes inventory
    Revising workplan (dates and deliverables) for Jan. 16 deadline
    Next FSWG call: Jan. 28, presentation on Utah’s Smoke Management Plan
    Gearing up for next tasks: multi-year baseline and 2028 fire inventory projections

## Slide 8
Oil and Gas Work Group

## Slide 9: Oil and Gas Work Group (OGWG)
Co-Chairs:
  Amanda Brimmer, Regional Air Quality Council (RAQC), Denver, CO
  Mark Jones, New Mexico Environment Department, Santa Fe, NM
  Darla Potter, Wyoming DEQ - Air Quality Division, Cheyenne, WY
Call Schedule:
  OGWG - 2nd Tuesday, every other month @ noon MT
    December 11, 2018
    Upcoming - Special Workplan Call January 22, 2019
    Upcoming - February 12, 2019
  OGWG Project Management Team (PMT) Calls – as needed
    November 16
    Upcoming - January 9
Representation:
  Federal, state, local, TSC & other WG co-chairs, and consultants
Website:
  https://www.wrapair2.org/OGWG.aspx

## Slide 10: Status Report for Oil and Gas Work Group
Task 1: 2014 Base Year O&G Emissions Inventory | 
Approach: Contractor (Ramboll) performing work on following tasks: | Status/Deliverables
Inventory Compilation, Reconciliation, Data Gaps | Spreadsheet* + WG Discussion 8/14
2014 O&G Activity | Spreadsheet* + WG Discussion 8/14
Identify Emission Factors and Speciation Profiles for Oil and Gas Sources | PMT Discussion 8/20
State and industry survey | OGWG 10/9, PMT 9/28, 10/30, 11/16 WESTAR Council 10/10
Additional support to agencies on the survey (additional task) | Calls 12/7-11
Technical Improvements and Reporting | PMT Discussion 8/20
SMOKE-ready Emission Inventory Files | No work yet
Milestones: | 
Sept. 2018 – Literature review PowerPoint | 
Oct. 2018 – Survey finalized to send out | 
Apr. 2019 – SMOKE-ready 2014 O&G emissions inventory files | 
Coordination and Next Steps: | 
Assistance needed from States to complete survey (coordinate with local industry if needed) | 
OGWG and Project Management Team (PMT) review of draft work products | 
* Posted on OGWG webpage

## Slide 11: Survey Overview
Survey will be filled-out in two phases
  Phase 1: Agencies fill-out survey based on internal data sets
  Phase 2: Operators fill-out survey (top 3-5 operators in each basin)
12/11/18 OGWG Call

## Slide 12: Status Report for Oil and Gas Work Group
Task 2: Forecast 2028 (OTB & OTW Controls) Oil & Gas Emissions Inventory | 
Approach: Contractor (Ramboll) performing work on following tasks: | Status
Identify historic growth, supply, demand, and production decline | Compilation Complete
Identify a Range of Forecast Year Oil and Gas Scenarios | Next Step
Identify Rule Penetration and Effectiveness for Oil and Gas Sources: National, State, Local, Tribal | No Work Yet
Implement Regionally-Consistent 2028 Forecast (OTB & OTW controls) Emissions Inventory | “
SMOKE-ready Emission Inventory Files | “
Milestones: | 
May 2019 – Final Report | 
June 2019 – SMOKE-ready 2028 O&G emissions inventory files | 
Coordination and Next Steps: | 
OGWG and Project Management Team (PMT) review of draft work products | 

## Slide 13: Status, Schedule & Looking Ahead
12/11/18 OGWG Call

## Slide 14
Regional Technical Operations Work Group

## Slide 15: RTOWG Work Group
Co-Chairs:
  Gail Tonnesen (EPA R8)
  Kevin Briggs (CO CDPHE)
  Mike Barna (NPS ARD)
Call Schedule:
  Next call: late January 2019
  RTOWG co-chairs participating in other workgroup calls
Website:
  http://www.wrapair2.org/RTOWG.aspx

## Slide 16: Status Report for RTOWG
Joint RTOWG / Control Measures Subcommittee call, 12/12/18
  Overview of Control Measures Subcommittee’s “Reasonable Progress Source Identification and Analysis Protocol” – Curt Taipale (CDPHE)
  Options for Single-Source Visibility Ranking/Evaluation with Modeling Tools presentation – Ralph Morris (Ramboll)
Participated in the Monitoring Data and Glide Path Subcommittee call, 12/13/19
Participated in HAQAST haze and ozone calls; HAQAST meeting Jan. 3-4, 2019 in Phoenix

## Slide 17: Status Report for RTOWG
Development of initial 2014 modeling platform
  Approach
    Implement an initial modeling platform for 2014
  Status
    Modeling contract awarded to Ramboll for phase 1
  Milestones
    (see following slide)
  Coordination and Next Steps
    ~bi-weekly team calls

## Slide 18: Status Report for RTOWG

## Slide 19: Status Report for RTOWG

## Slide 20
Regional Haze Planning Work Group

## Slide 21
Co-Chairs: Tina Suarez-Murias (CARB) & Jay Baker (UT DEQ)
Call Schedule: 1st Tuesday every even month, noon-2PM Mountain Time
Website: https://www.wrapair2.org/RHPWG.aspx
Current Activities & Questions:
Deliverables from all five subcommittees prior to docket
Evaluating Work Group and Subcommittee Coordination, Overlap, and Roles
Figuring out task revisions for 2019 in Work Plan vs. State Responsibilities
Transition to Training for tool (deliverable) use and SIP writing
States assessing Source Controls in 2019 in order to Forecast for 2028
Regional Haze Planning Work Group
Notes: Sending out a calendar list to RHPWG to keep states on track with “what’s due” Action Items
Will likely meet once a month for process and training purposes

## Slide 22
Regional Haze Planning Work Group
REGIONAL HAZE (2018 Tasks) | IN PROGRESS or COMPLETE | TO DO in 2019 | ISSUES
Monitor Data Analysis | -Alternatives Analysis for MID Selection White Paper -States do Species Focus by Site -Patching/Substitution | -Glide Path Recalculation -Trends Analysis -New Natural Conditions end point only for this planning period | -Awaiting Final EPA Guidance on MID Selection (2018) and Natural Conditions (2019) -Progress Report requirements and responsibilities
Emission Inventory | -States Confirmed 2014 Inventories for most categories and completed White Paper | -Oil & Gas (Spring 2019) -Smoke & Fire (Spring 2019) -2028 Forecast and Trends | -EPA 2028 forecast from 2016 vs. 2014 differences -Multi-year Average Categories -Boundary Conditions & International Emissions
Air Quality Modeling | -Developing Categories for Source Apportionment | -Average multi-year categories -2014 Meteorology Model -Calculating RRF with MIDs | -Interplay of RHPWG & RTOWG for RH modeling -Reconciling WRAP work with EPA modeling -Is WEP necessary and affordable?
Source Analysis for Controls | -Screening Protocol White Paper | -Visibility as a Fifth Factor -Control Option “Clearinghouse”? | -States must do their own Analysis and have Emissions Reductions results by Fall 2019
Shared Database | --First Progress Report Oct. 5 -TSS v.2 ongoing development -Regional Haze Planning Overview | -Continue review of tools developed by CIRA collaborators -Develop educational and reference materials for TSS | -“Freezing” Data for Planning Purposes -Storing & Linking Reference Materials -Plan for future TSS v2 Progress Reports
Consultation & Coordination | -White Paper on Protocols | -Coordinate Training Modules -Contacts & Links | -Will Timeline & Work Plan help pace progress -Nexus between Tools, Training, & SIP Production

## Slide 23: Regional Haze Planning Work Group Monitoring Data & Glide Path Status Report
Approach
  Evaluate proposed EPA tracking metric with alternative extreme episodic event (E3) thresholds and other options for selecting the 20% Most Impaired Days (MID) in the west
  Set up Excel spreadsheet and R code analysis to test variables on 26 representative IMPROVE sites, which each State can use to analyze their IMPROVE sites using FED dataset
  Develop methodologies for evaluating Natural Condition alternative estimation techniques for future testing
Status
  Recommended EPA’s proposed metric as WRAP suggested metric methodology for Most Impaired Days
  Prepared draft document outlining potential alternative metrics, how to evaluate alternative, and coordination with other organizations
  Contractor support to develop data substitution methodologies
  Exploring ideas for natural condition estimation
  Updated data evaluation tools to include 2017 datasets
  Preparing draft summary documentation of work completed to date
Milestones
  Subcommittee summary document draft document under Work Group review in December
  Contractor preparing report documenting data patching and data substitution using State feedback
Coordination and Next Steps and Tasks
  Draft summary document presented to RHPWG (all states, FLMs, tribes, EPA) for feedback
  Research methodologies for Baseline and 2064 Natural Conditions adjustment (Glide Path slope and endpoints)
  Coordinate with Modeling and Emission Inventory subcommittee to determine metric needs for modeling
  Research methods for Uniform Rate of Progress adjustment (prescribed fire and international impacts)

## Slide 24: Regional Haze Planning Work Group Shared Database Status Report
Approach
  Assure that publically accessible database has useful information for states to use in SIP preparation
  Work with CIRA contacts to share state needs and evaluate design of TSS v.2
Status
  Reviewing Haze Analysis and Visibility Summary Tools on draft TSS v.2
  Comments compiled for CIRA collaborator’s monthly response
  Developing documents for eventual resource links on TSS v.2 (coordinate with other subcommittees)
Milestones
  Working on titles, labels and interpretation of some graphics
  Overview of Regional Haze Planning document soon to be added to docket
  Draft glossary available on TSS v.2 – will be updated
  Developing FAQ document
Coordination and Next Steps
  Working with RHPWG and other Subcommittees on documentation needs for posting to TSSv.2 or webpage
  Collaborators continue to develop updates for review – running list of most recent updates on TSS v.2 home page
  Subcommittee continues to suggest improvements through the SC Lead, who consolidates repetitious comments

## Slide 25: Regional Haze Planning Work Group Emissions Inventory & Modeling Protocol Status Report
Approach
  Collect and collate emissions data from all states (2014 and future forecasts)
  Photochemical modeling for CONUS western states
Status
  State comments/revisions on emissions are being used to create documentation for the modeling contractor
  Photochemical modeling contract reviewed before release
Milestones
  Completed review of 2014 NEI v2 and compiled revisions requested by states into report for RHPWG review and consensus prior to docket
Coordination and Next Steps
  Subcommittee Lead and Contractor formatting base year revisions into model ready format over next few weeks
  Work with RTO Work Group to secure contractor for baseline and future year modeling
  Get 2014 data from Oil & Gas and Fire & Smoke Work Groups model-ready by Spring 2019
  Coordinate with Fire & Smoke Work Group on multi-year averages to use for future year modeling

## Slide 26: Regional Haze Planning Work Group Control Measures Status Report
Approach
  Develop Reasonable Progress Protocol for States to identify and assess emissions reductions from Non-Mobile Anthropogenic Sources within their State
  Develop means to demonstrate these reductions improve visibility in Class I Areas
Status
  Interpret EPA proposed guidance for 80% of non-mobile anthropogenic sources (facility/unit/source category)
  Propose screening tools to identify sources (e.g. generally focus on SO2, SO4, NOx, and PM pollutants > 100 tpy; evaluate source emissions over distance from CIA: “Q/d > x”; and confirm sources with WRAP WEP analysis)
Milestones
  Develop and circulate schedule for States’ input to other Work Groups and contractors (pending)
  Draft WRAP Reasonable Progress Source Identification and Analysis Protocol to be shared with RHPWG soon
Coordination and Next Steps
  Review four-factor methods and visibility impact options (e.g. plume modeling, WEP)
  Work with other Work Groups on multi-year emissions averaging if needed for cost-benefit analysis or modeling
  Reconcile Area Source Emissions categories vs. Stationary Source facilities with multiple units for control analysis
  Determine needs for contractor assistance
Notes: -Circulate Screening Techniques “menu” as working draft to states for use as guidance selecting “target sources”
-Meeting on Tuesday (after) this was submitted – so report anything additional

## Slide 27: Regional Haze Planning Work Group Consultation and Coordination Status Report
Approach
  Recommend a framework for State/State, State/Local Air Agency, State/ FLM consultation and for coordination with EPA and Tribes
  Provide potential ideas for communication and outreach with stakeholders and the public
Status
  Prepared and presented three-tier framework for consultation & coordination with key informal consultation junctures identified
  Preparing white paper that provides more detail on the framework
  Coordinating with TDWG, FLMs, EPA to develop discussion questions to guide informal consultation efforts
Milestones
  Draft contractor report on Regional Haze Planning Readiness circulated to states for comment by 12/20
  Consensus on 12/11 from RHPWG on three-tier framework for consultation & coordination
Coordination and Next Steps
  Coordinate 2019 webinar schedule with TDWG trainings and set dates for webinars in consultation with other work groups and subcommittees
  Coordinate with TDWG and FLMs to update key contact lists
  Draft white paper for feedback from RHPWG
Notes: States should review the Planning Readiness draft report (sent to state leads) and submit their comments by December 20.
The three-tier framework for informal consultation/coordination was approved by consensus by the RHPWG, which will allow the subcommittee to move forward completing the draft white paper
Look forward to a schedule of educational webinars in 2019

## Slide 28
End of Workplan Progress Update