## Slide 1: Monthly Update on 2018-2019 WRAP Workplan May 29th, 2019 TSC and Work Group Co-Chairs Call
Tribal Data WG
Fire and Smoke WG
Oil and Gas WG
Regional Technical Operations WG
Regional Haze Planning WG

## Slide 2: Tribal Data Work Group

## Slide 3: Workplan Progress by Tribal Data Work Group
Workplan Progress over the Last Month
  National Tribal Forum on Air Quality: presentation/s; Info table w/ fact sheets; 1 Tribal WRAP member sign ups
  Approved data gap studies
  Updated versions of project materials posted to TDWG page
Workplan Tasks for the Next Two Months
  Complete finalization by consensus of products under contract (oil & gas study)
  Plan 2nd webinar
  Relay TDWG contractor feedback to PHPWG contractor on Consultation & Coordination Framework
  Format/package tribal contacts list into active tribes listserv for WRAP use

## Slide 4: Workplan Coordination Activities by Tribal Data Work Group
Workplan Coordination Occurring over the Last Month
  Presentation of workplan status to all WGs at Spring Mtg.
  Receipt & partial review of Consultation & Coordination Framework etc. from RHPWG.
  Oil and Gas Workgroup – ITEP, EN3 and TDWG drafted Tribal oil and gas related emissions
Workplan Coordination Needed over the Next Two Months
  RHPWG – submit to RHPWG combined or staggered- any reviews/comments of Framework (contractor/EN3, Co-chairs) to accompany C&G SC – requested reviews.
  Tribal contacts list – format & arrange for state planning use via RHPWG
  OGWG – webinar possibility?

## Slide 5: Fire and Smoke Work Group

## Slide 6: Workplan Progress by Fire and Smoke Work Group
Workplan Progress over the Last Month
  Baseline Wildfire Emissions Inventory development
    Reviewed whitepaper on Baseline Period Wildfire Emissions Estimates
    Provided feedback to contractor regarding methodology in whitepaper.
    Approved by consensus contractor work to develop baseline inventory.
  Began scoping out the Smoke Management Plan/Program mapping project
Workplan Tasks for the Next Two Months
  Baseline Wildfire Emissions Inventory development
    Review initial draft of Baseline Wildfire Emissions Inventory
    Review, approve, and forward to RH modelers Baseline Wildfire Emissions Inventory
  Continue scoping out the Smoke Management Plan/Program mapping project
  Begin discussions on future fire scenario development.

## Slide 7: Workplan Coordination Activities by Fire and Smoke Work Group
Workplan Coordination Occurring over the Last Month
  Coordination between Representative baseline and Future Fire Scenario sub-group and Fire and Smoke Workgroup.
Workplan Coordination Needed over the Next Two Months
  Coordinate with RTOWG for evaluation of sensitivity of modeled baseline vs. base year 20% most impaired days. E.g., how sensitive is modeled 20% most impaired days to modulating wildfire emissions?
  Coordinate with RTOWG and RHPWG on questions:
    How will future fire scenario modeling be used in RH planning? What specific questions need to be addressed?
    Given limited resources, how many future year modeling sensitivity scenarios are possible? How many future fire scenarios should be generated?
  Coordinate with TSC. What other questions beyond RH planning are we looking to address with the development of future fire emissions scenarios?

## Slide 8: Oil and Gas Work Group

## Slide 9: Workplan Progress by Oil and Gas Work Group
Workplan Progress over the Last Month
  OGWG and PMT review and feedback
  Base Year Inventory – Underway
    WRAP OGWG Baseline Year Survey Data (memo for OGWG review - May)
  Forecast Scenarios (On-the-books controls) – Underway
  Forecast (Additional Reasonable controls)
    Initiated discussions with RHPWG-Control Measures Subcommittee
Workplan Tasks for the Next Two Months
  Task 1: Base Year Inventory
    Draft Inventory (v2) and Report (for OGWG review – anticipated end of May)
    Final Inventory (v2) (anticipated mid-June)
  Task 2: Forecast 2028 Inventory (On-the-books controls) – Forecast scenarios
  Task 3: Forecast 2028 Inventory (Additional Reasonable controls) – Summer

## Slide 10: Workplan Coordination Activities by OGWG
Workplan Coordination Occurring over the Last Month
  April 4 & May 6 – Project Management Team Calls
    Coordinate and PMT feedback with Ramboll
  April 9 – OGWG Bi-Monthly Call
    Tribal Oil & Gas Outreach Progress
    BLM Air Resource Management Studies
  Assistance from Agencies on Forecast Scenarios
Workplan Coordination Needed over the Next Two Months
  RHPWG Control Measures Subcommittee – Identification of future O&G controls
  June 4 – Project Management Team Call
  June 11 – OGWG Bi-Monthly Call
    Agenda under development
  June 20 – RHPWG Quarterly Outreach Webinar
    OGWG summary under development
  OGWG and PMT review and feedback on draft work products

## Slide 11: Regional Technical Operations Work Group

## Slide 12: Workplan Progress by RTOWG
Workplan Progress over the Last Month
  RTOWG call 5/23/19
    NPS ammonia modeling study
    Receipt of WRAP 2014 Shakeout v1 platform at IWDW and TSSv2
    EPRI International Haze Study status report
    Status of 2016 National Collaborative Emissions Modeling Platform
    WRAP Regional Haze Modeling Scenarios and Schedule
  EPA model evaluation forum on 2016 national modeling, 5/2/19
  NASA HAQAST haze call, 5/20/19
  Review WRAP 2014 Shake-Out Study Phase III Scope of Work (SOW)

## Slide 13: Workplan Progress by RTOWG
Workplan Tasks for the Next Two Months
  Finalize Phase III SOW
  Generate new version of the 2014 base case (v2) with lessons learned from v1
  Re-run GEOS-Chem global model to estimate
    International impacts
    Estimate for ‘natural conditions’
  Finalize MPE results with improved inputs
  Fire plume rise sensitivity (and possibly others)
  Updated Emissions Inputs
    all CA anthro data
    OGWG inputs
    Minor corrections
    EI & MP Subcommittee drafting memo to summarize input changes

## Slide 14: Regional Haze Planning Work Group

## Slide 15: Workplan Progress by Regional Haze Planning Work Group
Workplan Progress over the Last Month
  Consensus on Overview of Regional Haze Planning (moved to Docket)
  Review of the Q/d analysis deliverables http://views.cira.colostate.edu/tssv2/Emissions/QDAnalysis.aspx
Workplan tasks for the Next Two Months
  Plan for the June 20th Milestone Webinar
  Consensus on the WRAP Communication Framework

## Slide 16: Workplan Coordination Activities by Regional Haze Planning Work Group
Workplan Coordination Occurring over the Last Month
  Work with Coordination and Glide Path SC in planning a Milestone Webinar in June
  Coordination with all subcommittees to move work products through the consensus process
    Q/d analysis
    Overview of Regional Haze Planning
Workplan Coordination Needed over the Next Two Months
  Finalize consensus on WRAP Communication Framework
  Coordinate with FSWG and OGWG on the June webinar
  Coordinate with CGP Subcommittee on the development of Regional Haze Storyboard

## Slide 17: Workplan Progress by Coordination and Glide Path Subcommittee
Workplan Progress over the Last Month
  Task 6.3: Develop New Materials
    D) Storyboard – Haze in the West
      Team has drafted an outline of the storyboard
    E) Webinar Presentations to States
      Next milestone webinar scheduled for June 20th, 2019. Focus on Fire emissions, O&G Survey Success, EI Projections, and State Q/d status updates
  Task 7.1: Review TSS v1 for Priority Needs
    Draft “TSS Priorities” document distributed to RTOWG and EI&MP Subcommittee chairs for feedback
  Task 7.2: Coordinate and Review TSS v2 Monitor Data Tool Development
    Monthly presentations on new metrics and tools from CIRA on TSS progress
Workplan Tasks for the Next Two Months
  Task 1.2: Analyze monitor data trends
    Update from ARS and Brandon (Montana) on the status of the trend analysis and natural conditions alternative ideas
  Task 6.3: Develop New Materials
    B) Glossary & C) FAQs
      Potential for contractor support. Creation of scope of work to detail deliverables
  Task 8.2: Establish Consultation-Coordination Framework
    Plan to integrate new FLM and tribal contact information into one centralized location

## Slide 18: Workplan Coordination by Coordination and Glide Path Subcommittee
Workplan Coordination Occurring over the Last Month
  The subcommittee coordinated with the following entities:
    RTOWG – Draft FLM Priorities Document Review
    EI&MP Sub – Draft FLM Priorities Document Review
    FLMs – Frank updated the list of FLM contacts before his retirement
Workplan Coordination Needed over the Next Two Months
  Fire Smoke Work Group – Potential inclusion in June 20, 2019 webinar
  O&G Work Group - Potential inclusion in June 20, 2019 webinar for survey success
  EI&MP Sub - Potential inclusion in June 20, 2019 webinar for EI projections
  Interested states - Inclusion in June 20, 2019 webinar for Q/d status

## Slide 19: Workplan Progress by EI&MP Subcommittee
Workplan Progress over the Last Month
  2014 Base Case (Shakeout v2) emissions changes submitted to contractor
    Pima County point source updates
    Sector change for N.D. point source
    California – complete replacement for anthropogenic sources (custom process underway)
    Other expected changes include O&G and boundary condition updates
Workplan Tasks for the Next Two Months
  Send out memo describing Shakeout v2 updates
  Collect representative baseline emissions updates from states (June 20 deadline)
  Procedural guidance for OTB emissions to be submitted by states (Aug 1 deadline)

## Slide 20: Workplan Coordination by EI&MP Subcommittee
Workplan Coordination Occurring over the Last Month
  O&G Workgroup reviewed v1 emissions;
  O&G v2 emissions will come from contractor based on state comments
Workplan Coordination Needed over the Next Two Months
  v2 shakeout, representative baseline, and OTB modeling scenarios require coordination as neded with O&G WG, contractor, Fire & Smoke WG,
  Coordinate with Communication subcommittee to provide guidance to states on what is needed from them for the different modeling scenarios.

## Slide 21
Workplan Progress over the Last Month
  WRAP contracted with Ramboll to complete a Q/d analysis for Class I areas in western states
  Completed Q/d analysis work products have been reviewed by RHPWG
  Spreadsheet and database tools are now available on the TSS
Workplan Tasks for the Next Two Months
  Begin to identify 2028 control strategies for incorporation in 2028 inventory
    Many states are notifying sources and beginning the control strategy analysis, some states already working on the analysis
    Draft Source Control Assessment Considerations memo being prepared to assist states in performing the four-factor analysis
WRAP goal: complete by late 2019
Workplan Progress by Control Measures Subcommittee

## Slide 22
Workplan Coordination Occurring over the Last Month
  Briefed RHPWG on Q/d analysis and shared with other states outside of the CM Subcommittee
Workplan Coordination Needed over the Next Two Months
  Coordination call with the O&G Workgroup to discuss potential control options for oil and gas sector
  Coordinate with EI &MP Subcommittee on timing of conversations with sources to generate/confirm emission inventory inputs for modeling
Workplan Coordination by Control Measures Subcommittee

## Slide 23
End of Workplan Progress Update