## Slide 1: Monthly Update on 2018-2019 WRAP Workplan June 26th, 2019 TSC and Work Group Co-Chairs Call
Tribal Data WG
Fire and Smoke WG
Oil and Gas WG
Regional Technical Operations WG
Regional Haze Planning WG

## Slide 2: Tribal Data Work Group

## Slide 3: Workplan Progress by Tribal Data Work Group
Workplan Progress over the Last Month
  Contracted/EN3 review & comments on CC Framework – “redline” draft of Framework based on the review
Workplan Tasks for the Next Two Months
  Complete finalization by consensus of products under contract (oil & gas study)
  Plan 2nd webinar
  Relay TDWG/contractor feedback to RHPWG contractor on Consultation & Coordination Framework
  Send participation letter for TDWG
  Create “active tribes” section of tribal contacts list based on participation letter responses

## Slide 4: Workplan Coordination Activities by Tribal Data Work Group
Workplan Coordination Occurring over the Last Month
  EN3 continued outreach with O&G tribes
Workplan Coordination Needed over the Next Two Months
  RHPWG – submit to RHPWG/Ramboll combined or staggered- any reviews/comments of Framework (contractor/EN3, Co-chairs) to accompany C&G SC – requested reviews. Target July 8
  Review turn-around revision from Ramboll by July 18 (TDWG call), possible joint call w/ CGSC early Aug
  Tribal contacts list – format & arrange for state planning use via RHPWG
  OGWG – webinar possibility? Remaining EI’s from contacted tribes- share with OGWG

## Slide 5: Fire and Smoke Work Group

## Slide 6: Workplan Progress by Fire and Smoke Work Group
Workplan Progress over the Last Month
  Baseline Wildfire Emissions Inventory development
    Reviewed & approved methodology for Baseline Period Wildfire Emissions Estimates
    Contractor working on baseline inventory
  Continued scoping out the Smoke Management Plan/Program mapping project
Workplan Tasks for the Next Two Months
  Baseline Wildfire Emissions Inventory development
    Finalize Baseline Wildfire Emissions Inventory
  Continue scoping out the Smoke Management Plan/Program mapping project
  Begin discussions on future fire scenario development.

## Slide 7: Workplan Coordination Activities by Fire and Smoke Work Group
Workplan Coordination Occurring over the Last Month
  Coordination between Representative Baseline and Future Fire Scenario sub-group and Fire and Smoke Workgroup.
Workplan Coordination Needed over the Next Two Months
  Coordinate with RTOWG for evaluation of sensitivity of modeled baseline vs. base year 20% most impaired days. e.g., how sensitive is modeled 20% most impaired days to modulating wildfire emissions?
  Coordinate with RTOWG and RHPWG on questions:
    How will future fire scenario modeling be used in RH planning? What specific questions need to be addressed?
    Given limited resources, how many future year modeling sensitivity scenarios are possible? How many future fire scenarios should be generated?
  Coordinate with TSC. What other questions beyond RH planning are we looking to address with the development of future fire emissions scenarios?

## Slide 8: Oil and Gas Work Group

## Slide 9: Workplan Progress by Oil and Gas Work Group
Workplan Progress over the Last Month
  OGWG and PMT review and feedback
  Baseline Inventory – Underway
    WRAP OGWG Draft Baseline Inventory (v2) and Report [v2 integrated OGWG survey data] (for OGWG review – June 25 comments were due)
  Forecast Scenarios – Underway
Workplan Tasks for the Next Two Months
  Task 1: Baseline Inventory
    Final Inventory (v2) (anticipated late June)
    Survey Data Memo [gas compositions and controls] (anticipated in early-July)
  Task 2: Forecast 2028 Inventory (On-the-books controls) – Summer
    Medium forecast scenario being finalized based on previous agency input
    Developing low and high forecast scenario methodology
  Task 3: Forecast 2028 Inventory (Additional Reasonable controls) – Summer
    Single forecast scenario and Integrate OGWG survey data

## Slide 10: Workplan Coordination Activities by OGWG
Workplan Coordination Occurring over the Last Month
  June 4 – Project Management Team Call
    Coordinate and PMT feedback with Ramboll
  June 11 – OGWG Bi-Monthly Call
    Proposed Navajo Nation Minor Source Regulations
    RHPWG Control Measures Subcommittee – O&G Source Coordination
  June 20 – RHPWG Quarterly Outreach Webinar included OGWG
Workplan Coordination Needed over the Next Two Months
  July 2 – Project Management Team Call
  August 13 – OGWG Bi-Monthly Call
  OGWG and PMT review and feedback on draft work products
Coordination (External to WRAP) Occurring / Needed
  EPA’s 2016 Modeling Platform – availability of OGWG Baseline Inventory
  2017 NEI – account for inventory improvements

## Slide 11: Regional Technical Operations Work Group

## Slide 12: Workplan Progress by RTOWG
Workplan Progress over the Last Month
  2014 Shakeout v.2 modeling underway
Workplan Tasks for the Next Two Months
  Review of Shakeout v.2 modeling results
  Representative baseline modeling
    Reflect current emissions under ‘normal’ conditions
    Basis for 2028 modeling
    Use updated GEOS-Chem results for boundary conditions
  White paper on new GEOS-Chem simulations to evaluate
    Natural conditions
    International contributions

## Slide 13: Workplan Coordination Activities by RTOWG
Workplan Coordination Occurring over the Last Month
  Calls we participated in
    WRAP Regional Haze Planning - Summer Solstice 2019 Outreach
    OGWG
    RHPWG
    EPA-State modeling review workgroup
    NASA HAQAST haze call
Workplan Coordination Needed over the Next Two Months
  RTOWG call, 7/16/19
  WAQS 2014 Shakeout v1 / v2 progress, 7/17/19
  Emission updates
    Shakeout v.2
    Baseline modeling

## Slide 14: Regional Haze Planning Work Group

## Slide 15: Workplan Progress by Regional Haze Planning Work Group
Workplan Progress and Coordination over the Last Month
  June 20th Milestone Webinar
  Coordinate with FSWG & OGWG on the June webinar
Workplan tasks and Coordination for the Next Two Months
  Consensus on the WRAP Communication Framework
  Coordinate with CGP Subcommittee on the development of Regional Haze Storyboard

## Slide 16: Workplan Progress by Coordination and Glide Path Subcommittee
Workplan Progress over the Last Month
  Task 6.3: Develop New Materials
    D) Storyboard – Haze in the West
      Team has drafted an outline of the storyboard. Looking to hire a contractor to produce a mock-up that can be presented to the states. Aiming to present on the Fall Periodic Webinar.
    E) Webinar Presentations to States
      Next milestone webinar targeting Fall 2019
  Task 7.1: Review TSS v1 for Priority Needs
    Coordinating call with RTOWG to discuss “TSS Priorities” document feedback
  Task 7.2: Coordinate and Review TSS v2 Monitor Data Tool Development
    Monthly presentations on new metrics and tools from CIRA on TSS progress
    We need to "freeze" the TSS version of the IMPROVE base data and RHR/Impairment metrics for planning period.
Workplan Tasks for the Next Two Months
  Task 1.2: Analyze monitor data trends
    Brandon (Montana) and ARS planning on giving a short update on the next call then hosting an August webinar on the results of the trend analysis and natural conditions alternative ideas project.
  Task 6.3: Develop New Materials
    B) Glossary & C) FAQs
      Potential for contractor support. Creation of scope of work to detail deliverables
  Task 8.2: Establish Consultation-Coordination Framework
    Ramboll is working with the C&GP sub and the TDWG to integrate feedback into a final product. FLM’s also drafting content for 1 pagers.

## Slide 17: Workplan Coordination Activities by Coordination and Glide Path Subcommittee
Workplan Coordination Occurring over the Last Month
  The subcommittee coordinated with the following entities:
    RTOWG – Draft FLM Priorities Document Review
    EI&MP Sub – Draft FLM Priorities Document Review
    FLMs – Updated agendas and Coordination Framework
Workplan Coordination Needed over the Next Two Months
  RTOWG – Coordination on Natural Conditions Project findings and opportunities to model outcomes for future planning periods.

## Slide 18: Workplan Progress by EI&MP Subcommittee
Workplan Progress over the Last Month
  2014 Base Case (Shakeout v2) emissions changes being processed by contractor
    Identified minor issues with some state inputs and corrected
  Representative Baseline emissions changes received from states
Workplan Tasks for the Next Two Months
  Send out memo describing Shakeout v2 updates
  Compile and reformat representative baseline emissions updates from states
  Procedural guidance for OTB emissions to be submitted by states

## Slide 19: Workplan Coordination by EI&MP Subcommittee
Workplan Coordination Occurring over the Last Month
  O&G Workgroup reviewed v1 emissions;
  O&G v2 emissions will come from contractor based on state comments
Workplan Coordination Needed over the Next Two Months
  v2 shakeout, representative baseline, and OTB modeling scenarios require coordination as needed with O&G WG, contractor, Fire & Smoke WG,
  Coordinate with Communication subcommittee to provide guidance to states on what is needed from them for the different modeling scenarios.

## Slide 20
Workplan Progress over the Last Month
  Q/d analysis work products complete
  Spreadsheet and database tools on the TSS
  Ramboll created an interactive map of Class I areas with radius of impact and facilities with Q > 4,000 tpy – posted on TSS
Workplan Tasks for the Next Two Months
  Begin to identify 2028 control strategies for incorporation in 2028 inventory
    Many states are notifying sources and beginning the control strategy analysis, some states already working on the analysis
    Draft Source Control Assessment Considerations memo being prepared to assist states in performing the four-factor analysis
WRAP goal: complete by late 2019
Workplan Progress by Control Measures Subcommittee

## Slide 21
Workplan Coordination Occurring over the Last Month
  Coordination call (on May 28th) with the O&G Workgroup discussing potential control options for oil and gas sector
Workplan Coordination Needed over the Next Two Months
  Continued coordination calls with the O&G Workgroup
    Montana coordinating western state RH O&G call to gauge interest in discussing potential control options for oil and gas sector
      Several states have expressed interest: Colorado, Montana, North Dakota, Utah and Wyoming
  Coordinate with EI &MP Subcommittee on timing of conversations with sources to generate/confirm emission inventory inputs for modeling
Workplan Coordination by Control Measures Subcommittee

## Slide 22
End of Workplan Progress Update