## Slide 1: Monthly Update on 2018-2019 WRAP Workplan July 31st, 2019 TSC and Work Group Co-Chairs Call
Tribal Data WG
Fire and Smoke WG
Oil and Gas WG
Regional Technical Operations WG
Regional Haze Planning WG

## Slide 2: Tribal Data Work Group

## Slide 3: Workplan Progress by Tribal Data Work Group
Workplan Progress over the Last Month
  Contracted/EN3 review & comments on CC Framework – “redline” draft of Framework based on the review
Workplan Tasks for the Next Two Months
  Complete finalization by consensus of products under contract (oil & gas study)
  Plan 2nd webinar
  Relay TDWG/contractor feedback to RHPWG contractor on Consultation & Coordination Framework
  Send participation letter for TDWG
  Create “active tribes” section of tribal contacts list based on participation letter responses

## Slide 4: Workplan Coordination Activities by Tribal Data Work Group
Workplan Coordination Occurring over the Last Month
  EN3 continued outreach with O&G tribes
Workplan Coordination Needed over the Next Two Months
  RHPWG – submit to RHPWG/Ramboll combined or staggered- any reviews/comments of Framework (contractor/EN3, Co-chairs) to accompany C&G SC – requested reviews. Target July 8
  Review turn-around revision from Ramboll by July 18 (TDWG call), possible joint call w/ CGSC early Aug
  Tribal contacts list – format & arrange for state planning use via RHPWG
  OGWG – webinar possibility? Remaining EI’s from contacted tribes- share with OGWG

## Slide 5: Fire and Smoke Work Group

## Slide 6: Workplan Progress by Fire and Smoke Work Group
Workplan Progress over the Last Month
  Finishing up Representative Baseline Fire Emissions Inventory
  Preparing Smoke Management Plan survey for states and tribes
Workplan Tasks for the Next Two Months
  Submit RB EI to modelers
  Prepare Future Fire Scenarios EI for sensitivity runs
  Distribute SMP survey, collect responses
  Help EPA prepare Fire EI for 2017 NEI

## Slide 7: Workplan Coordination Activities by Fire and Smoke Work Group
Workplan Coordination Occurring over the Last Month
  None
Workplan Coordination Needed over the Next Two Months
  Need to ask TDWG for tribal SMP contact list
  RB EI handoff to RTOWG

## Slide 8: Oil and Gas Work Group

## Slide 9: Workplan Progress by Oil and Gas Work Group
Workplan Progress Over the Last Month
  OGWG and Project Management Team (PMT) review and feedback
  Baseline Inventory – Underway
    WRAP OGWG Draft Baseline Inventory (v2) and Report [v2 integrated OGWG survey data]
      Six States (NM, UT, ND, MT, WY, AK) – Complete
      Colorado - Underway
    Survey Data Memo [gas compositions and controls] – Complete
  Forecast Scenarios – Underway
Workplan Tasks for the Next Two Months
  Task 1: Baseline Inventory
    Final Inventory (v2) (anticipated mid-August)
  Task 2: Forecast 2028 Inventory (On-the-books controls) – Mid-August
    Medium forecast scenario being finalized based on previous agency input
    Developing low and high forecast scenario methodology
  Task 3: Forecast 2028 Inventory (Additional Reasonable controls) – Late-Summer
    Single forecast scenario and integrate OGWG survey data

## Slide 10: Workplan Coordination Activities by OGWG
Workplan Coordination Occurring Over the Last Month
  June 26 – WG feedback due on Baseline 2014-16 O&G EI for WESTAR-WRAP Region
  July 2 – Project Management Team Call
    Coordinate and PMT feedback with Ramboll
  July 16 – Colorado 2014/2016 O&G EI Call
  July 17 – Western State RH O&G Call (OGWG lead on future controls identification)
Workplan Coordination Needed Over the Next Two Months
  August 6 & 20, Sept. 3 & 17 – Project Management Team Calls
  August 13 – OGWG Bi-Monthly Call
  OGWG and PMT review and feedback on draft work products
  Coordination with RHPWG Control Measures Subcommittee
Coordination (External to WRAP) Occurring / Needed
  EPA’s 2016 Modeling Platform – availability of OGWG baseline inventory
  2017 NEI – account for inventory improvements

## Slide 11: Regional Technical Operations Work Group

## Slide 12: Workplan Progress by RTOWG
Workplan Progress over the Last Month
  2014 Shakeout v.2 modeling underway
Workplan Tasks for the Next Two Months
  Review of Shakeout v.2 modeling results
  Representative baseline modeling
    Reflect current emissions under ‘normal’ conditions
    Basis for 2028 modeling
    Use updated GEOS-Chem results for boundary conditions
      Model runs are currently underway
  White paper on new GEOS-Chem simulations to evaluate
    Natural conditions
    International contributions

## Slide 13: Workplan Coordination Activities by RTOWG
Workplan Coordination Occurring over the Last Month
  Calls we participated in
    RHPWG (7/2)
    RTOWG co-chair coordination calls (7/8 and 7/22)
    OGWG (7/2)
      Participated in the Colorado ‘special O&G call’ on July 16
    2016 EPA-State modeling review forum (6/26 and 7/24)
      Also participated in some of the workgroup calls.
    NASA HAQAST background O3 haze call (7/3)
    IWDW call on July 15
    RHPWG Emission Inventory and Modeling Protocol subcommittee (7/25)
Workplan Coordination Needed over the Next Two Months
  WAQS 2014 Shakeout v1 / v2 progress, postponed from 7/24 to a later date
  Emission updates (RHPWG EI and MP subcommittee)
    Shakeout v.2
    Baseline modeling

## Slide 14: Intermountain West Data Warehouse
The IWDW Steering Committee had a call on July 15
The IWDW is certainly a part of the RH planning effort since it houses the model results, monitoring analysis, and the TSS. The IWDW also contributes some funding, staff support such as CIRA staff support, and in-kind services which also support the RH SIP effort.
On the call the IWDW steering committee discussed:
  Status of Technical Activities and Data Warehouse
    Brief tour of the updated IWDW website including the TSS website and 2014 modeling archive for the WRAP RH modeling effort
  Expiration of MOU amongst the cooperators
  Future NEPA Projects
  Status of Budget and Discuss Future Funding
  Monitoring Network Assessment

## Slide 15: Regional Haze Planning Work Group

## Slide 16
Workplan Progress and Coordination over the Last Month
  Coordinated with C&GP and EI&MP Subcommittees to present task updates on monthly call (July 2, 2019)
  Coordinated with O&G Workgroup on preliminary oil & gas state call
Workplan tasks and Coordination for the Next Two Months
  Final review of and consensus on the WRAP Communication Framework
  Development of Regional Haze in the West Storyboard
  Coordinate ongoing discussions of controls and modeling – both require states to consult with sources
  Next milestone webinar planned for mid- to late-September
Workplan Progress & Coordination by Regional Haze Planning Work Group

## Slide 17: Workplan Progress by Coordination and Glide Path Subcommittee
Workplan Progress over the Last Month
  Task 6.3: Develop New Materials
    D) Storyboard – Haze in the West
      Team has drafted an outline of the storyboard. Looking to hire a contractor to produce a mock-up that can be presented to the states. Aiming to present on the Fall Periodic Webinar.
    E) Webinar Presentations to States
      Planning next milestone webinar for mid- to late-September 2019
  Task 7.1: Review TSS v1 for Priority Needs
    Coordinating call with RTOWG to discuss “TSS Priorities” document feedback
  Task 7.2: Coordinate and Review TSS v2 Monitor Data Tool Development
    Monthly presentations on new metrics and tools from CIRA on TSS progress
    We need to "freeze" the TSS version of the IMPROVE base data and RHR/Impairment metrics for planning period.
Workplan Tasks for the Next Two Months
  Task 1.2: Analyze monitor data trends
    Brandon (Montana) and ARS presented results of the trend analysis and natural conditions alternatives task on the last subcommittee call. Currently planning an August webinar to share more detailed results.
  Task 6.3: Develop New Materials
    B) Glossary & C) FAQs
      Potential for contractor support. Creation of scope of work to detail deliverables.
  Task 8.2: Establish Consultation-Coordination Framework
    Deadline of August 15 for review and comment on latest draft of the Framework.

## Slide 18: Workplan Coordination Activities by Coordination and Glide Path Subcommittee
Workplan Coordination Occurring over the Last Month
  The subcommittee coordinated with the following entities:
    TDWG – New edits to the Consultation-Coordination Framework document
Workplan Coordination Needed over the Next Two Months
  RTOWG – Coordination on Natural Conditions project findings and opportunities to model outcomes for future planning periods.

## Slide 19
Workplan Progress by EI&MP Subcommittee
Workplan Progress over the Last Month
  2014 Base Case (Shakeout v2) emissions changes being processed by contractor
    Identified minor issues with some state inputs and corrected
  Compiled/Reformatted representative baseline emissions updates from states
Workplan Tasks for the Next Two Months
  Send out memo describing Shakeout v2 updates
  Procedural guidance for preparing OTB/OTW emissions updates
  OTB/OTW emissions to be submitted by states in August

## Slide 20: Workplan Coordination Activities by EI&MP Subcommittee
Workplan Coordination Occurring over the Last Month
  O&G Workgroup reviewed v1 emissions
  O&G v2 emissions will come from contractor based on state comments
Workplan Coordination Needed over the Next Two Months
  v2 shakeout, representative baseline, and OTB modeling scenarios require coordination as needed with O&G WG, contractor, Fire & Smoke WG,
  Coordinate with C&GP subcommittee to provide guidance to states on what is needed from them for the different modeling scenarios

## Slide 21
Workplan Progress over the Last Month
  Most states are beginning the control strategy analysis
  Discussed potential nonpoint/area source analysis
Workplan Tasks for the Next Two Months
  Begin to identify 2028 control strategies for incorporation in 2028 inventory
    Draft Source Control Assessment Considerations memo being prepared to assist states in performing the four-factor analysis
Workplan Progress by Control Measures Subcommittee

## Slide 22
Workplan Coordination Occurring over the Last Month
  Coordinated with O&G Workgroup and subset of oil and gas states for preliminary discussion of potential control options
Workplan Coordination Needed over the Next Two Months
  Continued coordination needed with the O&G Workgroup
  Coordinate with EI &MP Subcommittee on timing of conversations with sources to generate/confirm emission inventory inputs for modeling
Workplan Coordination Activities by Control Measures Subcommittee

## Slide 23
End of Workplan Progress Update