## Slide 1: Monthly Update on 2018-2019 WRAP Workplan December 4th, 2019 TSC and Work Group Co-Chairs Call
Tribal Data WG
Fire and Smoke WG
Oil and Gas WG
Regional Technical Operations WG
Regional Haze Planning WG

## Slide 2: Tribal Data Work Group

## Slide 3: Workplan Progress by Tribal Data Work Group
Workplan Progress over the Last 2 Months
  Draft of TDWG participation letter; reviewed
  Tribal Oil & Gas report – distributed to subject tribes
  Planning calls/webinar with ITEP
Workplan Tasks for the Next Two Months
  Tribal Oil & Gas report – distribution to OGWG – possibility of comments/edits
  Webinar with ITEP- debrief
  Send TDWG participation letter – via WRAP staff/WRAP web service
  Do a round of updating to tribal contacts list with “active tribes”

## Slide 4: Workplan Coordination Activities by Tribal Data Work Group
Workplan Coordination Occurring over the Last Month
  Webinar/planning calls (TDWG & ITEP)
Workplan Coordination Needed over the Next Two Months
  Any comments from OGWG on EN3’s report (originally asked for 2 week turnaround)
  Webinar – debrief (TDWG & ITEP)
  Any major updates on contact list to other WGs

## Slide 5: Fire and Smoke Work Group

## Slide 6: Workplan Progress by Fire and Smoke Work Group
Workplan Progress over the Last Month
  Held 2 RBFFS calls and one FSWG call
  Reviewed WESTAR-WRAP Modeling Scenarios draft V5 document,
    Discussion around this shaped framework for generating future fire scenario
    Matt Mavko produced a memo outlining the concept for the future wildfire scenario, which was discussed via email.
    Matt generating a future fire scenario based on these discussions
  Discussed ideas for the future of FETS, perhaps as a passive repository with fixed data structure. An easier framework to manage that could still add value.
  Paul gave status of smoke management programs survey, next steps are figuring out how to port info to web.
Workplan Tasks for the Next Two Months
  Continue discussing FETS ideas
  Continue looking at web display of smoke management programs survey
  Matt Mavko generating Rep Baseline and Future Fire scenario reports.

## Slide 7: Workplan Coordination Activities by Fire and Smoke Work Group
Workplan Coordination Occurring over the Last Month
  Held 2 RBFFS calls and one FSWG call
  Coordinated with RTOWG on planned modeling runs.
    Reviewed WESTAR-WRAP Modeling Scenarios draft V5 document
Workplan Coordination Needed over the Next Two Months
  ?

## Slide 8: Oil and Gas Work Group

## Slide 9: Workplan Progress by Oil and Gas Work Group
Workplan Progress Over the Last Month
  OGWG and Project Management Team (PMT) review and feedback
  Tasks 2, 3, 4 – Underway
Workplan Tasks for the Next Two Months
  Task 2: Forecast 2028 Inventory (OTB & OTW)
    “Reduced Legacy Well Activity” and “Increased Horizontal Well Activity” Scenarios
    No additional controls analysis
  Task 3: Forecast 2028 Inventory (Additional Reasonable controls)
    Methodology by which emission control estimates may be made by regulatory agencies
  Task 4: Agency Program Review Task
    Emphasis on describing state programs with agency input

## Slide 10: Workplan Coordination Activities by OGWG
Workplan Coordination Occurring Over the Last Month
  Nov. 12 – Project Management Team Call
  OGWG and PMT review and feedback on draft work products
    Alternate Scenarios Draft Report/Memo (2 scenarios included) & spreadsheets
    Additional Reasonable Controls Report/Memo
    Agency Input to describe state programs
Workplan Coordination Needed Over the Next Two Months
  Dec. 10 – OGWG Bi-Monthly Call
  Dec. 13 – Deadline for OGWG and PMT review and feedback on draft work products
    OGWG Agency Program Review Memo and spreadsheet
  Dec. 16 – Project Management Team Call
  Jan. 21 – Project Management Team Call
  Coordination with RHPWG Control Measures Subcommittee
Coordination (External to WRAP) Occurring / Needed
  EPA’s 2016 Modeling Platform Collaborative – availability of OGWG baseline & future inventory
  2017 NEI – account for inventory improvements

## Slide 11: Regional Technical Operations Work Group

## Slide 12: Workplan Progress by RTOWG
Workplan Progress over the Last Month
  Sensitivity simulations
    Fire plume rise
    BEIS v. MEGAN biogenic emissions
    Treatment of explicit elements
  Partial CAMx 2014v2 model performance evaluation
  Discussion of products to include in TSSv2

## Slide 13: Workplan Progress by RTOWG
Workplan Progress over the Last Month (cont’d)
  Emission sectors to update for representative baseline and 2028 On the Books inventories
Source Sector | RepBase | 2028 OTB | 2028 SMOKE Required
California All Sectors 12WUS2 | CARB-2014v2 | CARB-2028 | Yes-UNC (T4.1)
WRAP Fossil EGU w/ CEM | WRAP-RB-EGU | WRAP-2028-EGU1 | Yes-Ramboll (T4.2)
WRAP Fossil EGU w/o CEM | WRAP-RB-EGU | WRAP-2028-EGU | Yes-Ramboll (T4.2)
WRAP Non-Fossil EGU | EPA-2016v1 | EPA-2028v1 | Yes-Ramboll (T4.2)
Non-WRAP EGU | EPA-2016v1 | EPA-2028v1 | No (EPA Platform)
O&G WRAP O&G States | WRAP-RB-O&G | WRAP-2028-O&G | Yes-UNC (T4.3)
O&G WRAP Other States | EPA-2016v1 | EPA-2028v1 | Yes-UNC (T4.3)
O&G non-WRAP States | EPA-2016v1 | EPA-2028v1 | Yes-UNC (T4.3)
WRAP Non-EGU Point2 | WRAP-2014v2 | EPA-2028v1 | Yes-Ramboll
Non-WRAP non-EGU Point | EPA-2016v1 | EPA-2028v1 | Yes-Ramboll
On-Road Mobile 12WUS2 | WRAP-2014v2 | WRAP-2028-Mobile | No (WRAP MS study)
On-Road Mobile 36US | EPA-2016v14 | EPA-2028v14 | No (EPA Platform)
Non-Road 12WUS2 | EPA-2016v1 | WRAP-2028-Mobile | No (WRAP MS study)
Non-Road non-WRAP 36US | EPA-2016v1 | EPA-2028v1 | No
Other (Non-Point) 12WUS2 | EPA-2016v1 | EPA-2028v1 | Yes-UNC (T4.5)
Can/Mex/Offshore 12WUS2 | EPA-2016v1 | EPA-2028v1 | Yes-UNC (T4.6)
Fires (WF, Rx, Ag)3 | WRAP-RB-Fires | WRAP-RB-Fires3 | No (already processed)
Natural (Bio, etc.) | WRAP-2014v2 | WRAP-2014v2 | No (2014v2)
Boundary Conditions (BCs) | WRAP-2014-GEOS5 | WRAP-2014-GEOS5 | Hold BCs Constant?
WRAP-EB-EGU and WRAP-2028-EGU has updates from WRAP states. WRAP-2014v2 Non-EGU Point has updates from WRAP states A second 2018OTBb run will be made using 2014v2 actual fires |  |  | 
Source of emissions for the 12-km 12WUS2 domain and the WRAP current Representative Baseline (RepBase) and 2028OTBa emission scenarios.

## Slide 14
No. | Task | Description | Date
1. | 3.2 | CAMx-ready 2002 36/12-km emissions inputs Emissions summary tables (2002, 2014v2 and RepBase) [IWDW] | Dec 23, 2019 Dec 23, 2019
2. | 3.2 | PPT of 2002 emissions development ASCI gridded 2002 emissions [IWDW] | Dec 31, 2019 Dec 31, 2019
3. | 3.3 | Spatial QA plots of 2002 & RepBase concentrations | Jan 8, 2020
4. | 3.4 | Observed and projected Visibility at CIAs | Jan 16, 2020
5. | 3.4 | PPT on Dynamic Evaluation Spreadsheet of Dynamic Eval. Vis results at CIA [IWDW] Webpage on Dynamic Evaluation with results [IWDW] | Jan 22, 2020 Jan 22, 2020 Jan 24, 2020
6. | 4.1 | Summary tables comparing RepBase and 2028 EGU emissions | Dec 11, 2019
7. | 4.2 | CMAQ-ready 2028 emissions for 36US1 and 12US2 domains | Dec 23, 2019
8. | 4.2 | CAMx-ready 2028 emissions for 36US1 and 12WUS2 domains PPT on 2028 SMOKE modeling | Dec 31, 2019 Jan 3, 2020
9. | 4.3 | ASCII gridded 2028OTBa&b emissions [IWDW] | Jan 9, 2020
10. | 4.4 | Annual/Seasonal spatial maps of 2028OTBa&b key species ASCII gridded 2028OTBa&b ann/seas concentrations [IWDW] | Jan 15, 2020 Jan 15, 2020
11. | 6.1 | PPT on verification of the CAMx 2014v2 & RepBase on IWDW | Dec 19, 2019
12. | 6.2 | PPT on HYSPLIT back trajectories and residence time analysis Gridded ASCII residence time fields for all CIAs [IWDW] | Jan 16, 2020 Jan 16, 2020
13. | 4.6 | Preliminary 2028OTBa&b visibility projections PPT on 2028OTBa&b modeling and visibility projections Spreadsheet with 2028OTBa&b visibility projections [IWDW] | Jan 28, 2020 Jan 30, 2020 Jan 30, 2020
14. |  | PPT on WEP analysis ASCII gridded WEP & emissions and point sources [IWDW] | Feb 6, 2020 Feb 6, 2020
15 | 4.5 | CAMx 2028 WF and Rx fire sens modeling results Annual/Seasonal spatial maps of 2028 fire sens ASCII gridded 2028 fire sens concentrations [IWDW] | Feb 17, 2020 Feb 19, 2020 Feb 19, 2020
16 | 4.6 | PPT on additional visibility projections 2028 projection for IWDW [IWDW] | Feb 20, 2020 Feb 20, 2020
17 | 4.7 | PPT on 2028 state SrcApp modeling 2028 State SrcApp Vis Results at CIAs [IWDW] | Feb 21, 2020 Feb 21, 2020
18 | 6.2 | Final WEP products to IWDW [IWDW] | Feb 21, 2019
A | 5.2 | Monthly Progress Reports and Invoices | Monthly
B | 6.3 | Update RepBase WebPage on IWDW [IWDW] | Dec 18, 2019
C | 6.3 | Dynamic Evaluation WebPage [IWDW] | Jan 29, 2020
D | 6.3 | Update RepBase WebPage with 2028OTB [IWDW] | Feb 5, 2020
E | 6.3 | Update WebPage with Fire Sens [IWDW] | Feb 26, 2020
F | 6.3 | Update WebPage with 2028 SrcApp [IWDW] | Mar 11, 2020
G | 6.3 | Update WebPage [IWDW] | Mar 30, 2020
Workplan Progress by RTOWG
Workplan Tasks for the Next Two Months through March 2020

## Slide 15: Workplan Coordination Activities by RTOWG
Workplan Coordination Occurring over the Last Month
  Coordination with Ramboll on modeling progress (11/12)
  Monthly RTOWG call (11/19)
    Review sensitivity simulations
    Partial performance evaluation of CAMx 2014v2
    Discussion on modeling products and updates on schedule
  Bi-weekly RTOWG co-chair coordination calls
  Participation in other workgroup calls

## Slide 16: Workplan Coordination Activities by RTOWG
Workplan Coordination Needed over the Next Two Months
  RTOWG call (12/10)
    CAMx 2014v2 MPE
    2014v2 v. baseline emission inventory
  Coordination calls with Ramboll for completion of Phase III modeling deliverables and preparing for Phase IV
  Participation in other workgroup calls
Example: CAMx 2028OTB PM Source Apportionment
  2028 Vis Impairment at CIAs by State and Sector
  Contributions of International Anthro emissions

## Slide 17: Regional Haze Planning Work Group

## Slide 18
Workplan Progress and Coordination over the Last Month
  Review of EPA’s Regional Haze Guidance
Workplan tasks and Coordination for the Next Two Months
  Regional Haze in the West Storyboard feedback/survey
  Coordinate ongoing discussions of controls and modeling – both require states to consult with sources
Workplan Progress & Coordination by Regional Haze Planning Work Group

## Slide 19: Workplan Progress by Control Measures Subcommittee
Workplan Progress over the Last Month
  Call was held on November 25th
  States in various stages of 4-factor analysis work
Workplan Tasks for the Next Two Months
  Next call in January–
    States to update BART/RP controls and costs from Round 1 WRAP RH SIPs
    States to provide Q/d thresholds and sources subject to 4-factor work
    Continue discussion on determining remaining useful life for EGUs considering retirement

## Slide 20: Workplan Coordination Activities by Control Measures Subcommittee
Workplan Coordination Occurring over the Last Month
  Participate on monthly O&G Workgroup calls
Workplan Coordination Needed over the Next Two Months
  Continue to coordinate with O&G work group and Emission Inventory Subcommittee on emission forecasts.

## Slide 21: Workplan Progress by Coordination and Glide Path Subcommittee
Workplan Progress over the Last Month
  Elevated TSS FAQ Document to RHPWG
  Reviewed TSS Glossary for missing terms
  Reviewed of Emissions and Modeling Scenarios Comparison Specs
  TSSv2 Delivery Update Presentation
  IMPROVE Steering Committee Input
Workplan Tasks for the Next Two Month
  Continue overview of TSSv2 development
  Gain consensus on TSS FAQ and Glossary
  Revisit TSS Priorities document
  Support creation of RH Storyboard

## Slide 22: Workplan Coordination Activities by Coordination and Glide Path Subcommittee
Workplan Coordination Occurring over the Last Month
  The subcommittee coordinated with the following entities:
    RHPWG – Elevated TSS FAQ Doc for Consensus
Workplan Coordination Needed over the Next Two Months
  RTOWG – Coordination on Natural Conditions Project findings and opportunities to model outcomes for future planning periods.
  RTOWG – TSS Priorities for Modeling/EI

## Slide 23
Workplan Progress by EI&MP Subcommittee
Workplan Progress over the Last Month
  Obtained 2028 OTW/OTB emissions updates from states/locals
  California working with contractor to fix Road Dust precip controls in Rep Baseline.
Workplan Tasks for the Next Two Months
  Collect Controls Scenario (2028) emissions updates from states/locals
  Deliver future facility emissions from states/locals to contractor.
    2028 OTW/OTB and Controls scenarios
  Contractor to start Rep. Baseline and OTW/OTB simulations

## Slide 24: Workplan Coordination Activities by EI&MP Subcommittee
Workplan Coordination Occurring over the Last Month
  Coordinated with contractor to update emissions
Workplan Coordination Needed over the Next Two Months
  Representative baseline and future modeling scenarios require coordination as needed with O&G WG, contractor, Fire & Smoke WG,
  Coordinate with C&GP subcommittee to provide guidance to states on what is needed from them for the different modeling scenarios

## Slide 25
End of Workplan Progress Update