## Slide 1: Monthly Update on 2018-2019 WRAP Workplan March 27th, 2019 TSC and Work Group Co-Chairs Call
Tribal Data WG
Fire and Smoke WG
Oil and Gas WG
Regional Technical Operations WG
Regional Haze Planning WG

## Slide 2
Tribal Data Work Group

## Slide 3: Workplan Progress by Tribal Data Work Group
Workplan Progress over the Last Month
  Updated WRAP map on webpage to better reflect Tribal involvement
  Finalized several documents
    Regional Air Quality and the Regional Haze Rule: Information and Resources for Tribal Professionals and PowerPoint presentation
    Tribe, WRAP and the Reginal Haze Rule, Practices and Processes for Tribes to Address Regional Air Quality and PowerPoint presentation
  Regional Haze, and WRAP at the National Tribal Forum on Air Quality
  Scheduled webinar
Workplan Tasks for the Next Two Months
  Finalize work on AQS and EIS Gap Studies
  Finalize work on Tribal Oil and Gas Emission Inventory and Outreach
  Finalize Tribal contact list

## Slide 4: Workplan Coordination Activities by Tribal Data Work Group
Workplan Coordination Occurring over the Last Month
  Kick-off for Ramboll Task 7 - Consultation and Coordination Protocol document
  Call between OGWG & TDWG to confirm status of activities & plan next activities contracted for TDWG
Workplan Coordination Needed over the Next Two Months
  Oil and Gas EI
  Webinar schedule
  Consultation and Coordination Protocol

## Slide 5
Fire and Smoke Work Group
and

## Slide 6: Workplan Progress by Fire and Smoke Work Group
Workplan Progress over the Last Month
  Paul Corrigan (USFS and Utah) agreed to step in as 3rd co-chair
  Have had 2 more RBFFS calls, one with FSWG: March 6, 19
  Working out details on process to develop representative baseline and future fire scenarios fire emissions inventories for RH modeling
  Discussed new map deliverable idea for Smoke Management Plans task
Workplan Tasks for the Next Two Months
  Continue to identify and implement methodologies to determine future year and multi-year baseline fire emissions for RH modeling
  RBFFS next call scheduled for April 3, FSWG on May 15

## Slide 7: Workplan Coordination Activities by Fire and Smoke Work Group
Workplan Coordination Occurring over the Last Month
  Member overlap between RBFFS and EIMP Subcommittee and RHWG
Workplan Coordination Needed over the Next Two Months
  Carry on coordinating

## Slide 8
Oil and Gas Work Group

## Slide 9: Workplan Progress by Oil and Gas Work Group
Workplan Progress over the Last Month
  OGWG O&G Operator Surveys - Completion
  Forecast Scenarios - Underway
  OGWG Workplan Review & Update approved by consensus on Feb. 12 call and provided to TSC
Workplan Tasks for the Next Two Months
  Task 1: Base Year Inventory – Mid-March/Early-April - Survey compilation memo
  Task 2: Forecast 2028 Inventory (On-the-books controls) – Late-February/Early-April - Forecast scenarios

## Slide 10: Workplan Coordination Activities by OGWG
Workplan Coordination Occurring over the Last Month
  Assistance from Agencies/O&G operators to complete OGWG Survey
  March 4 – Project Management Team Call
    Discuss steps to wrap-up the survey effort with Ramboll.
    Coordinate on the forecast scenarios and provide PMT feedback to Ramboll.
  March 8 – Coordination Call on Tribal Outreach
    TDWG and OGWG Co-Chairs
  Assistance from Agencies on Forecast Scenarios
Workplan Coordination Needed over the Next Two Months
  April 4 – Project Management Team Call
  April 9 – OGWG Bi-Monthly Call
    Agenda under development
      Tribal Outreach Progress – invitation to TDWG contractor team (ITEP & EN3)
  Assistance from Agencies on Forecast Scenarios
  OGWG and PMT review and feedback on draft work products

## Slide 11
Regional Technical Operations Work Group

## Slide 12: Workplan Progress by RTOWG Work Group-2014 Shake-Out Project
Work Item | Completion | Comments
Phase I 2014 Shake-Out Modeling Plan | Dec 2018 | Completed
Single-Source Visibility Modeling Webinar | Dec 2018 | Completed
Single-Source Visibility Modeling Memorandum | Feb 2019 | 
2014 Emission Inputs | Jan 2019 | Completed
2014 36-km CONUS Domain Boundary Conditions | Jan 2019 | Completed
2014 Meteorological Inputs | Jan 2019 | Completed
2014 WRF and Biogenic PGM Sensitivity Test | Feb 2019 | Completed Since Last Update
2014 Annual CAMx and CMAQ Platforms | Feb 2019 | Completed Since Last Update
Phase II Illustrative Modeling Plan (WAQS/WestJumpAQMS) | Feb 2019 | Will be completed by Apr 5
2014 Annual CMAQ and CMAQ Base Case and MPE | Mar 2019 | Will be completed by Apr 5
Transfer 2014 Platform to IWDW | Feb 2019 | Will be completed by Apr 5
2014 Shake-Out Close-Out Meeting | Apr 5, 2019 | Will be completed by Apr 5
2014 Shake-Out Report | Mar 2019 | 

## Slide 13: Final Model Configuration for V1 Model Shakeout
CAMx and CMAQ 2014 annual 36-km and 12-km simulations
2014 GEOS-Chem Boundary Conditions (GCBC)
  Use updated GCBCs for Jun/Jul without volcano eruptions
12-km WRF Meteorology – WAQS 12WUS2 vs. EPA 12US2
  Difficult to select based on MPE due to GCBC ozone and Jun/Jul Overestimation
  Select WAQS 12WUS2 WRF meteorology based on better precip MPE and less wet deposition in summer
Emissions – MEGAN vs. BEIS biogenic emissions in 12-km domains
  Select BEIS based on improved OA performance at most, but not all, sites
Setting up final 2014 Shake-Out Runs to Meeting Apr 5 Close-Out Meeting
  CAMx 36/12-km should be completed

## Slide 14: Monthly RTOWG Call-March 11, 2019
Discussion Topics
  Consensus approval by RTOWG of 2018-19 WRAP Workplan update, especially Appendix E
  GEOS-Chem global model results for boundary conditions – Gail Tonnesen
  Ammonia emissions and modeling – Mike Barna
  Overview of project to develop Representative Baseline and Future Fires scenarios – Matt Mavko Planning Baseline Fire EI white paper
  2014 Shakeout Modeling Platform v1 status report – Ralph Morris

## Slide 15: Workplan Coordination Activities by Regional Technical Operations Work Group
RTOWG Workplan Coordination Occurring over the Last Month
  The RTOWG Monthly Call was held on March 11
  The RTOWG Co-Chairs had biweekly calls on March 4, March 8, March 18, and March 21 to discuss coordination efforts
  The RTOWG Co-Chairs had coordination calls with the Shake-out team of contractors on March 8 and March 25
Cross Coordination Activities
  The RTOWG Co-Chairs had cross coordination call with the RHPWG Emission Inventory and Modeling Protocol subgroup on March 25 to discussion portions of version 2 of the 2014 EI especially in regards to the California Emission Inventory Substitution
  On the Monthly RTOWG call on March 11, Matt Mavco gave a discussion on the plans from the Fire and Smoke Work group on proposals for the ‘average’ base year and ‘average’ future year fire emission inventories

## Slide 16: Workplan Coordination Activities by Regional Technical Operations Work Group
Workplan Coordination Needed over the Next Two Months
  Emissions updates from RHPWG EI subcommittee
  Updated fire emissions from FSWG
  Updated O&G emissions from OGWG

## Slide 17
Regional Haze Planning Work Group

## Slide 18: Workplan Progress by Regional Haze Planning Work Group
Workplan Progress over the Last Month
  Consensus on the Draft Workplan
  Complete Subcommittee and Workgroup restructuring
Workplan tasks for the Next Two Months
  Consensus on ‘Overview of Regional Haze’ document
  Potentially consensus on the WRAP Communication Framework
  Restructure the RHPWG website

## Slide 19: Workplan Coordination Activities by Regional Haze Planning Work Group
Workplan Coordination Occurring over the Last Month
  Work with Coordination and Glide Path SC in planning a Milestone Webinar in March to discuss monitoring data and control measures
  Coordination with all subcommittees to move work products through the consensus process
    TSS Website information
Workplan Coordination Needed over the Next Two Months
  Finalize consensus on WRAP Communication Framework
  Q & A Follow-up on March Milestone Webinar
  Coordinate with RTOWG on the Shakeout and next webinar
  Develop or finalize informational documents and plan for future informational webinars as new information becomes available on the TSS v2

## Slide 20: Coordination and Glide Path Subcommittee
Workplan Progress over the Last Month
  Informational webinar on Monitoring Data and Trends, Source Identification Protocol, and Tribal Maps Update March 20, 2019
  Consensus on TSS Website information
Workplan Tasks for the Next Two Months
  Development of or consensus for informational documents in support of SIP planning.
  Development of next quarterly informational webinar as new information becomes available on the TSS v2
  Consensus on WRAP Communication Framework
Subcommittee Coordination
  Input from MDGP Subcommittee members on TSS v.2 data
  Coordinate with Modeling/Emissions Inventory SC for planning next webinar
  Coordinate with Tribal Data to complete the Communication Framework

## Slide 21: Monitoring Data & Glide Path Tasks
Workplan Progress over the Last Month
  Now part of the Coordination & Glide Path Subcommittee
  Outline tasks for future contractor work on natural conditions
  Assist in upcoming monitoring data webinar
  Coordination with RTOWG on URP adjustment
Workplan Tasks for the Next Two Months
  Develop trend analysis methodology white paper
Subcommittee Coordination
  Coordination with RTOWG on URP adjustment
  May increase interaction with EPA and with IMPROVE Subcommittee to develop method for determining Glide Path 2064 endpoint (future)

## Slide 22: Emissions Inventory and Modeling Protocol Subcommittee
Workplan Progress over the Last Month
  Finalized Recommendations for Base Year Modeling
Workplan Tasks for the Next Two Months
  Evaluate, Refine, and Process Base Year Inventory
  Finalize Emissions Representativeness for baseline forecasting
Subcommittee Coordination
  Coordination with RTOWG to complete the modeling shakeout
  Coordinating with RHPWG for consensus on work products

## Slide 23: Control Measures Subcommittee
Workplan Progress over the Last Month
  Reasonable Progress Source Identification and Analysis Protocol prepared for docketing
  Contractor working on Q/d analysis
Workplan Tasks for the Next Two Months
  Finish Q/d analysis
  Discuss Q/d analysis work product on upcoming call
  Step down to bi-monthly calls after March call
Subcommittee Coordination
  EI&MP Subcommittee

## Slide 24
End of Workplan Progress Update

## Slide 25: Workplan Progress by (insert name) Work Group
Workplan Progress over the Last Month
  Example bullets
  Draft report out for review
  Provided feedback to contractor regarding IMPROVE data substitution
Workplan Tasks for the Next Two Months
  Example bullets
  Finalize draft report
  Review final contractor recommendations on data substitution

## Slide 26: Workplan Coordination Activities by (insert name) Work Group
Workplan Coordination Occurring over the Last Month
  Who did you coordinate with, what topics were discussed, and when did it occur (replace this text with you own)
Workplan Coordination Needed over the Next Two Months
  What activities do you need to coordinate on, with whom, and expected timeframe (replace this text with you own)