## Slide 1: Monthly Update on 2018-2019 WRAP Workplan July 29th, 2020 TSC and Work Group Co-Chairs Call
Oil & Gas WG
Regional Technical Operations WG
Regional Haze Planning WG
Emission Inventory & Modeling Protocol Sc

## Slide 2: Oil and Gas Work Group

## Slide 3: Oil and Gas Work Group
Upcoming OGWG Communication Call (every 4 months)
  August 11, 2020: Draft Agenda
    Topic specific updates
      Invited: CARB Reporting on Venting, Fugitive, and Flaring Emissions from Natural Gas
      Invited: BLM Additional Source Apportionment Work
    Track oil & gas sector and keep up to date via roundtable
      Initiatives / Rulemaking changes
      Market downturn impacts
      2nd Additional Reasonable Controls
  Next Call December 8, 2020

## Slide 4: Regional Technical Operations Work Group

## Slide 5: Workplan Progress by RTOWG
Workplan Progress over the Last Month
  Weekly co-chair coordination calls
  Weekly calls with Ramboll to keep track of modeling progress
  RTOWG call (7/15/20)
    2028 projection emissions changes and corrections / state review of point sources by July 21st / resulting modeling schedule
    Review of alternate visibility projection methods
    Recommended URP adjustment method
    PAC1 visibility modeling results

## Slide 6: Workplan Progress by RTOWG
Workplan Progress over the Last Month
  Documents up for review on RTOWG webpage:
    Procedures for Making 2028 Visibility Projections using the WRAP-WAQS 2014 Modeling Platform (July 24, 2020 draft)
    Adjusting the URP Glidepath Accounting for International Anthropogenic Emissions and Prescribed Fires using the WRAP 2014/2028 Modeling Platform Results (July 24, 2020 draft)
  Errors identified in 2028OTBa emission inventory (some double counting of sources), corrections are underway
  Proposed updates to 2028OTBa to make 2028OTBa2
  Potential Additional Controls, Round #1 (PAC1) CAMx simulation completed

## Slide 7: Workplan Product Results by RTOWG
Adjusted URP that accounts for international and prescribed wildland fires (ESTIMATED -NOT FINAL)
Unadjusted URP
Contribution from international and Rx fire
    From: “Adjusting the URP Glidepath Accounting for International Anthropogenic Emissions and Prescribed Fires using the WRAP 2014/2028 Modeling Platform Results (July 24, 2020 draft)” on RTOWG webpage

## Slide 8: Workplan Product Results by RTOWG
Potential Additional Controls, Round #1 (PAC1)
  As expected, very small changes in projected 2028 MID dv
    Mostly hundredths of dv changes
    Largest changes in or near states with emissions reductions (e.g., NM, AZ, ND)
    Smallest changes away from such states (e.g., CA)
  Round 2 of Potential Additional Controls (PAC2)
    Need state emission changes to be tested by Sept. 10, 2020
  Caveats:
    2028OTB emissions include double counted O&G sources
      In both 2028OTBa and 2028PAC1
      Does not affect the reductions in 2028 MID due to PAC1 controls
      Probably minimal affect on 2028 MID projections

## Slide 10: Upcoming Work by RTOWG
Workplan Tasks for the Next Two Months
Assuming all state updates on 2028 emissions are provided by July 21st in FF10 format:
  2028OTBa2 SMOKE emissions modeling finished by August 4
  CAMx 2028OTBa2 standard model run finished by August 11
    Revised 2028OTBa2 projections on TSS by August 13
  CAMx 2028OTBa2 high-level source apportionment run finished by August 31
    U.S. vs. International anthropogenic, fires and natural contributions
    Adjust URP Glidepath for International Emissions and Wildland Prescribed Fires
    Use for Dynamic Evaluation U.S. anthropogenic emissions extinction Glidepath from 2002 to zero in 2064 with 2016 (RepBase) and 2028 (OTBa2) visibility projections
  CAMx 2028OTBa2 low-level source apportionment run finished in October
    State-specific and Source Sector-specific contributions

## Slide 11: Updates to 2028OTBa2 emission inventory

## Slide 12: Regional Haze Planning Work Group
Verbal Update Only

## Slide 13: Workplan Progress by RHPWG EIMP SC
Workplan Progress over the Last Month
  Added task to provide model-input and NEI emissions summaries by model sector.
  2028 OTB double counting necessitated review of O&G and non-EGU. States provided updates for the 2028 OTB emissions. This scenario will be rerun.
Workplan Tasks for the Next Two Months
  Contractor will continue to provide deliverables
  PACv2 Emissions Submittals due in August.

## Slide 14
End of Workplan Progress Update