## Slide 1: Monthly Update on 2018-2019 WRAP Workplan August 26th, 2020 TSC and Work Group Co-Chairs Call
Tribal Data Workgroup
Regional Technical Operations WG
Emission Inventory & Modeling Protocol Sc

## Slide 2: Tribal Data Work Group

## Slide 3: Upcoming Work by Tribal Data Work Group
WRAP Tribal Data WG Workplan Results for Regional Haze and Modeling Update - Virtual Remote Meeting #4 | 
Date | Wednesday, September 2nd 2020
Time | 11:00 AM MDT - 12:30 PM MDT
Contact | Tom Moore - tmoore@westar.org
Description | WRAP Tribal Data WG Workplan Results for Regional Haze and Modeling Update - Virtual Remote Meeting #4 September 2, 2020 Step 1: Dial-In U.S. & Canada: 800.768.2983 Access Code: 6619876342 Step 2: Web Login https://cc.callinfo.com/r/17t0e02zdh1ti&eom Agenda to be added

## Slide 4: Regional Technical Operations Work Group

## Slide 5: Workplan Progress by RTOWG
Workplan Progress over the Last Month
  Weekly co-chair coordination calls
  Weekly calls with Ramboll to keep track of modeling progress
  New spec sheets for
    Representative Baseline (‘RepBase2’) and 2028 On-the-Books (‘2028OTBa2’) CAMx Simulations
    High-Level Source Apportionment (‘H-L SA’) Modeling Using the RepBase2 and 2028OTBa2 Emission Scenario
  Emissions processing for RepBase2 and 2028OTBa2

## Slide 6: Upcoming Work by RTOWG
Generally speaking, the analytical tools to be developed from current modeling tasks (to be completed by mid-October) are
  Three versions of future visibility projections
    EPA default method on IMPROVE Most Impaired Days
    EPA default method with fire impacts removed on IMPROVE Most Impaired Days
    ‘ModMID’, with CAMx-derived Most Impaired Days to isolate US anthropogenic contributions
  Adjustments to the Uniform Rate of Progress Glidepath to account for
    International anthropogenic contributions
    Prescribed wildland fires

## Slide 7: Upcoming Work by RTOWG
Upcoming Tasks through Mid-October (dates are approximate)
  RepBase2 and 2028OTBa2 emissions on TSS (9/11)
  RepBase2 combined CAMx standard model and high-level source apportionment run (9/14)
  2028OTBa2 standard model run (9/14)
  RepBase2 and 2028OTBa2 model results on TSS (9/23)
  2028OTBa2 high-level source apportionment run (10/1)
  URP glidepath adjustment tool on TSS (10/9)
  PAC2 modeling using revising 2028OTBa2 emissions (mid-October)

## Slide 8: Upcoming Work by RTOWG
Workplan Tasks by November
  2028OTBa2 low-level source apportionment run
    State-specific and Source Sector-specific contributions for WESTAR-WRAP states (not other states)
  2028OTBa2 low-level source apportionment results on TSS
  Finalization of dynamic modeling study
  Fire sensitivity scenarios

## Slide 9: Example methods for calculating relative response factors at CABI in Montana

## Slide 10: Workplan Progress by EI&MP SC
Workplan Progress over the Last Month
  Double-counting and other issues with first model runs reported.
  States reviewed Rep Base and 2028 OTB data for Model Reruns (2 separate review processes; 1 week turnarounds; primarily nonEGU and O&G)
  States provided feedback to contractor regarding data corrections/changes.
Workplan Tasks for the Next Two Months
  Contractor re-runs Rep Base and 2028 OTB
  States submit PAC2 emissions updates

## Slide 11
End of Workplan Progress Update