**2018-19 Workplan completion schedule**

Feb. 27, 2018 update

* March 2nd – end of comment period on v2 by WGs
* March 9th – v3 distributed to TSC and WG Co-chairs’ review
* March 9-14 - TSC and WG Co-chairs’ review
* March 15-19 – processing of March 9-14 comments and formatting for Board review draft
* March 20 or 21 – send to Board
* April 4 – Board call to review – discuss – approve
* April 24th at WESTAR and WRAP meting – Regional Haze planning and Workplan implementation status (start 230 pm PDT)
* April 26th morning 8 am to 12 pm PDT – WRAP Board, TSC, and WG Co-Chairs’ meeting