## Workgroup Internal Subtasks
Workgroup / Subcommittee | Item | Due Date
OGWG | Review/comments on draft baseline inventory (v2) and report | 2019-06-25
EIMP Sc | Facility Emissions Submission deadline for Representative Baseline Modeling | 2019-07-03
TDWG | Review/comments to Ramboll/CGSC on CC Framework “redline” draft | 2019-07-08
OGWG | O&G Activity forecast scenarios developed by contractor | 2019-07-15
OGWG | Memo on survey compilation of emission controls by contrator | 2019-07-15
TDWG | Review/comments on next “turnaround” version by Ramboll, finalize comments | 2019-07-18
OGWG | OTB and OTW emission controls | 2019-07-31
RTOWG | Completion of Representative Baseline modeling | 2019-07-31
EIMP Sc | Facility Emissions Submission deadline for 2028 OTW/OTB Scenario | 2019-08-01
OGWG | OTB and OTW controls future year inventory and report | 2019-08-23
OGWG | Review/comments on draft future year inventory and report | 2019-08-30
OGWG | Final v2 baseline inventory and report by contractor | 2019-08-30
EIMP Sc | Facility Emissions Submission deadline for 2028 Controls Scenario | 2019-12-19

## RH Planning Key Checkins
Key Check-Ins and Critical Milestones for Regional Haze Planning Technical Support (by Task)
| 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021
Task | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3
Task 1. Monitoring Data Analysis
Reach consensus -- tracking metric
Reach consensus -- Natural Conditions estimates
Reach consensus -- adjusting the glideslope for natural fire and int'l emissions
Task 2. Emissions Inventory
Enhanced base year emission inventory ready for modeling
Reach consensus -- inventory projection methods for fire, oil and gas, others
Enhanced planning emission inventory (on-the-way/on-the-books) ready for modeling
Final 2028 control measures emission inventory ready for modeling
Task 3. Air Quality Modeling (Visibility and Source Appointment Modeling)
Approve modeling plans and protocol
Base year modeling and Model Performance Evaluation complete
2028 planning modeling complete (on-the-way/on-the-books controls)
Final 2028 control measures modeling complete
Task 4. Evaluating Modeling Results
Reach consensus -- resolution of tracking metric and model output
Reach consensus -- scenarios for sensitivity testing/modeling
Evaluate change in visibility -- Base year to 2028 (Reasonable Progress Goals)
Task 5. Control Measures Analysis (Reasonable Progress Analysis)
Reach consensus -- development and application of screening tools
Reach consensus -- application of Source Appointment modeling results
Reach consensus -- use of visibility as a fifth factor and how to incorporate
States finish control analysis
Task 6. Coordinate Training and Outreach Efforts
Oversee compilation and distribution of materials
Task 7. Technical Support System TSS v2
TSS v2 fully functional with all necessary data and tools
Task 8. State Planning and Adoption Process
2018 RH SIP due

## Regional Analysis Key Checkins
On-going Activities and Key Check-Ins for Associated Regional Analysis Technical Support (by Work Group)
| 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021
Task | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3
Technical Steering Committee
Oversee finalization of 2018-2019 WRAP Workplan and budget for Board approval
Provide monthly oversight and direction to Work Groups and coordinate activities | ----------------------------------------------------------------------------------------------- on-going -------------------------------------------------------------------------------------------------------------------
Conduct periodic assessment of 2018-2019 Workplan progress and report out to Board
Conduct mid-course review of 2018-2019 Workplan and revise as necessary
Regional Haze Planning Work Group
Provide oversight and direction to Subcommittees and coordinate activities | ----------------------------------------------------------------------------------------------- on-going -------------------------------------------------------------------------------------------------------------------
Identify and provide training needed for SIP preparation | ----------------------------------------------------------------------------------------------- on-going -------------------------------------------------------------------------------------------------------------------
Schedule and arrange regional haze planning webinars and meetings as needed
Regional Technical Operations Work Group
Coordinate with other Work Groups to identify needed air quality modeling products | ----------------------------------------------------------------------------------------------- on-going -------------------------------------------------------------------------------------------------------------------
Leverage opportunities and WRAP work through coordination and collaboration | ----------------------------------------------------------------------------------------------- on-going -------------------------------------------------------------------------------------------------------------------
Fire and Smoke Work Group
WRAP Tools/Fire Emissions Tracking System update and continued operation |  |  |  |  | ---------------------------------------------------------------- on-going ------------------------------------------------------------------------------------
Identify key data to collect in support of exceptional event demonstrations
Coordinate wildfire response and smoke management
Oil and Gas Work Group
Member agency collaboration on sub-regional oil and gas management | ----------------------------------------------------------------------------------------------- on-going -------------------------------------------------------------------------------------------------------------------
Regional and local air quality planning needs | ----------------------------------------------------------------------------------------------- on-going -------------------------------------------------------------------------------------------------------------------
Tribal Data Work Group
Solicit Tribal membership and participation in WRAP | ----------------------------------------------------------------------------------------------- on-going -------------------------------------------------------------------------------------------------------------------
Assist Tribes with WRAP/WESTAR technical tools and data analyses | ----------------------------------------------------------------------------------------------- on-going -------------------------------------------------------------------------------------------------------------------
Develop strategies to facilitate submittal of Tribal monitoring and emissions data

## RH Planning Gannt
WRAP 2018-2019 WorkPlan | [7 empty] | 2018 |  |  |  |  | 2019 |  |  |  |  | 2020 |  |  |  | 2021
RHP | RTO | F&S | O&G | TD | CON | # | Task | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3
Critical Milestones for Regional Haze Planning Technical Support
[7 empty] | Evaluation of RHR revisions |  |  |  |  | X
Monitoring data evaluation
[7 empty] | Base, planning, and future year emissions data work | [9 empty] | X
Base-year model platform and MPE completed
States use WRAP analysis for RH Planning
Future-year on-the-books scenarios modeling
Source apportionment & sensitivity analysis
[7 empty] | Technical work done, data products in TSS.v2 | [11 empty] | X
[7 empty] | SIP submission to EPA | [16 empty] | X
Timeline by Task
[6 empty] | 1 | Monitor data analysis
[6 empty] | 2 | Emission inventory
[6 empty] | 3 | Air quality modeling
[6 empty] | 4 | Evaluating modeling results
[6 empty] | 5 | Control measures analysis
[6 empty] | 6 | Coordinate training and outreach efforts
[6 empty] | 7 | Technical support system
[6 empty] | 8 | States' planning and adoption process
Detailed Timeline by Task
[6 empty] | 1 | Monitoring Data Analysis
[6 empty] | 1.1 | Evaluate EPA tracking metric and alternatives
[6 empty] | 1.2 | Analyze monitor data (trends, ranges, linkages)
[6 empty] | 1.3 | Identify dominant visibility-impairing pollutants for each CIA
[6 empty] | 2 | Emissions Inventory
[6 empty] | 2.1 | Process and evaluate 2014 NEI and refinements
[6 empty] | 2.2 | Evaluate use of 2016 EPA modeling platform
[6 empty] | 2.3 | Develop and refine 2028 emission inventories
[6 empty] | 2.4 | Develop screening tools
[6 empty] | 2.5 | Special inventory needs
[6 empty] | 2.6 | State specific analysis of EI trends
[6 empty] | 3 | Air Quality Modeling
[6 empty] | 3.1 | Prepare modeling plan
[6 empty] | 3.2 | Prepare and evaluate meteorological data
[6 empty] | 3.3 | Perform dynamic model evaluations
[6 empty] | 3.4 | Conduct sensitivity testing
[6 empty] | 3.5 | Evaluate use of 2016 EPA modeling platform
[6 empty] | 3.6 | Conduct/evaluate base year air quality modeling
[6 empty] | 3.7 | Conduct/evaluate 2028 air quality modeling
[6 empty] | 4 | Evaluating Modeling Results
[6 empty] | 4.1 | Resolve tracking metric and model output issue
[6 empty] | 4.2 | Sensitivity/control strategy evaluation modeling for 2028
[6 empty] | 4.3 | Evaluate base year & 2028 source apportionment modeling results
[6 empty] | 4.4 | Evaluate change in visibility from base year to 2028
[6 empty] | 5 | Control Measure Analysis
[6 empty] | 5.1 | Develop criteria for source identification & 4-factor analysis
[6 empty] | 5.2 | Determine whether to use visibility as fifth factor
[6 empty] | 5.3 | Conduct regional/state source screening
[6 empty] | 5.4 | Evaluate emission source impacts on Class I areas
[6 empty] | 5.5 | Identify/incorporate 2028 emissions reductions from control strategies
[6 empty] | 6 | Coordinate Training and Outreach Efforts
[6 empty] | 6.1 | Assess needs for materials useful to SIP planners
[6 empty] | 6.2 | Identify and compile existing materials
[6 empty] | 6.3 | Develop new materials
[6 empty] | 6.4 | Oversee completion and distribution of materials
[6 empty] | 7 | Technical Support System TSS.v2
[6 empty] | 7.1 | Review TSS v1 for priority needs
[6 empty] | 7.2 | Coordinate and review TSS monitor data tool development
[6 empty] | 7.3 | Coordinate/review TSS emissions data/emissions projections tool development
[6 empty] | 7.4 | Coordinate and review TSS base year modeling tool development
[6 empty] | 7.5 | Coordinate and review TSS 2028 on-the-books modeling tool development
[6 empty] | 7.6 | Coordinate and review TSS reasonable control modeling tool development
[6 empty] | 7.7 | Provide TSS training webinars
[6 empty] | 8 | State Planning and Adoption Process
[6 empty] | 8.1 | Identify SIP planning target dates
[6 empty] | 8.2 | Establish consultation framework
[6 empty] | 8.3 | Coordinate and support consultation among WRAP member agencies
[6 empty] | 8.4 | Support state-led SIP development, consultation, and public review
[6 empty] | 8.5 | Submit SIP to U.S. EPA

## Regional Analysis Gannt
WRAP 2018-2019 WorkPlan | [7 empty] | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021
RHP | RTO | F&S | O&G | TD | CON | # | Task | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3
Critical Milestones for Associated Regional Analysis Technical Support in 2018-2019
[6 empty] | 10.1 | BY emissions processing, modeling
[6 empty] | 10.4 | 2028 Emissions projections
[6 empty] | 10.5 | IWDW-WAQS 2028 on-the-books air quality modeling
[6 empty] | 10.7 | IWDW-WAQS 2028 control scenarios’ air quality modeling
WRAP tools/FETS update and operation
Historic and future fire activity and emissions
Evaluation of smoke management plans
Ongoing Exceptional Events analysis and coordination
WRAP member-agency coordination on wildfire response &...
Review existing Oil and Gas Work Products
ID regional and local air quality planning needs
[6 empty] | 13.1 | Help Tribes understand WRAP/WESTAR product benefits
[6 empty] | 13.2 | Solicit Tribal membership in WRAP and participation in TDWG
[6 empty] | 13.7 | Coordinate to facilitate support of TIPs and tribal programs
Detailed Timeline by Work Group
[6 empty] | 9 | Technical Steering Committee (TSC) Progress Calls and Meetings
Planning/oversight/coordination/direction calls
Board/TSC/Co-Chairs meetings at Business Meetings
Biannual planning/progress/informational Meetings
[6 empty] | 10 | Regional Technical Operations Work Group (RTOWG)
[6 empty] | 10.1 | BY emissions processing, modeling
[6 empty] | 10.2 | Dynamic model evaluations for ozone/PM/nitrogen
[6 empty] | 10.3 | IWDW-WAQS AQ modeling for...
[6 empty] | 10.4 | 2028 emissions projections
[6 empty] | 10.5 | IWDW-WAQS 2028 on-the-books air quality modeling
[6 empty] | 10.6 | IWDW-WAQS FY source apportionment/sensitivity modeling
[6 empty] | 10.7 | IWDW-WAQS 2028 control scenarios’ air quality modeling
[6 empty] | 11 | Fire and Smoke Work Group (FSWG)
WRAP Tools/FETS update and operation
Historic and future fire activity and emissions
Evaluation of smoke management plans
Exceptional Events: ID key data to collect for demonstrations
Coordination on wildfire response and smoke management
[6 empty] | 12 | Oil and Gas Work Group (OGWG)
Regional and local air quality planning needs
ID and review of member agency oil and gas programs
ID and review of member agency emissions management
Assess impacts from oil and gas production
Develop oil and gas tool box
Member agency collaboration on sub-regional oil and gas management
[6 empty] | 13 | Tribal Data Development Work Group (TDDWG)
[6 empty] | 13.1 | Help Tribes understand WRAP/WESTAR product benefits
[6 empty] | 13.2 | Solicit Tribal membership in WRAP and participation in TDWG
[6 empty] | 13.3 | Help Tribes understand monitoring data and use of AQS
[6 empty] | 13.4 | Help Tribes understand the EI process and NEI capability and use
[6 empty] | 13.6 | Ensure availability of monitoring/emissions data from Tribes
[6 empty] | 13.7 | Coordinate to facilitate support of TIPs and tribal programs
[6 empty] | 13.8 | Provide educational opportunities for WRAP member Tribes
[6 empty] | 14 | Regional Haze Planning Work Group (RHPWG)
[6 empty] | 10.1 | BY emissions processing, modeling
[6 empty] | 10.2 | Dynamic model evaluations for ozone/PM/nitrogen
[6 empty] | 10.3 | IWDW-WAQS AQ modeling for...
[6 empty] | 10.4 | 2028 emissions projections
[6 empty] | 10.5 | IWDW-WAQS 2028 on-the-books air quality modeling
[6 empty] | 10.6 | IWDW-WAQS FY source apportionment/sensitivity modeling
[6 empty] | 10.7 | IWDW-WAQS 2028 control scenarios’ air quality modeling
WRAP Tools/FETS update and operation
Historic and future fire activity and emissions
Evaluation of smoke management plans
ID action items requiring coordination with others