## RH Planning Tech Support
Key Check-Ins and Critical Milestones for Regional Haze Planning Technical Support (by Task)
| 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021
Task | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3
Task 1. Monitoring Data Analysis
Reach consensus -- tracking metric | [15 empty] | Revised by RHPWG
Reach consensus -- Natural Conditions estimates | [15 empty] | Revised by RHPWG
Reach consensus -- adjusting the glideslope for natural fire and int'l emissions | [15 empty] | Revised by RHPWG
Task 2. Emissions Inventory
Enhanced base year emission inventory ready for modeling | [15 empty] | Revised by FSWG
Reach consensus -- inventory projection methods for fire, oil and gas, others | [15 empty] | Revised by FSWG
Enhanced planning emission inventory (on-the-way/on-the-books) ready for modeling
Final 2028 control measures emission inventory ready for modeling
Task 3. Air Quality Modeling (Visibility and Source Appointment Modeling)
Approve modeling plans and protocol
Base year modeling and Model Performance Evaluation complete
2028 planning modeling complete (on-the-way/on-the-books controls)
Final 2028 control measures modeling complete
Task 4. Analyzing Future Year Modeling Results
Reach consensus -- resolution of tracking metric and model output
Reach consensus -- scenarios for sensitivity testing/modeling
Evaluate change in visibility -- Base year to 2028 (Reasonable Progress Goals)
Task 5. Control Measures Analysis (Reasonable Progress Analysis)
Reach consensus -- development and application of screening tools
Reach consensus -- application of Source Appointment modeling results
Reach consensus -- use of visibility as a "fifth" factor and how to incorporate
States finish control analysis
Task 6. Embedded Progress Report (5-Year Reports)
5-year Progress Report due
Task 7. Technical Support System TSS v2
TSS v2 available for training/use
TSS v2 fully functional with all necessary data and tools | [15 empty] | Revised by RHPWG
Task 8. State Planning and Adoption Process
2018 RH SIP due
Note on AH31: Frank Forsgren: The Gantt chart suggests this could be moved up to the end of 1st Q 2020

## Regional Analysis Tech Support
On-going Activities and Key Check-Ins for Associated Regional Analysis Technical Support (by Work Group)
| 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021
Task | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3
Technical Steering Committee
Oversee finalization of 2018-2019 WRAP Workplan and budget for Board approval
Provide monthly oversight and direction to Work Groups and coordinate activities | ---------------------------------------------------------------------------------------------- on-going ------------------------------------------------------------------------------------------------------------------
Conduct periodic assessment of 2018-2019 Workplan progress and report out to Board
Conduct mid-course review of 2018-2019 Workplan and revise as necessary
Regional Haze Planning Work Group
Provide oversight and direction to Subcommittees and coordinate activities | ---------------------------------------------------------------------------------------------- on-going ------------------------------------------------------------------------------------------------------------------
Identify and provide training needed for SIP preparation | ---------------------------------------------------------------------------------------------- on-going ------------------------------------------------------------------------------------------------------------------
Schedule and arrange regional haze planning meetings as needed
Regional Technical Operations Work Group
Coordinate with other Work Groups to identify needed air quality modeling products | ---------------------------------------------------------------------------------------------- on-going ------------------------------------------------------------------------------------------------------------------
Leverage opportunities and WRAP work through coordination and collaboration | ---------------------------------------------------------------------------------------------- on-going ------------------------------------------------------------------------------------------------------------------
Fire and Smoke Work Group
WRAP Tools/Fire Emissions Tracking System Update and Continued Operation | ---------------------------------------------------------------------------------------------- on-going ------------------------------------------------------------------------------------------------------------------
WRAP Tools/Fire Emissions Tracking System Update and Continued Operation |  |  |  |  | ----------------------------------------------------------------------- on-going ------------------------------------------------------------------------------------------- | [10 empty] | Revised by FSWG
Identify key data to collect in support of exceptional event demonstrations | ---------------------------------------------------------------------------------------------- on-going ------------------------------------------------------------------------------------------------------------------
Identify key data to collect in support of exceptional event demonstrations | [15 empty] | Revised by FSWG
Coordinate wildfire response and smoke management | ---------------------------------------------------------------------------------------------- on-going ------------------------------------------------------------------------------------------------------------------
Coordinate wildfire response and smoke management | [15 empty] | Revised by FSWG
Oil and Gas Work Group
Member agency collaboration on sub-regional oil and gas management | ---------------------------------------------------------------------------------------------- on-going ------------------------------------------------------------------------------------------------------------------
Regional and local air quality planning needs | ---------------------------------------------------------------------------------------------- on-going ------------------------------------------------------------------------------------------------------------------
Tribal Data Work Group
Solicit Tribal membership and participation in WRAP | ---------------------------------------------------------------------------------------------- on-going ------------------------------------------------------------------------------------------------------------------
Assist Tribes with WRAP/WESTAR technical tools and data analyses | ---------------------------------------------------------------------------------------------- on-going ------------------------------------------------------------------------------------------------------------------
Develop strategies to facilitate submittal of Tribal monitoring and emissions data
Note on G20: Sara Strachan: Completed and ready for docket.
Note on AA22: Sara Strachan: We have plenty to accomplish for 2019, so I propose we push this task out to 2020.