## RH Planning Tech Support clean
WRAP 2018-2019 WorkPlan | [7 empty] | 2018 |  |  |  |  | 2019 |  |  |  |  | 2020 |  |  |  | 2021
RHP | RTO | F&S | O&G | TD | CON | # | Task | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3
Critical Milestones for Regional Haze Planning Technical Support
[7 empty] | Evaluation of RHR Revisions |  |  |  |  | X
Monitoring Data Evaluation
[7 empty] | Base, Planning, and Future Year Emissions Data work | [9 empty] | X
Base-year model platform and MPE completed
States use WRAP analysis for RH Planning
Future-year "on the books" scenarios modeling
[7 empty] | Source apportionment & sensitivity analysis | [5 empty] | X
[7 empty] | Technical work done, data products in TSS.v2 | [11 empty] | X
[7 empty] | SIP submission to EPA | [16 empty] | X
Timeline by Task
[6 empty] | 1 | Monitor Data Analysis
[6 empty] | 2 | Emission Inventory
[6 empty] | 3 | Air Quality Modeling
[6 empty] | 4 | Evaluating Modeling Results
[6 empty] | 5 | Control Measures Analysis
[6 empty] | 6 | Coordinate Training and Outreach Efforts
[6 empty] | 7 | Technical Support System
[6 empty] | 8 | States Planning and Adoption Process
Detailed Timeline by Task
[6 empty] | 1 | Monitoring Data Analysis
[6 empty] | 1.1 | Evaluate EPA tracking metric and alternatives
[6 empty] | 1.2 | Analyze monitor data (trends, ranges, linkages)
[6 empty] | 1.3 | Identify dominant visibility-impairing pollutants for each CIA
[6 empty] | 2 | Emissions Inventory
[6 empty] | 2.1 | Process and evaluate 2014 NEI and refinements
[6 empty] | 2.2 | Evaluate use of 2016 EPA modeling platform
[6 empty] | 2.3 | Develop and refine 2028 emission inventories
[6 empty] | 2.4 | Develop screening tools
[6 empty] | 2.5 | Special Inventory Needs
[6 empty] | 2.6 | State Specific Analysis of EI Trends
[6 empty] | 3 | Air Quality Modeling
[6 empty] | 3.1 | Prepare modeling plan
[6 empty] | 3.2 | Prepare and evaluate meteorological data
[6 empty] | 3.3 | Perform dynamic model evaluations
[6 empty] | 3.4 | Conduct sensitivity testing
[6 empty] | 3.5 | Evaluate use of 2016 EPA modeling platform
[6 empty] | 3.6 | Conduct/Evaluate Base Year AQ Modeling
[6 empty] | 3.7 | Conduct/Evaluate 2028 AQ Modeling
[6 empty] | 4 | Evaluate Modeling Results
[6 empty] | 4.1 | Resolve tracking metric and model output issue
[6 empty] | 4.2 | Sensitivity/control strategy evaluation modeling for 2028
[6 empty] | 4.3 | Evaluate BY & 2028 source apportionment modeling results
[6 empty] | 4.4 | Evaluate change in visibility from BY to 2028
[6 empty] | 5 | Control Measure Analysis
[6 empty] | 5.1 | Develop criteria for source identification & 4-factor analysis
[6 empty] | 5.2 | Determine whether to use visibility as "fifth" factor
[6 empty] | 5.3 | Conduct regional/state source screening
[6 empty] | 5.4 | Evaluate emission source impacts on Class I areas
[6 empty] | 5.5 | Identify/incorporate 2028 emissions reductions from control strategies
[6 empty] | 6 | Coordinate Training and Outreach Efforts
[6 empty] | 6.1 | Assess needs for materials useful to SIP planners
[6 empty] | 6.2 | Identify and compile existing materials
[6 empty] | 6.3 | Develop new materials
[6 empty] | 6.4 | Oversee completion and distribution of materials
[6 empty] | 7 | Technical Support System TSS.v2
[6 empty] | 7.1 | Review TSS v1 for priority needs
[6 empty] | 7.2 | Coordinate and review TSS monitor data tool development
[6 empty] | 7.3 | Coordinate/review TSS emissions data and emissions projections tool development
[6 empty] | 7.4 | Coordinate and review TSS base year modeling tool development
[6 empty] | 7.5 | Coordinate and review TSS 2028 on-the-books modeling tool development
[6 empty] | 7.6 | Coordinate and reviewTSS reasonable control modeling tool development
[6 empty] | 7.7 | Provide TSS training webinars
[6 empty] | 8 | State Planning and Adoption Process
[6 empty] | 8.1 | Identify SIP planning target dates
[6 empty] | 8.2 | Establish consultation framework
[6 empty] | 8.3 | Coordinate and support consulation among WRAP member agencies
[6 empty] | 8.4 | Support state-led SIP development, consultation, and public review
[6 empty] | 8.5 | Submit SIP to U.S. EPA
Note on A1: Frank Forsgren:

## RH Planning Tech Support trac
WRAP 2018-2019 WorkPlan | [7 empty] | 2018 |  |  |  |  | 2019 |  |  |  |  | 2020 |  |  |  | 2021
RHP | RTO | F&S | O&G | TD | CON | # | Task | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3
Critical Milestones for Regional Haze Planning Technical Support
[7 empty] | Evaluation of RHR Revisions |  |  |  |  | X
Monitoring Data Evaluation
[7 empty] | Base, Planning, and Future Year Emissions Data work | [9 empty] | X
Base-year model platform and MPE completed
States use WRAP analysis for RH Planning
Future-year "on the books" scenarios modeling
[7 empty] | Source apportionment & sensitivity analysis | [5 empty] | X
[7 empty] | Technical work done, data products in TSS.v2 | [11 empty] | X
[7 empty] | SIP submission to EPA | [16 empty] | X
Timeline by Task
[6 empty] | 1 | Monitor Data Analysis
[6 empty] | 2 | Emission Inventory
[6 empty] | 3 | Air Quality Modeling
[6 empty] | 4 | Analyzing Future Year Evaluating Modeling Results
[6 empty] | 5 | Control Measures Analysis
[6 empty] | 6 | Coordinate Training and Outreach Efforts Embedded Progress Report
[6 empty] | 7 | Technical Support System
[6 empty] | 8 | States Planning and Adoption Process
Detailed Timeline by Task
[6 empty] | 1 | Monitoring Data Analysis
[6 empty] | 1.1 | Evaluate EPA tracking metric and alternatives
[6 empty] | 1.2 | Analyze monitor data (trends, ranges, linkages)
[6 empty] | 1.3 | Identify dominant visibility-impairing pollutants for each CIA
[6 empty] | 2 | Emissions Inventory
[6 empty] | 2.1 | Process and evaluate 2014 NEI and refinements
[6 empty] | 2.2 | Evaluate use of 2016 EPA modeling platform
[6 empty] | 2.3 | Develop and refine 2028 emission inventories
[6 empty] | 2.4 | Develop screening tools
[6 empty] | 2.5 | Special Inventory Needs
[6 empty] | 2.6 | State Specific Analysis of EI Trends
[6 empty] | 3 | Air Quality Modeling
[6 empty] | 3.1 | Prepare modeling plan
[6 empty] | 3.2 | Prepare and evaluate meteorological data
[6 empty] | 3.3 | Perform dynamic model evaluations
[6 empty] | 3.4 | Conduct sensitivity testing
[6 empty] | 3.5 | Evaluate use of 2016 EPA modeling platform
[6 empty] | 3.6 | Conduct/Evaluate AQ Modeling for BY and 2028 inventories Conduct/Evaluate Base Year AQ Modeling
[6 empty] | 3.7 | Conduct/Evaluate 2028 AQ Modeling
[6 empty] | 4 | Analyzing Evaluate Future Year Modeling Results
[6 empty] | 4.1 | Resolve tracking metric and model output issue
[6 empty] | 4.2 | Sensitivity/control strategy evaluation modeling for 2028
[6 empty] | 4.3 | Evaluate BY & 2028 source apportionment modeling results
[6 empty] | 4.4 | Evaluate change in visibility from BY to 2028
[6 empty] | 5 | Control Measure Analysis
[6 empty] | 5.1 | Develop criteria for source identification & 4-factor analysis
[6 empty] | 5.2 | Determine whether to use visibility as "fifth" factor
[6 empty] | 5.3 | Conduct regional/state source screening
[6 empty] | 5.4 | Evaluate emission source impacts on Class I areas States conduct control measure analysis
[6 empty] | 5.5 | Identify and incorporate 2028 emissions reductions from control strategies & add to 2028 inventory
[6 empty] | 6 | Coordinate Training and Outreach Efforts Embedded Progress Report
[6 empty] | 6.1 | Assess needs for materials useful to SIP planners Access visibility conditions and changes
[6 empty] | 6.2 | Identify and compile existing materials Analyze changes in emissions over the past 5 years
[6 empty] | 6.3 | Develop new materials Prepare progress report
[6 empty] | 6.4 | Oversee completion and distribution of materials
[6 empty] | 7 | Technical Support System TSS.v2
[6 empty] | 7.1 | Review TSS v1 for priority needs CIRA staff to reach out to RHPWG to review TSSv1 & v2
[6 empty] | 7.2 | PopulateCoordinate and review TSS with monitor data tool development
[6 empty] | 7.3 | Populate Coordinate and review TSS with emissions data and emissions projections tool development
[6 empty] | 7.4 | Populate Coordinate and review TSS base year modeling results tool development
[6 empty] | 7.5 | Populate Coordinate and review TSS 2028 on-the-books modeling results tool developmentProvide TSS training
[6 empty] | 7.6 | Populate Coordinate and reviewTSS v2 with 2028 ARC scenario reasonable control modeling results tool development Populate TSS with 2028 on-the-books modeling results
[6 empty] | 7.7 | Provide TSS training webinars Populate TSS with 2028 ARC scenario modeling results
[6 empty] | 8 | State Planning and Adoption Process
[6 empty] | 8.1 | Identify SIP planning target dates
[6 empty] | 8.2 | Establish consultation framework
[6 empty] | 8.3 | Coordinate and support consulation among with WRAP member agencies
[6 empty] | 8.4 | Support state-led SIP development, consultation, and public review Public comment review period (30 days)
[6 empty] | 8.5 | Submit SIP to U.S. EPA Deadline for submittal SIP Submission to USEPA
Original
Delete
Add
[6 empty] | Populate | Delete text
[6 empty] | Review | Add text
Note on A1: Frank Forsgren:

## Regional Analysis Support clean
WRAP 2018-2019 WorkPlan | [7 empty] | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021
RHP | RTO | F&S | O&G | TD | CON | # | Task | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3
Critical Milestones for Associated Regional Analysis Technical Support in 2018-2019
[6 empty] | 10.1 | BY Emissions Processing, Modeling
[6 empty] | 10.4 | 2028 Emissions projections
[6 empty] | 10.5 | IWDW-WAQS 2028 On-the-Books Air Quality Modeling
[6 empty] | 10.7 | IWDW-WAQS 2028 Control Scenarios’ Air Quality Modeling
WRAP tools / FETS update and operation
Historic and future fire activity and emisisons
Evaluation of smoke management plans
Ongoing Exceptional Events analysis and coordination
WRAP member-agency coordination on wildfire response &...
Review Existing Oil and Gas Work Products
ID regional and local air quality planning needs
[6 empty] | 13.1 | Help Tribes understand WRAP/WESTAR product benefits
[6 empty] | 13.2 | Solicit Tribal membership in WRAP and participation in TDWG
[6 empty] | 13.7 | Coordinate to facilitate support of TIPs and tribal programs
Detailed Timeline by Work Group
[6 empty] | 9 | Technical Steering Committee (TSC) Progress Calls and Meetings
Planning/Oversight/Coordination/Direction calls
Board/TSC/Co-Chairs meetings at Business Meetings
Biannual Planning/Progress/Informational Meetings
[6 empty] | 10 | Regional Technical Operations Work Group (RTOWG)
[6 empty] | 10.1 | BY Emissions Processing, Modeling
[6 empty] | 10.2 | Dynamic model evaluations for ozone/PM/nitrogen
[6 empty] | 10.3 | IWDW-WAQS AQ modeling for...
[6 empty] | 10.4 | 2028 Emissions projections
[6 empty] | 10.5 | IWDW-WAQS 2028 On-the-Books Air Quality Modeling
[6 empty] | 10.6 | IWDW-WAQS FY Source Apportionment/Sensitivity Modeling
[6 empty] | 10.7 | IWDW-WAQS 2028 Control Scenarios’ Air Quality Modeling
[6 empty] | 11 | Fire and Smoke Work Group (FSWG)
WRAP Tools/FETS Update and Operation
Historic and Future Fire Activity and Emissions
Evaluation of Smoke Management Plans
Exceptional Events: ID key data to collect for demonstrations
Coordination on wildfire response and smoke management
[6 empty] | 12 | Oil and Gas Work Group (OGWG)
Regional and local air quality planning needs
ID and review of member agency oil and gas programs
ID and review of member agency emissions management
Assess impacts from oil and gas production
Develop oil and gas tool box
Member agency collaboration on sub-regional oil and gas management
[6 empty] | 13 | Tribal Data Development Work Group (TDDWG)
[6 empty] | 13.1 | Help Tribes understand WRAP/WESTAR product benefits
[6 empty] | 13.2 | Solicit Tribal membership in WRAP and participation in TDWG
[6 empty] | 13.3 | Help Tribes understand monitoring data and use of AQS
[6 empty] | 13.4 | Help Tribes understand the EI process and NEI capability and use
[6 empty] | 13.6 | Ensure availablility of monitoring/emissions data from Tribes
[6 empty] | 13.7 | Coordinate to facilitate support of TIPs and tribal programs
[6 empty] | 13.8 | Provide educational opportunities for WRAP member Tribes
[6 empty] | 14 | Regional Haze Planning Work Group (RHPWG)
[6 empty] | 10.1 | BY Emissions Processing, Modeling
[6 empty] | 10.2 | Dynamic model evaluations for ozone/PM/nitrogen
[6 empty] | 10.3 | IWDW-WAQS AQ modeling for...
[6 empty] | 10.4 | 2028 Emissions projections
[6 empty] | 10.5 | IWDW-WAQS 2028 On-the-Books Air Quality Modeling
[6 empty] | 10.6 | IWDW-WAQS FY Source Apportionment/Sensitivity Modeling
[6 empty] | 10.7 | IWDW-WAQS 2028 Control Scenarios’ Air Quality Modeling
WRAP Tools/FETS Update and Operation
Historic and Future Fire Activity and Emissions
Evaluation of Smoke Management Plans
ID action items requiring coordination with others

## Regional Analysis Support trac
WRAP 2018-2019 WorkPlan | [7 empty] | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021
RHP | RTO | F&S | O&G | TD | CON | # | Task | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3
Critical Milestones for Associated Regional Analysis Technical Support in 2018-2019
[6 empty] | 10.1 | BY Emissions Processing, Modeling
[6 empty] | 10.4 | 2028 Emissions projections
[6 empty] | 10.5 | IWDW-WAQS 2028 On-the-Books Air Quality Modeling
[6 empty] | 10.7 | IWDW-WAQS 2028 Control Scenarios’ Air Quality Modeling
WRAP tools / FETS update and operation
Historic and future fire activity and emisisons
Evaluation of smoke management plans
Ongoing Exceptional Events analysis and coordination
WRAP member-agency coordination on wildfire response &...
Review Existing Oil and Gas Work Products
ID regional and local air quality planning needs
[6 empty] | 13.1 | Help Tribes understand WRAP/WESTAR product benefits
[6 empty] | 13.2 | Solicit Tribal membership in WRAP and participation in TDWG
[6 empty] | 13.7 | Coordinate to facilitate support of TIPs and tribal programs
Detailed Timeline by Work Group
[6 empty] | 9 | Technical Steering Committee (TSC) Progress Calls and Meetings
Planning/Oversight/Coordination/Direction calls
Board/TSC/Co-Chairs meetings at Business Meetings
Biannual Planning/Progress/Informational Meetings
[6 empty] | 10 | Regional Technical Operations Work Group (RTOWG)
[6 empty] | 10.1 | BY Emissions Processing, Modeling
[6 empty] | 10.2 | Dynamic model evaluations for ozone/PM/nitrogen
[6 empty] | 10.3 | IWDW-WAQS AQ modeling for...
[6 empty] | 10.4 | 2028 Emissions projections
[6 empty] | 10.5 | IWDW-WAQS 2028 On-the-Books Air Quality Modeling
[6 empty] | 10.6 | IWDW-WAQS FY Source Apportionment/Sensitivity Modeling
[6 empty] | 10.7 | IWDW-WAQS 2028 Control Scenarios’ Air Quality Modeling
[6 empty] | 11 | Fire and Smoke Work Group (FSWG)
WRAP Tools/FETS Update and Operation
Historic and Future Fire Activity and Emissions
Evaluation of Smoke Management Plans
Exceptional Events: ID key data to collect for demonstrations
Coordination on wildfire response and smoke management
[6 empty] | 12 | Oil and Gas Work Group (OGWG)
Regional and local air quality planning needs
ID and review of member agency oil and gas programs
ID and review of member agency emissions management
Assess impacts from oil and gas production
Develop oil and gas tool box
Member agency collaboration on sub-regional oil and gas management
[6 empty] | 13 | Tribal Data Development Work Group (TDDWG)
[6 empty] | 13.1 | Help Tribes understand WRAP/WESTAR product benefits
[6 empty] | 13.2 | Solicit Tribal membership in WRAP and participation in TDWG
[6 empty] | 13.3 | Help Tribes understand monitoring data and use of AQS
[6 empty] | 13.4 | Help Tribes understand the EI process and NEI capability and use
[6 empty] | 13.6 | Ensure availablility of monitoring/emissions data from Tribes
[6 empty] | 13.7 | Coordinate to facilitate support of TIPs and tribal programs
[6 empty] | 13.8 | Provide educational opportunities for WRAP member Tribes
[6 empty] | 14 | Regional Haze Planning Work Group (RHPWG)
[6 empty] | 10.1 | BY Emissions Processing, Modeling
[6 empty] | 10.2 | Dynamic model evaluations for ozone/PM/nitrogen
[6 empty] | 10.3 | IWDW-WAQS AQ modeling for...
[6 empty] | 10.4 | 2028 Emissions projections
[6 empty] | 10.5 | IWDW-WAQS 2028 On-the-Books Air Quality Modeling
[6 empty] | 10.6 | IWDW-WAQS FY Source Apportionment/Sensitivity Modeling
[6 empty] | 10.7 | IWDW-WAQS 2028 Control Scenarios’ Air Quality Modeling
WRAP Tools/FETS Update and Operation
Historic and Future Fire Activity and Emissions
Evaluation of Smoke Management Plans
ID action items requiring coordination with others
Original
Delete
Add
[6 empty] | Populate | Delete text
[6 empty] | Review | Add text
Note on H4: Meteorological modeling/MPE, Global Modeling/MPE, Regional Air Quality Modeling/MPE -Lexie Wilson
Note on H5: (contributions from OGWG, FSWG, rules on the books, and states) -Lexie Wilson
Note on H12: & smoke management -Lexie Wilson
Note on H24: Meteorological modeling/MPE, Global Modeling/MPE, Regional Air Quality Modeling/MPE -Lexie Wilson
Note on H26: ...Planning/4 Corners Study/coordinate with EPRI International Haze Study -Lexie Wilson
Note on H27: (contributions from OGWG, FSWG, rules on the books, and states) -Lexie Wilson
Note on H53: Meteorological modeling/MPE, Global Modeling/MPE, Regional Air Quality Modeling/MPE -Lexie Wilson
Note on H55: ...Planning/4 Corners Study/coordinate with EPRI International Haze Study -Lexie Wilson
Note on H56: (contributions from OGWG, FSWG, rules on the books, and states) -Lexie Wilson