## RH Planning Tech Support
WRAP 2018-2019 WorkPlan | [7 empty] | 2018 |  |  |  | 2019 |  |  |  |  | 2020 |  |  |  | 2021
RHP | RTO | F&S | O&G | TD | CON | # | Task | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3
Critical Milestones for Regional Haze Planning Technical Support
Evaluation of RHR Revisions
[7 empty] | Monitoring Data Evaluation | [16 empty] | Revised by RHPWG
[7 empty] | Base, Planning, and Future Year Emissions Data work | [8 empty] | X
Base-year model platform and MPE completed
States use WRAP analysis for RH Planning
Future-year "on the books" scenarios modeling
[7 empty] | Source apportionment & sensitivity analysis |  |  |  |  | X
[7 empty] | Technical work done, data products in TSS.v2 | [10 empty] | X
Timeline by Task
[6 empty] | 1 | Monitor Data Analysis | [16 empty] | Revised by RHPWG
[6 empty] | 2 | Emission Inventory
[6 empty] | 3 | Air Quality Modeling
[6 empty] | 4 | Analyzing Future Year Modeling Results
[6 empty] | 5 | Control Measures Analysis
[6 empty] | 6 | Embedded Progress Report
[6 empty] | 7 | Technical Support System
[6 empty] | 8 | States Planning and Adoption Process
Detailed Timeline by Task
[6 empty] | 1 | Monitoring Data Analysis
[6 empty] | 1.1 | Evaluate EPA tracking metric and alternatives | [16 empty] | Revised by RHPWG
[6 empty] | 1.2 | Analyze monitor data (trends, ranges, linkages) | [16 empty] | Revised by RHPWG
[6 empty] | 1.3 | Identify dominant visibility-impairing pollutants for each CIA | [16 empty] | Revised by RHPWG
[6 empty] | 2 | Emissions Inventory
[6 empty] | 2.1 | Process and evaluate 2014 NEI and refinements | [16 empty] | Revised by FSWG
[6 empty] | 2.2 | Evaluate use of 2016 EPA modeling platform
[6 empty] | 2.3 | Develop and refine 2028 emission inventories | [16 empty] | Revised by FSWG
[6 empty] | 2.4 | Develop screening tools
[6 empty] | 3 | Air Quality Modeling
[6 empty] | 3.1 | Prepare modeling plan
[6 empty] | 3.2 | Prepare and evaluate meteorological data
[6 empty] | 3.3 | Perform dynamic model evaluations
[6 empty] | 3.4 | Conduct sensitivity testing
[6 empty] | 3.5 | Evaluate use of 2016 EPA modeling platform
[6 empty] | 3.6 | Conduct/Evaluate AQ Modeling for BY and 2028 inventories
[6 empty] | 4 | Analyzing Future Year Modeling Results
[6 empty] | 4.1 | Resolve tracking metric and model output issue
[6 empty] | 4.2 | Sensitivity/control strategy evaluation modeling for 2028
[6 empty] | 4.3 | Evaluate BY & 2028 source apportionment modeling results
[6 empty] | 4.4 | Evaluate change in visibility from BY to 2028
[6 empty] | 5 | Control Measure Analysis
[6 empty] | 5.1 | Develop criteria for source identification & 4-factor analysis
[5 empty] | ?? | 5.2 | Determine whether to use visibility as "fifth" factor
[6 empty] | 5.3 | Conduct regional/state source screening
[6 empty] | 5.4 | States conduct control measure analysis
[6 empty] | 5.5 | Identify 2028 control strategies & add to 2028 inventory
[6 empty] | 6 | Embedded Progress Report
[6 empty] | 6.1 | Access visibility conditions and changes
[6 empty] | 6.2 | Analyze changes in emissions over the past 5 years
[6 empty] | 6.3 | Prepare progress report
[6 empty] | 7 | Technical Support System TSS.v2
[6 empty] | 7.1 | CIRA staff to reach out to RHPWG to review TSSv1 & v2
[6 empty] | 7.2 | Populate TSS with monitor data
[6 empty] | 7.3 | Populate TSS with emissions data | [16 empty] | Revised by RHPWG
[6 empty] | 7.4 | Populate TSS with base year modeling results | [16 empty] | Revised by RHPWG
[6 empty] | 7.5 | Provide TSS training | [16 empty] | Revised by RHPWG
[6 empty] | 7.6 | Populate TSS with 2028 on-the-books modeling results | [16 empty] | Revised by RHPWG
[6 empty] | 7.7 | Populate TSS with 2028 ARC scenario modeling results
[6 empty] | 8 | State Planning and Adoption Process
[6 empty] | 8.1 | Identify SIP planning target dates | [16 empty] | Revised by RHPWG
[6 empty] | 8.2 | Establish consultation framework | [16 empty] | Revised by RHPWG
[6 empty] | 8.3 | Consulation with WRAP member agencies
[6 empty] | 8.4 | Public comment review period (30 days) | [16 empty] | Revised by RHPWG
[6 empty] | 8.5 | Deadline for submittal SIP Submission to USEPA | [16 empty] | Revised by RHPWG
[6 empty] | 8.6 | Conduct stakeholders outreach (on-going) | [16 empty] | Revised by RHPWG
Note on A1: Frank Forsgren:
Note on H6: (on the books) -Lexie Wilson
Note on H30: (Q/d and weighted emission potential) -Lexie Wilson
Note on H35: boundary conditions, fire emissions, grid size, climate change -Lexie Wilson
Note on H37: Using source apportionment and sensitivity methods -Lexie Wilson BY = base year -Lexie Wilson
Note on H41: (OTW/OTB) Also - identify source sectors and facilities for control measures evaluation -Lexie Wilson BY = base year -Lexie Wilson
Note on H42: BY = base year -Lexie Wilson
Note on H44: a.k.a. "how to identify sources and move through the 4-factor analysis process" -Lexie Wilson based on monitor, emissions, screening, and modeling data -Lexie Wilson
Note on H45: for control measure analysis and identify threshold -Lexie Wilson
Note on H48: (Additional Reasonable Control scenario) -Lexie Wilson
Note on H60: ARC = Additional Reasonable Control -Lexie Wilson
Note on H64: including Federal Land Managers and Tribes, both formal and informal consulations -Lexie Wilson

## Regional Analysis Tech Support
WRAP 2018-2019 WorkPlan | [7 empty] | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021
RHP | RTO | F&S | O&G | TD | CON | # | Task | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3
Critical Milestones for Associated Regional Analysis Technical Support in 2018-2019
[6 empty] | 10.1 | BY Emissions Processing, Modeling
[6 empty] | 10.4 | 2028 Emissions projections
[6 empty] | 10.5 | IWDW-WAQS 2028 On-the-Books Air Quality Modeling
[6 empty] | 10.7 | IWDW-WAQS 2028 Control Scenarios’ Air Quality Modeling
[7 empty] | WRAP tools / FETS update and operation | [15 empty] | Revised by FSWG
[7 empty] | historic and future fire activity and emisisons | [15 empty] | Revised by FSWG
[7 empty] | evaluation of smoke management plans | [15 empty] | Revised by FSWG
[7 empty] | ongoing Exceptional Events analysis and coordination | [15 empty] | Revised by FSWG
[7 empty] | WRAP member-agency coordination on wildfire response &... | [15 empty] | Revised by FSWG
Review Existing Oil and Gas Work Products
ID regional and local air quality planning needs
[6 empty] | 13.1 | Help Tribes understand WRAP/WESTAR product benefits
[6 empty] | 13.2 | Solicit Tribal membership in WRAP and participation in TDWG
[6 empty] | 13.7 | Coordinate to facilitate support of TIPs and tribal programs
Detailed Timeline by Work Group
[6 empty] | 9 | Technical Steering Committee (TSC) Progress Calls and Meetings
Planning/Oversight/Coordination/Direction calls
Board/TSC/Co-Chairs meetings at Business Meetings
Biannual Planning/Progress/Informational Meetings
[6 empty] | 10 | Regional Technical Operations Work Group (RTOWG)
[6 empty] | 10.1 | BY Emissions Processing, Modeling
[6 empty] | 10.2 | Dynamic model evaluations for ozone/PM/nitrogen
[6 empty] | 10.3 | IWDW-WAQS AQ modeling for...
[6 empty] | 10.4 | 2028 Emissions projections
[6 empty] | 10.5 | IWDW-WAQS 2028 On-the-Books Air Quality Modeling
[6 empty] | 10.6 | IWDW-WAQS FY Source Apportionment/Sensitivity Modeling
[6 empty] | 10.7 | IWDW-WAQS 2028 Control Scenarios’ Air Quality Modeling
[6 empty] | 11 | Fire and Smoke Work Group (FSWG)
[7 empty] | WRAP Tools/FETS Update and Operation | [15 empty] | Revised by FSWG
[7 empty] | Historic and Future Fire Activity and Emissions | [15 empty] | Revised by FSWG
[7 empty] | Evaluation of Smoke Management Plans | [15 empty] | Revised by FSWG
[7 empty] | Exceptional Events: ID key data to collect for demonstrations | [15 empty] | Revised by FSWG
[7 empty] | Coordination on wildfire response and smoke management | [15 empty] | Revised by FSWG
[6 empty] | 12 | Oil and Gas Work Group (OGWG)
Regional and local air quality planning needs
ID and review of member agency oil and gas programs
ID and review of member agency emissions management
Assess impacts from oil and gas production
Develop oil and gas tool box
Member agency collaboration on sub-regional oil and gas management
[6 empty] | 13 | Tribal Data Development Work Group (TDDWG)
[6 empty] | 13.1 | Help Tribes understand WRAP/WESTAR product benefits
[6 empty] | 13.2 | Solicit Tribal membership in WRAP and participation in TDWG
[6 empty] | 13.3 | Help Tribes understand monitoring data and use of AQS
[6 empty] | 13.4 | Help Tribes understand the EI process and NEI capability and use
[6 empty] | 13.6 | Ensure availablility of monitoring/emissions data from Tribes
[6 empty] | 13.7 | Coordinate to facilitate support of TIPs and tribal programs
[6 empty] | 13.8 | Provide educational opportunities for WRAP member Tribes
[6 empty] | 14 | Regional Haze Planning Work Group (RHPWG)
[6 empty] | 10.2 | BY Emissions Processing, Modeling
[6 empty] | 10.3 | Dynamic model evaluations for ozone/PM/nitrogen
[6 empty] | 10.4 | IWDW-WAQS AQ modeling for...
[6 empty] | 10.5 | 2028 Emissions projections
[6 empty] | 10.6 | IWDW-WAQS 2028 On-the-Books Air Quality Modeling
[6 empty] | 10.7 | IWDW-WAQS FY Source Apportionment/Sensitivity Modeling
[6 empty] | 10.8 | IWDW-WAQS 2028 Control Scenarios’ Air Quality Modeling
[7 empty] | WRAP Tools/FETS Update and Operation | [15 empty] | Revised by FSWG
[7 empty] | Historic and Future Fire Activity and Emissions | [15 empty] | Revised by FSWG
[7 empty] | Evaluation of Smoke Management Plans | [15 empty] | Revised by FSWG
ID action items requiring coordination with others
Note on H4: Meteorological modeling/MPE, Global Modeling/MPE, Regional Air Quality Modeling/MPE -Lexie Wilson
Note on H5: (contributions from OGWG, FSWG, rules on the books, and states) -Lexie Wilson
Note on H12: & smoke management -Lexie Wilson
Note on H24: Meteorological modeling/MPE, Global Modeling/MPE, Regional Air Quality Modeling/MPE -Lexie Wilson
Note on H26: ...Planning/4 Corners Study/coordinate with EPRI International Haze Study -Lexie Wilson
Note on H27: (contributions from OGWG, FSWG, rules on the books, and states) -Lexie Wilson
Note on H53: Meteorological modeling/MPE, Global Modeling/MPE, Regional Air Quality Modeling/MPE -Lexie Wilson
Note on H55: ...Planning/4 Corners Study/coordinate with EPRI International Haze Study -Lexie Wilson
Note on H56: (contributions from OGWG, FSWG, rules on the books, and states) -Lexie Wilson