## Jan TSC activities table
WRAP 2018-2019 WorkPlan | [7 empty] | 2018 | [11 empty] | 2018
RHP | RTO | F&S | O&G | TD | CON | # | Task | J | F | M | A | M | J | J | A | S | O | N | D | January
[6 empty] | 1 | [13 empty] | Monitoring Data Analysis
[6 empty] | 1.1 | Evaluate EPA tracking metric and alternatives | bar: 2018 F to 2018 M
[6 empty] | 1.2 | Analyze monitor data (trends, ranges, linkages) | bar: 2018 M to 2018 J
[6 empty] | 1.3 | Identify dominant visibility-impairing pollutants for each CIA | bar: 2018 J
[6 empty] | 2 | [13 empty] | Emissions Inventory
[6 empty] | 2.1 | Process and evaluate 2014 NEI and refinements | [12 empty] | OGWG initiated contract with Ramboll for emission inventory road map project. OGWG/contractor call 1/24. | bar: 2018 F to 2018 M
[6 empty] | 2.2 | Evaluate use of 2016 EPA modeling platform | bar: 2018 J to 2018 A
[6 empty] | 2.3 | Develop and refine 2028 emission inventories | [12 empty] | OGWG initiated contract with Ramboll for emission inventory road map project. OGWG/contractor call 1/24. | bar: 2018 M to 2018 D
[6 empty] | 2.4 | Develop screening tools | bar: 2018 S to 2018 D
[6 empty] | 3 | [13 empty] | Air Quality Modeling
[6 empty] | 3.1 | Prepare modeling plan | bar: 2018 F to 2018 M
[6 empty] | 3.2 | Prepare and evaluate meteorological data | bar: 2018 M to 2018 A
[6 empty] | 3.3 | Perform dynamic model evaluations | bar: 2018 M to 2018 J
[6 empty] | 3.4 | Conduct sensitivity testing | bar: 2018 A to 2018 J
[6 empty] | 3.5 | Evaluate use of 2016 EPA modeling platform | bar: 2018 J to 2018 J
[6 empty] | 3.6 | Conduct/Evaluate AQ Modeling for BY and 2028 inventories | bar: 2018 A to 2018 D
[6 empty] | 4 | [13 empty] | Analyzing Future Year Modeling Results
[6 empty] | 4.1 | Resolve tracking metric and model output issue | bar: 2018 F to 2018 J
[6 empty] | 4.2 | Sensitivity/control strategy evaluation modeling for 2028
[6 empty] | 4.3 | Evaluate BY & 2028 source apportionment modeling results
[6 empty] | 4.4 | Evaluate change in visibility from BY to 2028
[6 empty] | 5 | [13 empty] | Control Measure Analysis
[6 empty] | 5.1 | Develop criteria for source identification & 4-factor analysis | bar: 2018 A to 2018 N
[5 empty] | ?? | 5.2 | Determine whether to use visibility as "fifth" factor | bar: 2018 A to 2018 N
[6 empty] | 5.3 | Conduct regional/state source screening | bar: 2018 D
[6 empty] | 5.4 | States conduct control measure analysis | bar: 2018 O to 2018 D
[6 empty] | 5.5 | Identify 2028 control strategies & add to 2028 inventory
[6 empty] | 6 | [13 empty] | Embedded Progress Report
[6 empty] | 6.1 | Access visibility conditions and changes
[6 empty] | 6.2 | Analyze changes in emissions over the past 5 years
[6 empty] | 6.3 | Prepare progress report
[6 empty] | 7 | [13 empty] | Technical Support System TSS.v2
[6 empty] | 7.1 | CIRA staff to reach out to RHPWG to review TSSv1 & v2 | bar: 2018 F to 2018 A
[6 empty] | 7.2 | Populate TSS with monitor data | bar: 2018 M to 2018 J
[6 empty] | 7.3 | Populate TSS with emissions data | bar: 2018 M to 2018 J
[6 empty] | 7.4 | Populate TSS with base year modeling results | bar: 2018 J to 2018 S
[6 empty] | 7.5 | Provide TSS training | bar: 2018 S to 2018 N
[6 empty] | 7.6 | Populate TSS with 2028 on-the-books modeling results
[6 empty] | 7.7 | Populate TSS with 2028 ARC scenario modeling results
[6 empty] | 8 | [13 empty] | State Planning and Adoption Process
[6 empty] | 8.1 | Identify SIP planning target dates | [12 empty] | TSC Workplan Development Calls: FSWG 1/12, 1/23, 1/30; OGWG 1/24; RTOWG 1/26, 1/30; TSC Co-Chairs 1/31; TSC/WG Co-Chairs 1/8 | bar: 2018 J to 2018 M
[6 empty] | 8.2 | Establish consultation framework | bar: 2018 J to 2018 D
[6 empty] | 8.3 | Consulation with WRAP member agencies
[6 empty] | 8.4 | Public comment period (30 days)
[6 empty] | 8.5 | SIP Submission to USEPA
Note on H11: (Q/d and weighted emission potential) -Lexie Wilson
Note on H16: boundary conditions, fire emissions, grid size, climate change -Lexie Wilson
Note on H18: Using source apportionment and sensitivity methods -Lexie Wilson BY = base year -Lexie Wilson
Note on H22: (OTW/OTB) Also - identify source sectors and facilities for control measures evaluation -Lexie Wilson BY = base year -Lexie Wilson
Note on H23: BY = base year -Lexie Wilson
Note on H25: a.k.a. "how to identify sources and move through the 4-factor analysis process" -Lexie Wilson based on monitor, emissions, screening, and modeling data -Lexie Wilson
Note on H26: for control measure analysis and identify threshold -Lexie Wilson
Note on H29: (Additional Reasonable Control scenario) -Lexie Wilson
Note on H41: ARC = Additional Reasonable Control -Lexie Wilson
Note on H45: including Federal Land Managers and Tribes, both formal and informal consulations -Lexie Wilson

## Feb TSC activities table
WRAP 2018-2019 WorkPlan | [7 empty] | 2018 | [11 empty] | 2018
RHP | RTO | F&S | O&G | TD | CON | # | Task | J | F | M | A | M | J | J | A | S | O | N | D | February
[6 empty] | 1 | [13 empty] | Monitoring Data Analysis
[6 empty] | 1.1 | Evaluate EPA tracking metric and alternatives | bar: 2018 F to 2018 M
[6 empty] | 1.2 | Analyze monitor data (trends, ranges, linkages) | bar: 2018 M to 2018 J
[6 empty] | 1.3 | Identify dominant visibility-impairing pollutants for each CIA | bar: 2018 J
[6 empty] | 2 | [13 empty] | Emissions Inventory
[6 empty] | 2.1 | Process and evaluate 2014 NEI and refinements | bar: 2018 F to 2018 M
[6 empty] | 2.2 | Evaluate use of 2016 EPA modeling platform | [12 empty] | RTOWG initiated contract with Ramboll for Modeling Representativeness Analsysis project. RTOWG/Contractor Calls on Modeling Representativeness Analysis Project: 2/9, 2/22 | bar: 2018 J to 2018 A
[6 empty] | 2.3 | Develop and refine 2028 emission inventories | bar: 2018 M to 2018 D
[6 empty] | 2.4 | Develop screening tools | bar: 2018 S to 2018 D
[6 empty] | 3 | [13 empty] | Air Quality Modeling
[6 empty] | 3.1 | Prepare modeling plan | [12 empty] | RTOWG initiated contract with Ramboll for Modeling Representativeness Analsysis project. RTOWG/Contractor Calls on Modeling Representativeness Analysis Project: 2/9, 2/22 | bar: 2018 F to 2018 M
[6 empty] | 3.2 | Prepare and evaluate meteorological data | bar: 2018 M to 2018 A
[6 empty] | 3.3 | Perform dynamic model evaluations | bar: 2018 M to 2018 J
[6 empty] | 3.4 | Conduct sensitivity testing | bar: 2018 A to 2018 J
[6 empty] | 3.5 | Evaluate use of 2016 EPA modeling platform | bar: 2018 J to 2018 J
[6 empty] | 3.6 | Conduct/Evaluate AQ Modeling for BY and 2028 inventories | bar: 2018 A to 2018 D
[6 empty] | 4 | [13 empty] | Analyzing Future Year Modeling Results
[6 empty] | 4.1 | Resolve tracking metric and model output issue | bar: 2018 F to 2018 J
[6 empty] | 4.2 | Sensitivity/control strategy evaluation modeling for 2028
[6 empty] | 4.3 | Evaluate BY & 2028 source apportionment modeling results
[6 empty] | 4.4 | Evaluate change in visibility from BY to 2028
[6 empty] | 5 | [13 empty] | Control Measure Analysis
[6 empty] | 5.1 | Develop criteria for source identification & 4-factor analysis | bar: 2018 A to 2018 N
[5 empty] | ?? | 5.2 | Determine whether to use visibility as "fifth" factor | bar: 2018 A to 2018 N
[6 empty] | 5.3 | Conduct regional/state source screening | bar: 2018 D
[6 empty] | 5.4 | States conduct control measure analysis | bar: 2018 O to 2018 D
[6 empty] | 5.5 | Identify 2028 control strategies & add to 2028 inventory
[6 empty] | 6 | [13 empty] | Embedded Progress Report
[6 empty] | 6.1 | Access visibility conditions and changes
[6 empty] | 6.2 | Analyze changes in emissions over the past 5 years
[6 empty] | 6.3 | Prepare progress report
[6 empty] | 7 | [13 empty] | Technical Support System TSS.v2
[6 empty] | 7.1 | CIRA staff to reach out to RHPWG to review TSSv1 & v2 | bar: 2018 F to 2018 A
[6 empty] | 7.2 | Populate TSS with monitor data | bar: 2018 M to 2018 J
[6 empty] | 7.3 | Populate TSS with emissions data | bar: 2018 M to 2018 J
[6 empty] | 7.4 | Populate TSS with base year modeling results | bar: 2018 J to 2018 S
[6 empty] | 7.5 | Provide TSS training | bar: 2018 S to 2018 N
[6 empty] | 7.6 | Populate TSS with 2028 on-the-books modeling results
[6 empty] | 7.7 | Populate TSS with 2028 ARC scenario modeling results
[6 empty] | 8 | [13 empty] | State Planning and Adoption Process
[6 empty] | 8.1 | Identify SIP planning target dates | [12 empty] | TSC Workplan Development Calls: FSWG 2/27; OGWG 2/13; RHPWG 2/7, 2/22; RTOWG 2/12; TSC Co-Chairs 2/15, 2/21; 2/27, 2/28; TSC/WG Co-Chairs 2/5, 2/9, 2/26 | bar: 2018 J to 2018 M
[6 empty] | 8.2 | Establish consultation framework | bar: 2018 J to 2018 D
[6 empty] | 8.3 | Consulation with WRAP member agencies
[6 empty] | 8.4 | Public comment period (30 days)
[6 empty] | 8.5 | SIP Submission to USEPA
Note on H11: (Q/d and weighted emission potential) -Lexie Wilson
Note on H16: boundary conditions, fire emissions, grid size, climate change -Lexie Wilson
Note on H18: Using source apportionment and sensitivity methods -Lexie Wilson BY = base year -Lexie Wilson
Note on H22: (OTW/OTB) Also - identify source sectors and facilities for control measures evaluation -Lexie Wilson BY = base year -Lexie Wilson
Note on H23: BY = base year -Lexie Wilson
Note on H25: a.k.a. "how to identify sources and move through the 4-factor analysis process" -Lexie Wilson based on monitor, emissions, screening, and modeling data -Lexie Wilson
Note on H26: for control measure analysis and identify threshold -Lexie Wilson
Note on H29: (Additional Reasonable Control scenario) -Lexie Wilson
Note on H41: ARC = Additional Reasonable Control -Lexie Wilson
Note on H45: including Federal Land Managers and Tribes, both formal and informal consulations -Lexie Wilson

## March TSC activities table
WRAP 2018-2019 WorkPlan | [7 empty] | 2018 | [11 empty] | 2018
RHP | RTO | F&S | O&G | TD | CON | # | Task | J | F | M | A | M | J | J | A | S | O | N | D | March
[6 empty] | 1 | [13 empty] | Monitoring Data Analysis
[6 empty] | 1.1 | Evaluate EPA tracking metric and alternatives | bar: 2018 F to 2018 M
[6 empty] | 1.2 | Analyze monitor data (trends, ranges, linkages) | bar: 2018 M to 2018 J
[6 empty] | 1.3 | Identify dominant visibility-impairing pollutants for each CIA | bar: 2018 J
[6 empty] | 2 | [13 empty] | Emissions Inventory
[6 empty] | 2.1 | Process and evaluate 2014 NEI and refinements | bar: 2018 F to 2018 M
[6 empty] | 2.2 | Evaluate use of 2016 EPA modeling platform | bar: 2018 J to 2018 A
[6 empty] | 2.3 | Develop and refine 2028 emission inventories | bar: 2018 M to 2018 D
[6 empty] | 2.4 | Develop screening tools | bar: 2018 S to 2018 D
[6 empty] | 3 | [13 empty] | Air Quality Modeling
[6 empty] | 3.1 | Prepare modeling plan | [12 empty] | RTOWG/Contractor Calls on Modeling Representativeness Analysis Project: 3/15, 3/22 | bar: 2018 F to 2018 M
[6 empty] | 3.2 | Prepare and evaluate meteorological data | bar: 2018 M to 2018 A
[6 empty] | 3.3 | Perform dynamic model evaluations | bar: 2018 M to 2018 J
[6 empty] | 3.4 | Conduct sensitivity testing | bar: 2018 A to 2018 J
[6 empty] | 3.5 | Evaluate use of 2016 EPA modeling platform | [12 empty] | RTOWG/Contractor Calls on Modeling Representativeness Analysis Project: 3/15, 3/22 | bar: 2018 J to 2018 J
[6 empty] | 3.6 | Conduct/Evaluate AQ Modeling for BY and 2028 inventories | bar: 2018 A to 2018 D
[6 empty] | 4 | [13 empty] | Analyzing Future Year Modeling Results
[6 empty] | 4.1 | Resolve tracking metric and model output issue | bar: 2018 F to 2018 J
[6 empty] | 4.2 | Sensitivity/control strategy evaluation modeling for 2028
[6 empty] | 4.3 | Evaluate BY & 2028 source apportionment modeling results
[6 empty] | 4.4 | Evaluate change in visibility from BY to 2028
[6 empty] | 5 | [13 empty] | Control Measure Analysis
[6 empty] | 5.1 | Develop criteria for source identification & 4-factor analysis | bar: 2018 A to 2018 N
[5 empty] | ?? | 5.2 | Determine whether to use visibility as "fifth" factor | bar: 2018 A to 2018 N
[6 empty] | 5.3 | Conduct regional/state source screening | bar: 2018 D
[6 empty] | 5.4 | States conduct control measure analysis | bar: 2018 O to 2018 D
[6 empty] | 5.5 | Identify 2028 control strategies & add to 2028 inventory
[6 empty] | 6 | [13 empty] | Embedded Progress Report
[6 empty] | 6.1 | Access visibility conditions and changes
[6 empty] | 6.2 | Analyze changes in emissions over the past 5 years
[6 empty] | 6.3 | Prepare progress report
[6 empty] | 7 | [13 empty] | Technical Support System TSS.v2
[6 empty] | 7.1 | CIRA staff to reach out to RHPWG to review TSSv1 & v2 | bar: 2018 F to 2018 A
[6 empty] | 7.2 | Populate TSS with monitor data | bar: 2018 M to 2018 J
[6 empty] | 7.3 | Populate TSS with emissions data | bar: 2018 M to 2018 J
[6 empty] | 7.4 | Populate TSS with base year modeling results | bar: 2018 J to 2018 S
[6 empty] | 7.5 | Provide TSS training | bar: 2018 S to 2018 N
[6 empty] | 7.6 | Populate TSS with 2028 on-the-books modeling results
[6 empty] | 7.7 | Populate TSS with 2028 ARC scenario modeling results
[6 empty] | 8 | [13 empty] | State Planning and Adoption Process
[6 empty] | 8.1 | Identify SIP planning target dates | [12 empty] | TSC Workplan Development Calls: OGWG 3/26; RHPWG 3/26; RTOWG 3/22; TSC Co-Chairs 3/5, 3/7, 3/8, 3/13, 3/14, 3/15, 3/26, 3/27 | bar: 2018 J to 2018 M
[6 empty] | 8.2 | Establish consultation framework | bar: 2018 J to 2018 D
[6 empty] | 8.3 | Consulation with WRAP member agencies
[6 empty] | 8.4 | Public comment period (30 days)
[6 empty] | 8.5 | SIP Submission to USEPA
Note on H11: (Q/d and weighted emission potential) -Lexie Wilson
Note on H16: boundary conditions, fire emissions, grid size, climate change -Lexie Wilson
Note on H18: Using source apportionment and sensitivity methods -Lexie Wilson BY = base year -Lexie Wilson
Note on H22: (OTW/OTB) Also - identify source sectors and facilities for control measures evaluation -Lexie Wilson BY = base year -Lexie Wilson
Note on H23: BY = base year -Lexie Wilson
Note on H25: a.k.a. "how to identify sources and move through the 4-factor analysis process" -Lexie Wilson based on monitor, emissions, screening, and modeling data -Lexie Wilson
Note on H26: for control measure analysis and identify threshold -Lexie Wilson
Note on H29: (Additional Reasonable Control scenario) -Lexie Wilson
Note on H41: ARC = Additional Reasonable Control -Lexie Wilson
Note on H45: including Federal Land Managers and Tribes, both formal and informal consulations -Lexie Wilson

## April TSC activities table
WRAP 2018-2019 WorkPlan | [7 empty] | 2018 | [11 empty] | 2018
RHP | RTO | F&S | O&G | TD | CON | # | Task | J | F | M | A | M | J | J | A | S | O | N | D | April
[6 empty] | 1 | [13 empty] | Monitoring Data Analysis
[6 empty] | 1.1 | Evaluate EPA tracking metric and alternatives | bar: 2018 F to 2018 M
[6 empty] | 1.2 | Analyze monitor data (trends, ranges, linkages) | bar: 2018 M to 2018 J
[6 empty] | 1.3 | Identify dominant visibility-impairing pollutants for each CIA | bar: 2018 J
[6 empty] | 2 | [13 empty] | Emissions Inventory
[6 empty] | 2.1 | Process and evaluate 2014 NEI and refinements | bar: 2018 F to 2018 M
[6 empty] | 2.2 | Evaluate use of 2016 EPA modeling platform | bar: 2018 J to 2018 A
[6 empty] | 2.3 | Develop and refine 2028 emission inventories | bar: 2018 M to 2018 D
[6 empty] | 2.4 | Develop screening tools | bar: 2018 S to 2018 D
[6 empty] | 3 | [13 empty] | Air Quality Modeling
[6 empty] | 3.1 | Prepare modeling plan | bar: 2018 F to 2018 M
[6 empty] | 3.2 | Prepare and evaluate meteorological data | bar: 2018 M to 2018 A
[6 empty] | 3.3 | Perform dynamic model evaluations | bar: 2018 M to 2018 J
[6 empty] | 3.4 | Conduct sensitivity testing | bar: 2018 A to 2018 J
[6 empty] | 3.5 | Evaluate use of 2016 EPA modeling platform | bar: 2018 J to 2018 J
[6 empty] | 3.6 | Conduct/Evaluate AQ Modeling for BY and 2028 inventories | bar: 2018 A to 2018 D
[6 empty] | 4 | [13 empty] | Analyzing Future Year Modeling Results
[6 empty] | 4.1 | Resolve tracking metric and model output issue | bar: 2018 F to 2018 J
[6 empty] | 4.2 | Sensitivity/control strategy evaluation modeling for 2028
[6 empty] | 4.3 | Evaluate BY & 2028 source apportionment modeling results
[6 empty] | 4.4 | Evaluate change in visibility from BY to 2028
[6 empty] | 5 | [13 empty] | Control Measure Analysis
[6 empty] | 5.1 | Develop criteria for source identification & 4-factor analysis | bar: 2018 A to 2018 N
[5 empty] | ?? | 5.2 | Determine whether to use visibility as "fifth" factor | bar: 2018 A to 2018 N
[6 empty] | 5.3 | Conduct regional/state source screening | bar: 2018 D
[6 empty] | 5.4 | States conduct control measure analysis | bar: 2018 O to 2018 D
[6 empty] | 5.5 | Identify 2028 control strategies & add to 2028 inventory
[6 empty] | 6 | [13 empty] | Embedded Progress Report
[6 empty] | 6.1 | Access visibility conditions and changes
[6 empty] | 6.2 | Analyze changes in emissions over the past 5 years
[6 empty] | 6.3 | Prepare progress report
[6 empty] | 7 | [13 empty] | Technical Support System TSS.v2
[6 empty] | 7.1 | CIRA staff to reach out to RHPWG to review TSSv1 & v2 | bar: 2018 F to 2018 A
[6 empty] | 7.2 | Populate TSS with monitor data | bar: 2018 M to 2018 J
[6 empty] | 7.3 | Populate TSS with emissions data | bar: 2018 M to 2018 J
[6 empty] | 7.4 | Populate TSS with base year modeling results | bar: 2018 J to 2018 S
[6 empty] | 7.5 | Provide TSS training | bar: 2018 S to 2018 N
[6 empty] | 7.6 | Populate TSS with 2028 on-the-books modeling results
[6 empty] | 7.7 | Populate TSS with 2028 ARC scenario modeling results
[6 empty] | 8 | [13 empty] | State Planning and Adoption Process
[6 empty] | 8.1 | Identify SIP planning target dates | bar: 2018 J to 2018 M
[6 empty] | 8.2 | Establish consultation framework | bar: 2018 J to 2018 D
[6 empty] | 8.3 | Consulation with WRAP member agencies
[6 empty] | 8.4 | Public comment period (30 days)
[6 empty] | 8.5 | SIP Submission to USEPA
Note on H11: (Q/d and weighted emission potential) -Lexie Wilson
Note on H16: boundary conditions, fire emissions, grid size, climate change -Lexie Wilson
Note on H18: Using source apportionment and sensitivity methods -Lexie Wilson BY = base year -Lexie Wilson
Note on H22: (OTW/OTB) Also - identify source sectors and facilities for control measures evaluation -Lexie Wilson BY = base year -Lexie Wilson
Note on H23: BY = base year -Lexie Wilson
Note on H25: a.k.a. "how to identify sources and move through the 4-factor analysis process" -Lexie Wilson based on monitor, emissions, screening, and modeling data -Lexie Wilson
Note on H26: for control measure analysis and identify threshold -Lexie Wilson
Note on H29: (Additional Reasonable Control scenario) -Lexie Wilson
Note on H41: ARC = Additional Reasonable Control -Lexie Wilson
Note on H45: including Federal Land Managers and Tribes, both formal and informal consulations -Lexie Wilson

## May TSC activities table
WRAP 2018-2019 WorkPlan | [7 empty] | 2018 | [11 empty] | 2018
RHP | RTO | F&S | O&G | TD | CON | # | Task | J | F | M | A | M | J | J | A | S | O | N | D | May
[6 empty] | 1 |  | 2018 May: Monitoring Data Analysis
[6 empty] | 1.1 | Evaluate EPA tracking metric and alternatives | bar: 2018 F to 2018 M
[6 empty] | 1.2 | Analyze monitor data (trends, ranges, linkages) | bar: 2018 M to 2018 J
[6 empty] | 1.3 | Identify dominant visibility-impairing pollutants for each CIA | bar: 2018 J
[6 empty] | 2 |  | 2018 May: Emissions Inventory
[6 empty] | 2.1 | Process and evaluate 2014 NEI and refinements | bar: 2018 F to 2018 M
[6 empty] | 2.2 | Evaluate use of 2016 EPA modeling platform | bar: 2018 J to 2018 A
[6 empty] | 2.3 | Develop and refine 2028 emission inventories | bar: 2018 M to 2018 D
[6 empty] | 2.4 | Develop screening tools | bar: 2018 S to 2018 D
[6 empty] | 3 |  | 2018 May: Air Quality Modeling
[6 empty] | 3.1 | Prepare modeling plan | bar: 2018 F to 2018 M
[6 empty] | 3.2 | Prepare and evaluate meteorological data | bar: 2018 M to 2018 A
[6 empty] | 3.3 | Perform dynamic model evaluations | bar: 2018 M to 2018 J
[6 empty] | 3.4 | Conduct sensitivity testing | bar: 2018 A to 2018 J
[6 empty] | 3.5 | Evaluate use of 2016 EPA modeling platform | bar: 2018 J to 2018 J
[6 empty] | 3.6 | Conduct/Evaluate AQ Modeling for BY and 2028 inventories | bar: 2018 A to 2018 D
[6 empty] | 4 |  | 2018 May: Analyzing Future Year Modeling Results
[6 empty] | 4.1 | Resolve tracking metric and model output issue | bar: 2018 F to 2018 J
[6 empty] | 4.2 | Sensitivity/control strategy evaluation modeling for 2028
[6 empty] | 4.3 | Evaluate BY & 2028 source apportionment modeling results
[6 empty] | 4.4 | Evaluate change in visibility from BY to 2028
[6 empty] | 5 |  | 2018 May: Control Measure Analysis
[6 empty] | 5.1 | Develop criteria for source identification & 4-factor analysis | bar: 2018 A to 2018 N
[5 empty] | ?? | 5.2 | Determine whether to use visibility as "fifth" factor | bar: 2018 A to 2018 N
[6 empty] | 5.3 | Conduct regional/state source screening | bar: 2018 D
[6 empty] | 5.4 | States conduct control measure analysis | bar: 2018 O to 2018 D
[6 empty] | 5.5 | Identify 2028 control strategies & add to 2028 inventory
[6 empty] | 6 |  | 2018 May: Embedded Progress Report
[6 empty] | 6.1 | Access visibility conditions and changes
[6 empty] | 6.2 | Analyze changes in emissions over the past 5 years
[6 empty] | 6.3 | Prepare progress report
[6 empty] | 7 |  | 2018 May: Technical Support System TSS.v2
[6 empty] | 7.1 | CIRA staff to reach out to RHPWG to review TSSv1 & v2 | bar: 2018 F to 2018 A
[6 empty] | 7.2 | Populate TSS with monitor data | bar: 2018 M to 2018 J
[6 empty] | 7.3 | Populate TSS with emissions data | bar: 2018 M to 2018 J
[6 empty] | 7.4 | Populate TSS with base year modeling results | bar: 2018 J to 2018 S
[6 empty] | 7.5 | Provide TSS training | bar: 2018 S to 2018 N
[6 empty] | 7.6 | Populate TSS with 2028 on-the-books modeling results
[6 empty] | 7.7 | Populate TSS with 2028 ARC scenario modeling results
[6 empty] | 8 |  | 2018 May: State Planning and Adoption Process
[6 empty] | 8.1 | Identify SIP planning target dates | bar: 2018 J to 2018 M
[6 empty] | 8.2 | Establish consultation framework | bar: 2018 J to 2018 D
[6 empty] | 8.3 | Consulation with WRAP member agencies | bar: 2018 F to 2018 D
[6 empty] | 8.4 | Public comment period (30 days)
[6 empty] | 8.5 | SIP Submission to USEPA
Note on H11: (Q/d and weighted emission potential) -Lexie Wilson
Note on H16: boundary conditions, fire emissions, grid size, climate change -Lexie Wilson
Note on H18: Using source apportionment and sensitivity methods -Lexie Wilson BY = base year -Lexie Wilson
Note on H22: (OTW/OTB) Also - identify source sectors and facilities for control measures evaluation -Lexie Wilson BY = base year -Lexie Wilson
Note on H23: BY = base year -Lexie Wilson
Note on H25: a.k.a. "how to identify sources and move through the 4-factor analysis process" -Lexie Wilson based on monitor, emissions, screening, and modeling data -Lexie Wilson
Note on H26: for control measure analysis and identify threshold -Lexie Wilson
Note on H29: (Additional Reasonable Control scenario) -Lexie Wilson
Note on H41: ARC = Additional Reasonable Control -Lexie Wilson
Note on H45: including Federal Land Managers and Tribes, both formal and informal consulations -Lexie Wilson

## June TSC activities table
WRAP 2018-2019 WorkPlan | [7 empty] | 2018 | [11 empty] | 2018
RHP | RTO | F&S | O&G | TD | CON | # | Task | J | F | M | A | M | J | J | A | S | O | N | D
[6 empty] | 1 | [13 empty] | Monitoring Data Analysis
[6 empty] | 1.1 | Evaluate EPA tracking metric and alternatives | bar: 2018 F to 2018 M
[6 empty] | 1.2 | Analyze monitor data (trends, ranges, linkages) | bar: 2018 M to 2018 J
[6 empty] | 1.3 | Identify dominant visibility-impairing pollutants for each CIA | bar: 2018 J
[6 empty] | 2 | [13 empty] | Emissions Inventory
[6 empty] | 2.1 | Process and evaluate 2014 NEI and refinements | bar: 2018 F to 2018 M
[6 empty] | 2.2 | Evaluate use of 2016 EPA modeling platform | bar: 2018 J to 2018 A
[6 empty] | 2.3 | Develop and refine 2028 emission inventories | bar: 2018 M to 2018 D
[6 empty] | 2.4 | Develop screening tools | bar: 2018 S to 2018 D
[6 empty] | 3 | [13 empty] | Air Quality Modeling
[6 empty] | 3.1 | Prepare modeling plan | bar: 2018 F to 2018 M
[6 empty] | 3.2 | Prepare and evaluate meteorological data | bar: 2018 M to 2018 A
[6 empty] | 3.3 | Perform dynamic model evaluations | bar: 2018 M to 2018 J
[6 empty] | 3.4 | Conduct sensitivity testing | bar: 2018 A to 2018 J
[6 empty] | 3.5 | Evaluate use of 2016 EPA modeling platform | bar: 2018 J to 2018 J
[6 empty] | 3.6 | Conduct/Evaluate AQ Modeling for BY and 2028 inventories | bar: 2018 A to 2018 D
[6 empty] | 4 | [13 empty] | Analyzing Future Year Modeling Results
[6 empty] | 4.1 | Resolve tracking metric and model output issue | bar: 2018 F to 2018 J
[6 empty] | 4.2 | Sensitivity/control strategy evaluation modeling for 2028
[6 empty] | 4.3 | Evaluate BY & 2028 source apportionment modeling results
[6 empty] | 4.4 | Evaluate change in visibility from BY to 2028
[6 empty] | 5 | [13 empty] | Control Measure Analysis
[6 empty] | 5.1 | Develop criteria for source identification & 4-factor analysis | bar: 2018 A to 2018 N
[5 empty] | ?? | 5.2 | Determine whether to use visibility as "fifth" factor | bar: 2018 A to 2018 N
[6 empty] | 5.3 | Conduct regional/state source screening | bar: 2018 D
[6 empty] | 5.4 | States conduct control measure analysis | bar: 2018 O to 2018 D
[6 empty] | 5.5 | Identify 2028 control strategies & add to 2028 inventory
[6 empty] | 6 | [13 empty] | Embedded Progress Report
[6 empty] | 6.1 | Access visibility conditions and changes
[6 empty] | 6.2 | Analyze changes in emissions over the past 5 years
[6 empty] | 6.3 | Prepare progress report
[6 empty] | 7 | [13 empty] | Technical Support System TSS.v2
[6 empty] | 7.1 | CIRA staff to reach out to RHPWG to review TSSv1 & v2 | bar: 2018 F to 2018 A
[6 empty] | 7.2 | Populate TSS with monitor data | bar: 2018 M to 2018 J
[6 empty] | 7.3 | Populate TSS with emissions data | bar: 2018 M to 2018 J
[6 empty] | 7.4 | Populate TSS with base year modeling results | bar: 2018 J to 2018 S
[6 empty] | 7.5 | Provide TSS training | bar: 2018 S to 2018 N
[6 empty] | 7.6 | Populate TSS with 2028 on-the-books modeling results
[6 empty] | 7.7 | Populate TSS with 2028 ARC scenario modeling results
[6 empty] | 8 | [13 empty] | State Planning and Adoption Process
[6 empty] | 8.1 | Identify SIP planning target dates | bar: 2018 J to 2018 M
[6 empty] | 8.2 | Establish consultation framework | bar: 2018 J to 2018 D
[6 empty] | 8.3 | Consulation with WRAP member agencies
[6 empty] | 8.4 | Public comment period (30 days)
[6 empty] | 8.5 | SIP Submission to USEPA
Note on H11: (Q/d and weighted emission potential) -Lexie Wilson
Note on H16: boundary conditions, fire emissions, grid size, climate change -Lexie Wilson
Note on H18: Using source apportionment and sensitivity methods -Lexie Wilson BY = base year -Lexie Wilson
Note on H22: (OTW/OTB) Also - identify source sectors and facilities for control measures evaluation -Lexie Wilson BY = base year -Lexie Wilson
Note on H23: BY = base year -Lexie Wilson
Note on H25: a.k.a. "how to identify sources and move through the 4-factor analysis process" -Lexie Wilson based on monitor, emissions, screening, and modeling data -Lexie Wilson
Note on H26: for control measure analysis and identify threshold -Lexie Wilson
Note on H29: (Additional Reasonable Control scenario) -Lexie Wilson
Note on H41: ARC = Additional Reasonable Control -Lexie Wilson
Note on H45: including Federal Land Managers and Tribes, both formal and informal consulations -Lexie Wilson

## July TSC activities table
WRAP 2018-2019 WorkPlan | [7 empty] | 2018 | [11 empty] | 2018
RHP | RTO | F&S | O&G | TD | CON | # | Task | J | F | M | A | M | J | J | A | S | O | N | D | July
[6 empty] | 1 | [13 empty] | Monitoring Data Analysis
[6 empty] | 1.1 | Evaluate EPA tracking metric and alternatives | bar: 2018 F to 2018 M
[6 empty] | 1.2 | Analyze monitor data (trends, ranges, linkages) | bar: 2018 M to 2018 J
[6 empty] | 1.3 | Identify dominant visibility-impairing pollutants for each CIA | bar: 2018 J
[6 empty] | 2 | [13 empty] | Emissions Inventory
[6 empty] | 2.1 | Process and evaluate 2014 NEI and refinements | bar: 2018 F to 2018 M
[6 empty] | 2.2 | Evaluate use of 2016 EPA modeling platform | bar: 2018 J to 2018 A
[6 empty] | 2.3 | Develop and refine 2028 emission inventories | bar: 2018 M to 2018 D
[6 empty] | 2.4 | Develop screening tools | bar: 2018 S to 2018 D
[6 empty] | 3 | [13 empty] | Air Quality Modeling
[6 empty] | 3.1 | Prepare modeling plan | bar: 2018 F to 2018 M
[6 empty] | 3.2 | Prepare and evaluate meteorological data | bar: 2018 M to 2018 A
[6 empty] | 3.3 | Perform dynamic model evaluations | bar: 2018 M to 2018 J
[6 empty] | 3.4 | Conduct sensitivity testing | bar: 2018 A to 2018 J
[6 empty] | 3.5 | Evaluate use of 2016 EPA modeling platform | bar: 2018 J to 2018 J
[6 empty] | 3.6 | Conduct/Evaluate AQ Modeling for BY and 2028 inventories | bar: 2018 A to 2018 D
[6 empty] | 4 | [13 empty] | Analyzing Future Year Modeling Results
[6 empty] | 4.1 | Resolve tracking metric and model output issue | bar: 2018 F to 2018 J
[6 empty] | 4.2 | Sensitivity/control strategy evaluation modeling for 2028
[6 empty] | 4.3 | Evaluate BY & 2028 source apportionment modeling results
[6 empty] | 4.4 | Evaluate change in visibility from BY to 2028
[6 empty] | 5 | [13 empty] | Control Measure Analysis
[6 empty] | 5.1 | Develop criteria for source identification & 4-factor analysis | bar: 2018 A to 2018 N
[5 empty] | ?? | 5.2 | Determine whether to use visibility as "fifth" factor | bar: 2018 A to 2018 N
[6 empty] | 5.3 | Conduct regional/state source screening | bar: 2018 D
[6 empty] | 5.4 | States conduct control measure analysis | bar: 2018 O to 2018 D
[6 empty] | 5.5 | Identify 2028 control strategies & add to 2028 inventory
[6 empty] | 6 | [13 empty] | Embedded Progress Report
[6 empty] | 6.1 | Access visibility conditions and changes
[6 empty] | 6.2 | Analyze changes in emissions over the past 5 years
[6 empty] | 6.3 | Prepare progress report
[6 empty] | 7 | [13 empty] | Technical Support System TSS.v2
[6 empty] | 7.1 | CIRA staff to reach out to RHPWG to review TSSv1 & v2 | bar: 2018 F to 2018 A
[6 empty] | 7.2 | Populate TSS with monitor data | bar: 2018 M to 2018 J
[6 empty] | 7.3 | Populate TSS with emissions data | bar: 2018 M to 2018 J
[6 empty] | 7.4 | Populate TSS with base year modeling results | bar: 2018 J to 2018 S
[6 empty] | 7.5 | Provide TSS training | bar: 2018 S to 2018 N
[6 empty] | 7.6 | Populate TSS with 2028 on-the-books modeling results
[6 empty] | 7.7 | Populate TSS with 2028 ARC scenario modeling results
[6 empty] | 8 | [13 empty] | State Planning and Adoption Process
[6 empty] | 8.1 | Identify SIP planning target dates | bar: 2018 J to 2018 M
[6 empty] | 8.2 | Establish consultation framework | bar: 2018 J to 2018 D
[6 empty] | 8.3 | Consulation with WRAP member agencies
[6 empty] | 8.4 | Public comment period (30 days)
[6 empty] | 8.5 | SIP Submission to USEPA
Note on H11: (Q/d and weighted emission potential) -Lexie Wilson
Note on H16: boundary conditions, fire emissions, grid size, climate change -Lexie Wilson
Note on H18: Using source apportionment and sensitivity methods -Lexie Wilson BY = base year -Lexie Wilson
Note on H22: (OTW/OTB) Also - identify source sectors and facilities for control measures evaluation -Lexie Wilson BY = base year -Lexie Wilson
Note on H23: BY = base year -Lexie Wilson
Note on H25: a.k.a. "how to identify sources and move through the 4-factor analysis process" -Lexie Wilson based on monitor, emissions, screening, and modeling data -Lexie Wilson
Note on H26: for control measure analysis and identify threshold -Lexie Wilson
Note on H29: (Additional Reasonable Control scenario) -Lexie Wilson
Note on H41: ARC = Additional Reasonable Control -Lexie Wilson
Note on H45: including Federal Land Managers and Tribes, both formal and informal consulations -Lexie Wilson

## Aug TSC activities table
WRAP 2018-2019 WorkPlan | [7 empty] | 2018 | [11 empty] | 2018
RHP | RTO | F&S | O&G | TD | CON | # | Task | J | F | M | A | M | J | J | A | S | O | N | D | August
[6 empty] | 1 | [13 empty] | Monitoring Data Analysis
[6 empty] | 1.1 | Evaluate EPA tracking metric and alternatives | bar: 2018 F to 2018 M
[6 empty] | 1.2 | Analyze monitor data (trends, ranges, linkages) | bar: 2018 M to 2018 J
[6 empty] | 1.3 | Identify dominant visibility-impairing pollutants for each CIA | bar: 2018 J
[6 empty] | 2 | [13 empty] | Emissions Inventory
[6 empty] | 2.1 | Process and evaluate 2014 NEI and refinements | bar: 2018 F to 2018 M
[6 empty] | 2.2 | Evaluate use of 2016 EPA modeling platform | bar: 2018 J to 2018 A
[6 empty] | 2.3 | Develop and refine 2028 emission inventories | bar: 2018 M to 2018 D
[6 empty] | 2.4 | Develop screening tools | bar: 2018 S to 2018 D
[6 empty] | 3 | [13 empty] | Air Quality Modeling
[6 empty] | 3.1 | Prepare modeling plan | bar: 2018 F to 2018 M
[6 empty] | 3.2 | Prepare and evaluate meteorological data | bar: 2018 M to 2018 A
[6 empty] | 3.3 | Perform dynamic model evaluations | bar: 2018 M to 2018 J
[6 empty] | 3.4 | Conduct sensitivity testing | bar: 2018 A to 2018 J
[6 empty] | 3.5 | Evaluate use of 2016 EPA modeling platform | bar: 2018 J to 2018 J
[6 empty] | 3.6 | Conduct/Evaluate AQ Modeling for BY and 2028 inventories | bar: 2018 A to 2018 D
[6 empty] | 4 | [13 empty] | Analyzing Future Year Modeling Results
[6 empty] | 4.1 | Resolve tracking metric and model output issue | bar: 2018 F to 2018 J
[6 empty] | 4.2 | Sensitivity/control strategy evaluation modeling for 2028
[6 empty] | 4.3 | Evaluate BY & 2028 source apportionment modeling results
[6 empty] | 4.4 | Evaluate change in visibility from BY to 2028
[6 empty] | 5 | [13 empty] | Control Measure Analysis
[6 empty] | 5.1 | Develop criteria for source identification & 4-factor analysis | bar: 2018 A to 2018 N
[5 empty] | ?? | 5.2 | Determine whether to use visibility as "fifth" factor | bar: 2018 A to 2018 N
[6 empty] | 5.3 | Conduct regional/state source screening | bar: 2018 D
[6 empty] | 5.4 | States conduct control measure analysis | bar: 2018 O to 2018 D
[6 empty] | 5.5 | Identify 2028 control strategies & add to 2028 inventory
[6 empty] | 6 | [13 empty] | Embedded Progress Report
[6 empty] | 6.1 | Access visibility conditions and changes
[6 empty] | 6.2 | Analyze changes in emissions over the past 5 years
[6 empty] | 6.3 | Prepare progress report
[6 empty] | 7 | [13 empty] | Technical Support System TSS.v2
[6 empty] | 7.1 | CIRA staff to reach out to RHPWG to review TSSv1 & v2 | bar: 2018 F to 2018 A
[6 empty] | 7.2 | Populate TSS with monitor data | bar: 2018 M to 2018 J
[6 empty] | 7.3 | Populate TSS with emissions data | bar: 2018 M to 2018 J
[6 empty] | 7.4 | Populate TSS with base year modeling results | bar: 2018 J to 2018 S
[6 empty] | 7.5 | Provide TSS training | bar: 2018 S to 2018 N
[6 empty] | 7.6 | Populate TSS with 2028 on-the-books modeling results
[6 empty] | 7.7 | Populate TSS with 2028 ARC scenario modeling results
[6 empty] | 8 | [13 empty] | State Planning and Adoption Process
[6 empty] | 8.1 | Identify SIP planning target dates | bar: 2018 J to 2018 M
[6 empty] | 8.2 | Establish consultation framework | bar: 2018 J to 2018 D
[6 empty] | 8.3 | Consulation with WRAP member agencies
[6 empty] | 8.4 | Public comment period (30 days)
[6 empty] | 8.5 | SIP Submission to USEPA
Note on H11: (Q/d and weighted emission potential) -Lexie Wilson
Note on H16: boundary conditions, fire emissions, grid size, climate change -Lexie Wilson
Note on H18: Using source apportionment and sensitivity methods -Lexie Wilson BY = base year -Lexie Wilson
Note on H22: (OTW/OTB) Also - identify source sectors and facilities for control measures evaluation -Lexie Wilson BY = base year -Lexie Wilson
Note on H23: BY = base year -Lexie Wilson
Note on H25: a.k.a. "how to identify sources and move through the 4-factor analysis process" -Lexie Wilson based on monitor, emissions, screening, and modeling data -Lexie Wilson
Note on H26: for control measure analysis and identify threshold -Lexie Wilson
Note on H29: (Additional Reasonable Control scenario) -Lexie Wilson
Note on H41: ARC = Additional Reasonable Control -Lexie Wilson
Note on H45: including Federal Land Managers and Tribes, both formal and informal consulations -Lexie Wilson

## Sept TSC activities table
WRAP 2018-2019 WorkPlan | [7 empty] | 2018 | [11 empty] | 2018
RHP | RTO | F&S | O&G | TD | CON | # | Task | J | F | M | A | M | J | J | A | S | O | N | D | September
[6 empty] | 1 | [13 empty] | Monitoring Data Analysis
[6 empty] | 1.1 | Evaluate EPA tracking metric and alternatives | bar: 2018 F to 2018 M
[6 empty] | 1.2 | Analyze monitor data (trends, ranges, linkages) | bar: 2018 M to 2018 J
[6 empty] | 1.3 | Identify dominant visibility-impairing pollutants for each CIA | bar: 2018 J
[6 empty] | 2 | [13 empty] | Emissions Inventory
[6 empty] | 2.1 | Process and evaluate 2014 NEI and refinements | bar: 2018 F to 2018 M
[6 empty] | 2.2 | Evaluate use of 2016 EPA modeling platform | bar: 2018 J to 2018 A
[6 empty] | 2.3 | Develop and refine 2028 emission inventories | bar: 2018 M to 2018 D
[6 empty] | 2.4 | Develop screening tools | bar: 2018 S to 2018 D
[6 empty] | 3 | [13 empty] | Air Quality Modeling
[6 empty] | 3.1 | Prepare modeling plan | bar: 2018 F to 2018 M
[6 empty] | 3.2 | Prepare and evaluate meteorological data | bar: 2018 M to 2018 A
[6 empty] | 3.3 | Perform dynamic model evaluations | bar: 2018 M to 2018 J
[6 empty] | 3.4 | Conduct sensitivity testing | bar: 2018 A to 2018 J
[6 empty] | 3.5 | Evaluate use of 2016 EPA modeling platform | bar: 2018 J to 2018 J
[6 empty] | 3.6 | Conduct/Evaluate AQ Modeling for BY and 2028 inventories | bar: 2018 A to 2018 D
[6 empty] | 4 | [13 empty] | Analyzing Future Year Modeling Results
[6 empty] | 4.1 | Resolve tracking metric and model output issue | bar: 2018 F to 2018 J
[6 empty] | 4.2 | Sensitivity/control strategy evaluation modeling for 2028
[6 empty] | 4.3 | Evaluate BY & 2028 source apportionment modeling results
[6 empty] | 4.4 | Evaluate change in visibility from BY to 2028
[6 empty] | 5 | [13 empty] | Control Measure Analysis
[6 empty] | 5.1 | Develop criteria for source identification & 4-factor analysis | bar: 2018 A to 2018 N
[5 empty] | ?? | 5.2 | Determine whether to use visibility as "fifth" factor | bar: 2018 A to 2018 N
[6 empty] | 5.3 | Conduct regional/state source screening | bar: 2018 D
[6 empty] | 5.4 | States conduct control measure analysis | bar: 2018 O to 2018 D
[6 empty] | 5.5 | Identify 2028 control strategies & add to 2028 inventory
[6 empty] | 6 | [13 empty] | Embedded Progress Report
[6 empty] | 6.1 | Access visibility conditions and changes
[6 empty] | 6.2 | Analyze changes in emissions over the past 5 years
[6 empty] | 6.3 | Prepare progress report
[6 empty] | 7 | [13 empty] | Technical Support System TSS.v2
[6 empty] | 7.1 | CIRA staff to reach out to RHPWG to review TSSv1 & v2 | bar: 2018 F to 2018 A
[6 empty] | 7.2 | Populate TSS with monitor data | bar: 2018 M to 2018 J
[6 empty] | 7.3 | Populate TSS with emissions data | bar: 2018 M to 2018 J
[6 empty] | 7.4 | Populate TSS with base year modeling results | bar: 2018 J to 2018 S
[6 empty] | 7.5 | Provide TSS training | bar: 2018 S to 2018 N
[6 empty] | 7.6 | Populate TSS with 2028 on-the-books modeling results
[6 empty] | 7.7 | Populate TSS with 2028 ARC scenario modeling results
[6 empty] | 8 | [13 empty] | State Planning and Adoption Process
[6 empty] | 8.1 | Identify SIP planning target dates | bar: 2018 J to 2018 M
[6 empty] | 8.2 | Establish consultation framework | bar: 2018 J to 2018 D
[6 empty] | 8.3 | Consulation with WRAP member agencies
[6 empty] | 8.4 | Public comment period (30 days)
[6 empty] | 8.5 | SIP Submission to USEPA
Note on H11: (Q/d and weighted emission potential) -Lexie Wilson
Note on H16: boundary conditions, fire emissions, grid size, climate change -Lexie Wilson
Note on H18: Using source apportionment and sensitivity methods -Lexie Wilson BY = base year -Lexie Wilson
Note on H22: (OTW/OTB) Also - identify source sectors and facilities for control measures evaluation -Lexie Wilson BY = base year -Lexie Wilson
Note on H23: BY = base year -Lexie Wilson
Note on H25: a.k.a. "how to identify sources and move through the 4-factor analysis process" -Lexie Wilson based on monitor, emissions, screening, and modeling data -Lexie Wilson
Note on H26: for control measure analysis and identify threshold -Lexie Wilson
Note on H29: (Additional Reasonable Control scenario) -Lexie Wilson
Note on H41: ARC = Additional Reasonable Control -Lexie Wilson
Note on H45: including Federal Land Managers and Tribes, both formal and informal consulations -Lexie Wilson

## Oct TSC activities table
WRAP 2018-2019 WorkPlan | [7 empty] | 2018 | [11 empty] | 2018
RHP | RTO | F&S | O&G | TD | CON | # | Task | J | F | M | A | M | J | J | A | S | O | N | D | October
[6 empty] | 1 | [13 empty] | Monitoring Data Analysis
[6 empty] | 1.1 | Evaluate EPA tracking metric and alternatives | bar: 2018 F to 2018 M
[6 empty] | 1.2 | Analyze monitor data (trends, ranges, linkages) | bar: 2018 M to 2018 J
[6 empty] | 1.3 | Identify dominant visibility-impairing pollutants for each CIA | bar: 2018 J
[6 empty] | 2 | [13 empty] | Emissions Inventory
[6 empty] | 2.1 | Process and evaluate 2014 NEI and refinements | bar: 2018 F to 2018 M
[6 empty] | 2.2 | Evaluate use of 2016 EPA modeling platform | bar: 2018 J to 2018 A
[6 empty] | 2.3 | Develop and refine 2028 emission inventories | bar: 2018 M to 2018 D
[6 empty] | 2.4 | Develop screening tools | bar: 2018 S to 2018 D
[6 empty] | 3 | [13 empty] | Air Quality Modeling
[6 empty] | 3.1 | Prepare modeling plan | bar: 2018 F to 2018 M
[6 empty] | 3.2 | Prepare and evaluate meteorological data | bar: 2018 M to 2018 A
[6 empty] | 3.3 | Perform dynamic model evaluations | bar: 2018 M to 2018 J
[6 empty] | 3.4 | Conduct sensitivity testing | bar: 2018 A to 2018 J
[6 empty] | 3.5 | Evaluate use of 2016 EPA modeling platform | bar: 2018 J to 2018 J
[6 empty] | 3.6 | Conduct/Evaluate AQ Modeling for BY and 2028 inventories | bar: 2018 A to 2018 D
[6 empty] | 4 | [13 empty] | Analyzing Future Year Modeling Results
[6 empty] | 4.1 | Resolve tracking metric and model output issue | bar: 2018 F to 2018 J
[6 empty] | 4.2 | Sensitivity/control strategy evaluation modeling for 2028
[6 empty] | 4.3 | Evaluate BY & 2028 source apportionment modeling results
[6 empty] | 4.4 | Evaluate change in visibility from BY to 2028
[6 empty] | 5 | [13 empty] | Control Measure Analysis
[6 empty] | 5.1 | Develop criteria for source identification & 4-factor analysis | bar: 2018 A to 2018 N
[5 empty] | ?? | 5.2 | Determine whether to use visibility as "fifth" factor | bar: 2018 A to 2018 N
[6 empty] | 5.3 | Conduct regional/state source screening | bar: 2018 D
[6 empty] | 5.4 | States conduct control measure analysis | bar: 2018 O to 2018 D
[6 empty] | 5.5 | Identify 2028 control strategies & add to 2028 inventory
[6 empty] | 6 | [13 empty] | Embedded Progress Report
[6 empty] | 6.1 | Access visibility conditions and changes
[6 empty] | 6.2 | Analyze changes in emissions over the past 5 years
[6 empty] | 6.3 | Prepare progress report
[6 empty] | 7 | [13 empty] | Technical Support System TSS.v2
[6 empty] | 7.1 | CIRA staff to reach out to RHPWG to review TSSv1 & v2 | bar: 2018 F to 2018 A
[6 empty] | 7.2 | Populate TSS with monitor data | bar: 2018 M to 2018 J
[6 empty] | 7.3 | Populate TSS with emissions data | bar: 2018 M to 2018 J
[6 empty] | 7.4 | Populate TSS with base year modeling results | bar: 2018 J to 2018 S
[6 empty] | 7.5 | Provide TSS training | bar: 2018 S to 2018 N
[6 empty] | 7.6 | Populate TSS with 2028 on-the-books modeling results
[6 empty] | 7.7 | Populate TSS with 2028 ARC scenario modeling results
[6 empty] | 8 | [13 empty] | State Planning and Adoption Process
[6 empty] | 8.1 | Identify SIP planning target dates | bar: 2018 J to 2018 M
[6 empty] | 8.2 | Establish consultation framework | bar: 2018 J to 2018 D
[6 empty] | 8.3 | Consulation with WRAP member agencies
[6 empty] | 8.4 | Public comment period (30 days)
[6 empty] | 8.5 | SIP Submission to USEPA
Note on H11: (Q/d and weighted emission potential) -Lexie Wilson
Note on H16: boundary conditions, fire emissions, grid size, climate change -Lexie Wilson
Note on H18: Using source apportionment and sensitivity methods -Lexie Wilson BY = base year -Lexie Wilson
Note on H22: (OTW/OTB) Also - identify source sectors and facilities for control measures evaluation -Lexie Wilson BY = base year -Lexie Wilson
Note on H23: BY = base year -Lexie Wilson
Note on H25: a.k.a. "how to identify sources and move through the 4-factor analysis process" -Lexie Wilson based on monitor, emissions, screening, and modeling data -Lexie Wilson
Note on H26: for control measure analysis and identify threshold -Lexie Wilson
Note on H29: (Additional Reasonable Control scenario) -Lexie Wilson
Note on H41: ARC = Additional Reasonable Control -Lexie Wilson
Note on H45: including Federal Land Managers and Tribes, both formal and informal consulations -Lexie Wilson

## Nov TSC activities table
WRAP 2018-2019 WorkPlan | [7 empty] | 2018 | [11 empty] | 2018
RHP | RTO | F&S | O&G | TD | CON | # | Task | J | F | M | A | M | J | J | A | S | O | N | D | November
[6 empty] | 1 | [13 empty] | Monitoring Data Analysis
[6 empty] | 1.1 | Evaluate EPA tracking metric and alternatives | bar: 2018 F to 2018 M
[6 empty] | 1.2 | Analyze monitor data (trends, ranges, linkages) | bar: 2018 M to 2018 J
[6 empty] | 1.3 | Identify dominant visibility-impairing pollutants for each CIA | bar: 2018 J
[6 empty] | 2 | [13 empty] | Emissions Inventory
[6 empty] | 2.1 | Process and evaluate 2014 NEI and refinements | bar: 2018 F to 2018 M
[6 empty] | 2.2 | Evaluate use of 2016 EPA modeling platform | bar: 2018 J to 2018 A
[6 empty] | 2.3 | Develop and refine 2028 emission inventories | bar: 2018 M to 2018 D
[6 empty] | 2.4 | Develop screening tools | bar: 2018 S to 2018 D
[6 empty] | 3 | [13 empty] | Air Quality Modeling
[6 empty] | 3.1 | Prepare modeling plan | bar: 2018 F to 2018 M
[6 empty] | 3.2 | Prepare and evaluate meteorological data | bar: 2018 M to 2018 A
[6 empty] | 3.3 | Perform dynamic model evaluations | bar: 2018 M to 2018 J
[6 empty] | 3.4 | Conduct sensitivity testing | bar: 2018 A to 2018 J
[6 empty] | 3.5 | Evaluate use of 2016 EPA modeling platform | bar: 2018 J to 2018 J
[6 empty] | 3.6 | Conduct/Evaluate AQ Modeling for BY and 2028 inventories | bar: 2018 A to 2018 D
[6 empty] | 4 | [13 empty] | Analyzing Future Year Modeling Results
[6 empty] | 4.1 | Resolve tracking metric and model output issue | bar: 2018 F to 2018 J
[6 empty] | 4.2 | Sensitivity/control strategy evaluation modeling for 2028
[6 empty] | 4.3 | Evaluate BY & 2028 source apportionment modeling results
[6 empty] | 4.4 | Evaluate change in visibility from BY to 2028
[6 empty] | 5 | [13 empty] | Control Measure Analysis
[6 empty] | 5.1 | Develop criteria for source identification & 4-factor analysis | bar: 2018 A to 2018 N
[5 empty] | ?? | 5.2 | Determine whether to use visibility as "fifth" factor | bar: 2018 A to 2018 N
[6 empty] | 5.3 | Conduct regional/state source screening | bar: 2018 D
[6 empty] | 5.4 | States conduct control measure analysis | bar: 2018 O to 2018 D
[6 empty] | 5.5 | Identify 2028 control strategies & add to 2028 inventory
[6 empty] | 6 | [13 empty] | Embedded Progress Report
[6 empty] | 6.1 | Access visibility conditions and changes
[6 empty] | 6.2 | Analyze changes in emissions over the past 5 years
[6 empty] | 6.3 | Prepare progress report
[6 empty] | 7 | [13 empty] | Technical Support System TSS.v2
[6 empty] | 7.1 | CIRA staff to reach out to RHPWG to review TSSv1 & v2 | bar: 2018 F to 2018 A
[6 empty] | 7.2 | Populate TSS with monitor data | bar: 2018 M to 2018 J
[6 empty] | 7.3 | Populate TSS with emissions data | bar: 2018 M to 2018 J
[6 empty] | 7.4 | Populate TSS with base year modeling results | bar: 2018 J to 2018 S
[6 empty] | 7.5 | Provide TSS training | bar: 2018 S to 2018 N
[6 empty] | 7.6 | Populate TSS with 2028 on-the-books modeling results
[6 empty] | 7.7 | Populate TSS with 2028 ARC scenario modeling results
[6 empty] | 8 | [13 empty] | State Planning and Adoption Process
[6 empty] | 8.1 | Identify SIP planning target dates | bar: 2018 J to 2018 M
[6 empty] | 8.2 | Establish consultation framework | bar: 2018 J to 2018 D
[6 empty] | 8.3 | Consulation with WRAP member agencies
[6 empty] | 8.4 | Public comment period (30 days)
[6 empty] | 8.5 | SIP Submission to USEPA
Note on H11: (Q/d and weighted emission potential) -Lexie Wilson
Note on H16: boundary conditions, fire emissions, grid size, climate change -Lexie Wilson
Note on H18: Using source apportionment and sensitivity methods -Lexie Wilson BY = base year -Lexie Wilson
Note on H22: (OTW/OTB) Also - identify source sectors and facilities for control measures evaluation -Lexie Wilson BY = base year -Lexie Wilson
Note on H23: BY = base year -Lexie Wilson
Note on H25: a.k.a. "how to identify sources and move through the 4-factor analysis process" -Lexie Wilson based on monitor, emissions, screening, and modeling data -Lexie Wilson
Note on H26: for control measure analysis and identify threshold -Lexie Wilson
Note on H29: (Additional Reasonable Control scenario) -Lexie Wilson
Note on H41: ARC = Additional Reasonable Control -Lexie Wilson
Note on H45: including Federal Land Managers and Tribes, both formal and informal consulations -Lexie Wilson

## Dec TSC activities table
WRAP 2018-2019 WorkPlan | [7 empty] | 2018 | [11 empty] | 2018
RHP | RTO | F&S | O&G | TD | CON | # | Task | J | F | M | A | M | J | J | A | S | O | N | D | December
[6 empty] | 1 | [13 empty] | Monitoring Data Analysis
[6 empty] | 1.1 | Evaluate EPA tracking metric and alternatives | bar: 2018 F to 2018 M
[6 empty] | 1.2 | Analyze monitor data (trends, ranges, linkages) | bar: 2018 M to 2018 J
[6 empty] | 1.3 | Identify dominant visibility-impairing pollutants for each CIA | bar: 2018 J
[6 empty] | 2 | [13 empty] | Emissions Inventory
[6 empty] | 2.1 | Process and evaluate 2014 NEI and refinements | bar: 2018 F to 2018 M
[6 empty] | 2.2 | Evaluate use of 2016 EPA modeling platform | bar: 2018 J to 2018 A
[6 empty] | 2.3 | Develop and refine 2028 emission inventories | bar: 2018 M to 2018 D
[6 empty] | 2.4 | Develop screening tools | bar: 2018 S to 2018 D
[6 empty] | 3 | [13 empty] | Air Quality Modeling
[6 empty] | 3.1 | Prepare modeling plan | bar: 2018 F to 2018 M
[6 empty] | 3.2 | Prepare and evaluate meteorological data | bar: 2018 M to 2018 A
[6 empty] | 3.3 | Perform dynamic model evaluations | bar: 2018 M to 2018 J
[6 empty] | 3.4 | Conduct sensitivity testing | bar: 2018 A to 2018 J
[6 empty] | 3.5 | Evaluate use of 2016 EPA modeling platform | bar: 2018 J to 2018 J
[6 empty] | 3.6 | Conduct/Evaluate AQ Modeling for BY and 2028 inventories | bar: 2018 A to 2018 D
[6 empty] | 4 | [13 empty] | Analyzing Future Year Modeling Results
[6 empty] | 4.1 | Resolve tracking metric and model output issue | bar: 2018 F to 2018 J
[6 empty] | 4.2 | Sensitivity/control strategy evaluation modeling for 2028
[6 empty] | 4.3 | Evaluate BY & 2028 source apportionment modeling results
[6 empty] | 4.4 | Evaluate change in visibility from BY to 2028
[6 empty] | 5 | [13 empty] | Control Measure Analysis
[6 empty] | 5.1 | Develop criteria for source identification & 4-factor analysis | bar: 2018 A to 2018 N
[5 empty] | ?? | 5.2 | Determine whether to use visibility as "fifth" factor | bar: 2018 A to 2018 N
[6 empty] | 5.3 | Conduct regional/state source screening | bar: 2018 D
[6 empty] | 5.4 | States conduct control measure analysis | bar: 2018 O to 2018 D
[6 empty] | 5.5 | Identify 2028 control strategies & add to 2028 inventory
[6 empty] | 6 | [13 empty] | Embedded Progress Report
[6 empty] | 6.1 | Access visibility conditions and changes
[6 empty] | 6.2 | Analyze changes in emissions over the past 5 years
[6 empty] | 6.3 | Prepare progress report
[6 empty] | 7 | [13 empty] | Technical Support System TSS.v2
[6 empty] | 7.1 | CIRA staff to reach out to RHPWG to review TSSv1 & v2 | bar: 2018 F to 2018 A
[6 empty] | 7.2 | Populate TSS with monitor data | bar: 2018 M to 2018 J
[6 empty] | 7.3 | Populate TSS with emissions data | bar: 2018 M to 2018 J
[6 empty] | 7.4 | Populate TSS with base year modeling results | bar: 2018 J to 2018 S
[6 empty] | 7.5 | Provide TSS training | bar: 2018 S to 2018 N
[6 empty] | 7.6 | Populate TSS with 2028 on-the-books modeling results
[6 empty] | 7.7 | Populate TSS with 2028 ARC scenario modeling results
[6 empty] | 8 | [13 empty] | State Planning and Adoption Process
[6 empty] | 8.1 | Identify SIP planning target dates | bar: 2018 J to 2018 M
[6 empty] | 8.2 | Establish consultation framework | bar: 2018 J to 2018 D
[6 empty] | 8.3 | Consulation with WRAP member agencies
[6 empty] | 8.4 | Public comment period (30 days)
[6 empty] | 8.5 | SIP Submission to USEPA
Note on H11: (Q/d and weighted emission potential) -Lexie Wilson
Note on H16: boundary conditions, fire emissions, grid size, climate change -Lexie Wilson
Note on H18: Using source apportionment and sensitivity methods -Lexie Wilson BY = base year -Lexie Wilson
Note on H22: (OTW/OTB) Also - identify source sectors and facilities for control measures evaluation -Lexie Wilson BY = base year -Lexie Wilson
Note on H23: BY = base year -Lexie Wilson
Note on H25: a.k.a. "how to identify sources and move through the 4-factor analysis process" -Lexie Wilson based on monitor, emissions, screening, and modeling data -Lexie Wilson
Note on H26: for control measure analysis and identify threshold -Lexie Wilson
Note on H29: (Additional Reasonable Control scenario) -Lexie Wilson
Note on H41: ARC = Additional Reasonable Control -Lexie Wilson
Note on H45: including Federal Land Managers and Tribes, both formal and informal consulations -Lexie Wilson

## Template 4 TSC activities table
WRAP 2018-2019 WorkPlan | [7 empty] | 2018 | [11 empty] | 2018
RHP | RTO | F&S | O&G | TD | CON | # | Task | J | F | M | A | M | J | J | A | S | O | N | D
[6 empty] | 1 | [13 empty] | Monitoring Data Analysis
[6 empty] | 1.1 | Evaluate EPA tracking metric and alternatives | bar: 2018 F to 2018 M
[6 empty] | 1.2 | Analyze monitor data (trends, ranges, linkages) | bar: 2018 M to 2018 J
[6 empty] | 1.3 | Identify dominant visibility-impairing pollutants for each CIA | bar: 2018 J
[6 empty] | 2 | [13 empty] | Emissions Inventory
[6 empty] | 2.1 | Process and evaluate 2014 NEI and refinements | bar: 2018 F to 2018 M
[6 empty] | 2.2 | Evaluate use of 2016 EPA modeling platform | bar: 2018 J to 2018 A
[6 empty] | 2.3 | Develop and refine 2028 emission inventories | bar: 2018 M to 2018 D
[6 empty] | 2.4 | Develop screening tools | bar: 2018 S to 2018 D
[6 empty] | 3 | [13 empty] | Air Quality Modeling
[6 empty] | 3.1 | Prepare modeling plan | bar: 2018 F to 2018 M
[6 empty] | 3.2 | Prepare and evaluate meteorological data | bar: 2018 M to 2018 A
[6 empty] | 3.3 | Perform dynamic model evaluations | bar: 2018 M to 2018 J
[6 empty] | 3.4 | Conduct sensitivity testing | bar: 2018 A to 2018 J
[6 empty] | 3.5 | Evaluate use of 2016 EPA modeling platform | bar: 2018 J to 2018 J
[6 empty] | 3.6 | Conduct/Evaluate AQ Modeling for BY and 2028 inventories | bar: 2018 A to 2018 D
[6 empty] | 4 | [13 empty] | Analyzing Future Year Modeling Results
[6 empty] | 4.1 | Resolve tracking metric and model output issue | bar: 2018 F to 2018 J
[6 empty] | 4.2 | Sensitivity/control strategy evaluation modeling for 2028
[6 empty] | 4.3 | Evaluate BY & 2028 source apportionment modeling results
[6 empty] | 4.4 | Evaluate change in visibility from BY to 2028
[6 empty] | 5 | [13 empty] | Control Measure Analysis
[6 empty] | 5.1 | Develop criteria for source identification & 4-factor analysis | bar: 2018 A to 2018 N
[5 empty] | ?? | 5.2 | Determine whether to use visibility as "fifth" factor | bar: 2018 A to 2018 N
[6 empty] | 5.3 | Conduct regional/state source screening | bar: 2018 D
[6 empty] | 5.4 | States conduct control measure analysis | bar: 2018 O to 2018 D
[6 empty] | 5.5 | Identify 2028 control strategies & add to 2028 inventory
[6 empty] | 6 | [13 empty] | Embedded Progress Report
[6 empty] | 6.1 | Access visibility conditions and changes
[6 empty] | 6.2 | Analyze changes in emissions over the past 5 years
[6 empty] | 6.3 | Prepare progress report
[6 empty] | 7 | [13 empty] | Technical Support System TSS.v2
[6 empty] | 7.1 | CIRA staff to reach out to RHPWG to review TSSv1 & v2 | bar: 2018 F to 2018 A
[6 empty] | 7.2 | Populate TSS with monitor data | bar: 2018 M to 2018 J
[6 empty] | 7.3 | Populate TSS with emissions data | bar: 2018 M to 2018 J
[6 empty] | 7.4 | Populate TSS with base year modeling results | bar: 2018 J to 2018 S
[6 empty] | 7.5 | Provide TSS training | bar: 2018 S to 2018 N
[6 empty] | 7.6 | Populate TSS with 2028 on-the-books modeling results
[6 empty] | 7.7 | Populate TSS with 2028 ARC scenario modeling results
[6 empty] | 8 | [13 empty] | State Planning and Adoption Process
[6 empty] | 8.1 | Identify SIP planning target dates | bar: 2018 J to 2018 M
[6 empty] | 8.2 | Establish consultation framework | bar: 2018 J to 2018 D
[6 empty] | 8.3 | Consulation with WRAP member agencies
[6 empty] | 8.4 | Public comment period (30 days)
[6 empty] | 8.5 | SIP Submission to USEPA
Note on H11: (Q/d and weighted emission potential) -Lexie Wilson
Note on H16: boundary conditions, fire emissions, grid size, climate change -Lexie Wilson
Note on H18: Using source apportionment and sensitivity methods -Lexie Wilson BY = base year -Lexie Wilson
Note on H22: (OTW/OTB) Also - identify source sectors and facilities for control measures evaluation -Lexie Wilson BY = base year -Lexie Wilson
Note on H23: BY = base year -Lexie Wilson
Note on H25: a.k.a. "how to identify sources and move through the 4-factor analysis process" -Lexie Wilson based on monitor, emissions, screening, and modeling data -Lexie Wilson
Note on H26: for control measure analysis and identify threshold -Lexie Wilson
Note on H29: (Additional Reasonable Control scenario) -Lexie Wilson
Note on H41: ARC = Additional Reasonable Control -Lexie Wilson
Note on H45: including Federal Land Managers and Tribes, both formal and informal consulations -Lexie Wilson

## RH activities table
WRAP 2018-2019 WorkPlan | [7 empty] | 2018 | [11 empty] | 2018
RHP | RTO | F&S | O&G | TD | CON | # | Task | J | F | M | A | M | J | J | A | S | O | N | D | January | February | March | April | May | June | July | August | September | October | November | December
[6 empty] | 1 | [13 empty] | 2018 January: Monitoring Data Analysis
[6 empty] | 1.1 | Evaluate EPA tracking metric and alternatives
[6 empty] | 1.2 | Analyze monitor data (trends, ranges, linkages)
[6 empty] | 1.3 | Identify dominant visibility-impairing pollutants for each CIA
[6 empty] | 2 | [13 empty] | 2018 January: Emissions Inventory
[6 empty] | 2.1 | Process and evaluate 2014 NEI and refinements
[6 empty] | 2.2 | Evaluate use of 2016 EPA modeling platform
[6 empty] | 2.3 | Develop and refine 2028 emission inventories
[6 empty] | 2.4 | Develop screening tools
[6 empty] | 3 | [13 empty] | 2018 January: Air Quality Modeling
[6 empty] | 3.1 | Prepare modeling plan
[6 empty] | 3.2 | Prepare and evaluate meteorological data
[6 empty] | 3.3 | Perform dynamic model evaluations
[6 empty] | 3.4 | Conduct sensitivity testing
[6 empty] | 3.5 | Evaluate use of 2016 EPA modeling platform
[6 empty] | 3.6 | Conduct/Evaluate AQ Modeling for BY and 2028 inventories
[6 empty] | 4 | [13 empty] | 2018 January: Analyzing Future Year Modeling Results
[6 empty] | 4.1 | Resolve tracking metric and model output issue
[6 empty] | 4.2 | Sensitivity/control strategy evaluation modeling for 2028
[6 empty] | 4.3 | Evaluate BY & 2028 source apportionment modeling results
[6 empty] | 4.4 | Evaluate change in visibility from BY to 2028
[6 empty] | 5 | [13 empty] | 2018 January: Control Measure Analysis
[6 empty] | 5.1 | Develop criteria for source identification & 4-factor analysis
[5 empty] | ?? | 5.2 | Determine whether to use visibility as "fifth" factor
[6 empty] | 5.3 | Conduct regional/state source screening
[6 empty] | 5.4 | States conduct control measure analysis
[6 empty] | 5.5 | Identify 2028 control strategies & add to 2028 inventory
[6 empty] | 6 | [13 empty] | 2018 January: Embedded Progress Report
[6 empty] | 6.1 | Access visibility conditions and changes
[6 empty] | 6.2 | Analyze changes in emissions over the past 5 years
[6 empty] | 6.3 | Prepare progress report
[6 empty] | 7 | [13 empty] | 2018 January: Technical Support System TSS.v2
[6 empty] | 7.1 | CIRA staff to reach out to RHPWG to review TSSv1 & v2
[6 empty] | 7.2 | Populate TSS with monitor data
[6 empty] | 7.3 | Populate TSS with emissions data
[6 empty] | 7.4 | Populate TSS with base year modeling results
[6 empty] | 7.5 | Provide TSS training
[6 empty] | 7.6 | Populate TSS with 2028 on-the-books modeling results
[6 empty] | 7.7 | Populate TSS with 2028 ARC scenario modeling results
[6 empty] | 8 | [13 empty] | 2018 January: State Planning and Adoption Process
[6 empty] | 8.1 | Identify SIP planning target dates
[6 empty] | 8.2 | Establish consultation framework
[6 empty] | 8.3 | Consulation with WRAP member agencies
[6 empty] | 8.4 | Public comment period (30 days)
[6 empty] | 8.5 | SIP Submission to USEPA
added a year to front end for early submitters
moved up 6 months
Note on H11: (Q/d and weighted emission potential) -Lexie Wilson
Note on H16: boundary conditions, fire emissions, grid size, climate change -Lexie Wilson
Note on H18: Using source apportionment and sensitivity methods -Lexie Wilson BY = base year -Lexie Wilson
Note on H22: (OTW/OTB) Also - identify source sectors and facilities for control measures evaluation -Lexie Wilson BY = base year -Lexie Wilson
Note on H23: BY = base year -Lexie Wilson
Note on H25: a.k.a. "how to identify sources and move through the 4-factor analysis process" -Lexie Wilson based on monitor, emissions, screening, and modeling data -Lexie Wilson
Note on H26: for control measure analysis and identify threshold -Lexie Wilson
Note on H29: (Additional Reasonable Control scenario) -Lexie Wilson
Note on H41: ARC = Additional Reasonable Control -Lexie Wilson
Note on H45: including Federal Land Managers and Tribes, both formal and informal consulations -Lexie Wilson

## Sheet1
2018-01-01
New
* 8.1 ID SIP planning target dates
2018-02-01
New
* 1.1 Evaluate EPA tracking metric and alternatives
* 2.1 Process and evaluate 2014 NEI and refinements
* 3.1 Prepare modeling plan
* 4.1 Resolve tracking metric and model output issue
* 7.1 CIRA staff to reach out to RHPWG to review TSS v1 and v2
* 8.3 Consult with WRAP member agencies
On-Going
* 8.1 ID SIP planning target dates
2018-03-01
New
* 1.2 Analyze monitor data (trends, ranges, and linkages)
* 3.2 Prepare and evaluate meteorological data
* 3.3 Perform dynamic model evaluations
On-Going
* 1.1 Evaluate EPA tracking metric and alternatives
* 2.1 Process and evaluate 2014 NEI and refinements
* 3.1 Prepare modeling plan
* 4.1 Resolve tracking metric and model output issue
* 7.1 CIRA staff to reach out to RHPWG to review TSS v1 and v2
* 8.1 ID SIP planning target dates
* 8.3 Consultation with WRAP member agencies
2018-04-01
New
* 3.4 Conduct sensitivity testing
* 3.6 Conduct/Evaluate AQ modeling for base year and 2028 inventories
On-Going
* 1.1 Evaluate EPA tracking metric and alternatives
* 1.2 Analyze monitor data (trends, ranges, and linkages)
* 2.1 Process and evaluate 2014 NEI and refinements
* 3.2 Prepare and evaluate meteorological data
* 3.3 Perform dynamic model evaluations
* 4.1 Resolve tracking metric and model output issue
* 7.1 CIRA staff to reach out to RHPWG to review TSS v1 and v2
* 8.3 Consultation with WRAP member agencies
2018-05-01
New
* 2.3 Develop and refine 2028 emission inventory
* 7.2 Populate TSS with monitor data
* 7.3 Populate TSS with emissions data
On-Going
* 1.1 Evaluate EPA tracking metric and alternatives
* 1.2 Analyze monitor data (trends, ranges, and linkages)
* 2.1 Process and evaluate 2014 NEI and refinements
* 3.3 Perform dynamic model evaluations
* 3.4 Conduct sensitivity testing
* 3.6 Conduct/Evaluate AQ modeling for base year and 2028 inventories
* 4.1 Resolve tracking metric and model output issue
* 8.3 Consultation with WRAP member agencies
2018-06-01
New
* 2.2 Evaluate use of 2016 EPA modeling platform
* 3.5 Evaluate use of 2016 EPA modeling platform
* 8.2 Establish consultation framework
On-Going
* 1.2 Analyze monitor data (trends, ranges, and linkages)
* 2.3 Develop and refine 2028 emission inventory
* 3.3 Perform dynamic model evaluations
* 3.4 Conduct sensitivity testing
* 3.6 Conduct/Evaluate AQ modeling for base year and 2028 inventories
* 4.1 Resolve tracking metric and model output issue
* 7.2 Populate TSS with monitor data
* 7.3 Populate TSS with emissions data
* 8.3 Consultation with WRAP member agencies
2018-07-01
New
* 1.3 Identify dominant visibility-impairing pollutants
* 7.4 Populate TSS with base year modeling results
On-Going
* 2.2 Evaluate use of 2016 EPA modeling platform
* 2.3 Develop and refine 2028 emission inventory
* 3.3 Perform dynamic model evaluations
* 3.4 Conduct sensitivity testing3.5 Evaluate use of 2016 EPA modeling platform
* 3.6 Conduct/Evaluate AQ modeling for base year and 2028 inventories
* 4.1 Resolve tracking metric and model output issue
* 7.2 Populate TSS with monitor data
* 7.4 Populate TSS with base year modeling results
* 8.2 Establish consultation framework
* 8.3 Consultation with WRAP member agencies
2018-08-01
New
* 5.1 Develop criteria for source identification and 4-factor analysis
* 5.2 Determine whether to use visibility as a “fifth” factor
On-Going
* 2.2 Evaluate use of 2016 EPA modeling platform
* 2.3 Develop and refine 2028 emission inventory
* 3.6 Conduct/Evaluate AQ modeling for base year and 2028 inventories
* 7.4 Populate TSS with base year modeling results
* 8.2 Establish consultation framework
* 8.3 Consultation with WRAP member agencies
2018-09-01
New
* 2.4 Develop screening tools
* 7.5 Provide TSS training
On-Going
* 2.3 Develop and refine 2028 emission inventory
* 3.6 Conduct/Evaluate AQ modeling for base year and 2028 inventories
* 5.1 Develop criteria for source identification and 4-factor analysis
* 5.2 Determine whether to use visibility as a “fifth” factor
* 7.4 Populate TSS with base year modeling results
* 8.2 Establish consultation framework
* 8.3 Consultation with WRAP member agencies
2018-10-01
New
* 5.4 States conduct control measures analysis
On-Going
* 2.3 Develop and refine 2028 emission inventory
* 2.4 Develop screening tools
* 3.6 Conduct/Evaluate AQ modeling for base year and 2028 inventories
* 5.1 Develop criteria for source identification and 4-factor analysis
* 5.2 Determine whether to use visibility as a “fifth” factor
* 7.5 Provide TSS training
* 8.2 Establish consultation framework
* 8.3 Consultation with WRAP member agencies
2018-11-01
New
* ----
On-Going
* 2.3 Develop and refine 2028 emission inventory
* 2.4 Develop screening tools
* 3.6 Conduct/Evaluate AQ modeling for base year and 2028 inventories
* 5.1 Develop criteria for source identification and 4-factor analysis
* 5.2 Determine whether to use visibility as a “fifth” factor
* 5.4 States conduct control measures analysis
* 7.5 Provide TSS training
* 8.2 Establish consultation framework
* 8.3 Consultation with WRAP member agencies
2018-12-01
New
* 5.3 Conduct regional/state source screening
On-Going
* 2.3 Develop and refine 2028 emission inventory
* 2.4 Develop screening tools
* 3.6 Conduct/Evaluate AQ modeling for base year and 2028 inventories
* 5.4 States conduct control measures analysis
* 8.2 Establish consultation framework
* 8.3 Consultation with WRAP member agencies
RHPWG – Monthly Listing of 2018 Tasks
3/19/18 fmf
1