## Slide 1: Upcoming projects* to support Regional Haze SIP/TIP planning
Regional Haze Planning Readiness Assessment
Emissions analysis for Electrical Generating Units
Regional Modeling Platform
* Technical Project Mgmt. teams to be designated as needed

## Slide 2: Regional Haze Planning Readiness Assessment
Supported by Regional Analysis funds from western state air programs ($25k)
Ramboll Environment & Health
  Julia Lester, project lead
Scope (complete by Dec. 2018):
  Task 1: Review and compile relevant planning documents (Aug.-Sept.)
  Task 2: Review on-line products of WRAP Regional Haze Planning Work Group and Subcommittees
    Design and implement a Planning Readiness Survey (Sept.-Oct.)
    Follow-up with each WESTAR-WRAP state (Oct.)
  Task 3: Develop a Synthesis Report (late Oct.-Nov.)
    Draft final report for review and discussion at Dec. 4-6, 2018 Technical Planning Meeting on WRAP Workplan progress
    Report to identify Regional Haze coordination/communication needs between states, tribes, local air agencies, federal land managers, and EPA
  Task 4: Organize / upload materials to updated RHPWG web page (Dec.)

## Slide 3: Analysis of EGU Emissions for Regional Haze Planning and Ozone Transport Contribution
Funded by Western Energy Supply and Transmission (WEST) Associates (up to $50k)
September 15, 2018 to March 15, 2019
Center for the New Energy Economy, CSU
  Patrick Cummins, project lead
Scope:
  Develop a comprehensive database of information on the fleet of fossil-fired EGUs in 13 Western states (circa 2014-2017) that contains information on the plants’ operating characteristics and emissions; and
  A projection of future plant utilization and emissions based on expected plant closures, re-powering plans, and additional controls required under a “rules on the books” scenario that includes any controls required by permit or consent decree during the period 2014 (base year) to 2028 (target year).
1-day workshop with EGU operators and states
  Salt Lake City
  Oct. 30, 2018
  WESTAR to support travel for 1 person from each state
  Ticketleap link to be distributed

## Slide 4: Regional Haze Modeling and Analysis Platform - WESTAR Request for Proposals:
Will use detail from IWDW-WAQS Workplan and WRAP 2018-2019 Workplan
  WRAP Workplan approved April 2018
  IWDW-WAQS Workplan to be approved late Sept.
    Workplans describe how to apply funds already at / on the way to WESTAR
    All combined funds from IWDW-WAQS and WRAP Regional Analysis will likely be awarded during next 18 months
  RFP release in Sept., contract award in Oct.
  Approval of contract by WESTAR Council prior to award
Objective of RFP is to scope out costs and timing for the numerous tasks and work products desired by IWDW-WAQS Cooperators and WESTAR-WRAP Member Agencies
  Many tasks are sequential
  Not all tasks for IWDW-WAQS and WRAP are the same
    Some tasks are TSSv2 planning tool-related applications of modeling platform data
  All results must be transferred to IWDW
    IWDW to “check off” data and results for completeness and eventual data transfers