## Sheet1
Air Directors Time and Resources Punchlist - time depends on number of Class 1 Areas
| SIP Element | Staff Persons | Hours | Duration or Time Frame
| Emissions Inventory | 1. _______________ | __ weeks (checking) | June 2018
|  | 2. _______________ | __ weeks (documentation) | June 2018
|  | 3. _______________ | __ weeks (forecasting and documenting) | July - August 2028
| Monitoring Data Analysis | 1. _______________ | __weeks (analysis - correct e3 threshold) | May -June 2018
|  |  | __ weeks (determining current routine natural) | June -July 2018
|  |  | __weeks (analysis - most impaired) | May -July 2018
|  |  | __weeks (recalculating baseline) | August-September 2018
|  |  | __weeks (recalculating 2064) | October - December 2018
|  |  | __ months (documentation) | May 2018 - ....
| Control Measures | 1. _______________ | __months (target categories or facilities) | June 2018-December 2018
|  | 2. _______________ | __ months (potential controls) | June 2018-December 2018
|  |  | __months (reduction scenarios) | January 2019-October 2019
|  |  | __months (selecting controls) | January 2019-October 2019
|  |  | __hours/days (meeting with permittee) | January 2019-October 2019
|  |  | __months (developing rule or permit conditions) | January 2019-...
| Modeling | 1. ________________ | __ weeks (protocol development) | June- July 2018
|  |  | __ weeks (documenting while computer runs) | Summer 2018
|  |  | __ weeks (analyzing results) | Fall 2018
|  |  | __months (source apportionmnt analysis) | Fall 2018
|  |  | __months (scenario runs) | 2019
|  |  | __months (documentation) | 2019
|  |  | ___months (writing final RPG justification) | 2020
| Consultation & Coordination | 1. _______________ | __ weeks (preparing) | 2018
| (involves staff & management) | 2. _______________ | __ hours (Kick-off meeting) | 2018
|  | 3. _______________ | __ hours (Follow -up conference calls) | 2018-2020
|  |  | __ weeks (documentation) | ongoing
|  |  | 6 months (final reviews) | 2021