## OGWG Template
Oil and Gas Work Group (OGWG) 2018-2019 Phase II Tasks, Deliverables, Schedule, & OGWG Involvement
Task Description |  | Deliverable Description | Schedule (Months from Project Start (est. 06/18)) | OGWG Involvement^
OGWG Co-Chair Administration & Meetings
Work Group Administration & Meetings |  | Coordination of Bi-Monthly OGWG calls and periodic Project Management Team calls, participation on other O&G calls, posting of materials on OGWG website, and other general planning efforts related to the OGWG. | On-Going | Coordinate and oversee efforts (est. 5-8 hours a month per co-chair)
Contracted Tasks for 2018-2019
Task 1 2014 (Planning) Base Year Emission Inventory
1a | Inventory Compilation, Reconciliation, Data Gaps | Emission Inventory File | 1 | not applicable
1b | 2014 O&G Activity | 2014 O&G Activity File | 1.5 | not applicable
1c | Identify Emission Factors and Speciation Profiles for Oil and Gas Sources | Literature Review PowerPoint | 2.5 | Comment on PPT
|  | Draft and Final O&G Survey | 3.5 | Review Draft, Complete Survey
|  | O&G Survey Results Memorandum | 5.5 | Comment on Memo
1d | Technical Improvements | Draft and Final Emission Inventory | 7 | Review Draft
1e | Reporting | Draft and Final Report | 7 | Review Draft
1f | SMOKE-ready Emission Inventory Files | SMOKE-ready Emission Inventory Files | 8.5 | not applicable
Task 2 Forecast Year (OTB & OTW Controls) Oil & Gas Emissions Inventory
2a | Identify historical growth, supply, demand, and production decline | Graphs of Historical O&G Activity Trends with O&G Price History | 3 | Comment on Graphs
2b | Identify a Range of Forecast Year Oil and Gas Scenarios | Draft and Final One-page Forecast Scenario Description, 2023 O&G Activity Growth Factors for Three Scenarios | 5.5 | Comment on One- pager, Comment on Graphs
2c | Identify Rule Penetration and Effectiveness for Oil and Gas Sources: National, State, Local, Tribal | OTB & OTW Emission Controls Matrix | 7 | Collaborate to fill-in matrix
2d | Implement Regionally-Consistent 2023 Forecast (OTB & OTW controls) Emissions Inventory | Methodology Presentation, Draft and Final Emission Inventory | 9.5 | Comment on Presentation, Review Draft Inventory
2e | Reporting | Draft and Final Report | 9.5 | Review Draft
2f | SMOKE-ready Emission Inventory Files | SMOKE-ready Emission Inventory Files | 10.5 | not applicable
Task 3 Forecast Year (Additional Reasonable Controls) Oil & Gas Emissions Inventory
3a | Identify Additional Reasonable Controls for Oil and Gas Sources | Additional Controls Emission Scenario Memorandum | 11 | Comment on Memo
3b | Identify Rule Penetration and Effectiveness for Oil and Gas Sources: National, State, Local, Tribal | Additional Reasonable Emission Controls Matrix | 14 | Comment on Controls Matrix
3c | Implement Regionally-consistent 2023 Forecast (Additional Reasonable Controls) Emissions Inventory | Methodology Presentation, Draft and Final Emission Inventory | 16 | Review Draft
3d | Reporting | Draft and Final Report | 16 | Review Draft
3e | SMOKE-ready Emission Inventory Files | SMOKE-ready Emission Inventory Files | 17 | not applicable
Task 4 O&G Programs and Emission Management
4a | Identification and Review of Member Agency Oil & Gas Programs | Survey of Existing O&G Programs. Survey Results Presentation. | 13 | Collaborate on Survey Development, Fill-out Survey, Comment on Presentation.
4b | Reporting | Draft and Final Memoranda | 15 | Review Draft
^Bold items will be reviewed by the full OGWG; items in regular font will be reviewed by the OGWG Project Management Team which is a subset of the OGWG.

## RHPWG Draft Template
WRAP 2018-2019 WorkPlan |  | 2018
# | Task | J | F | M | A | M | J | J | A | S | O | N | D | Deliverable Description | Work Group Involvement | Weeks FTE
1 | Monitoring Data Analysis
WRAP 2018-2019 WorkPlan #: 1.1; WRAP 2018-2019 WorkPlan Task: Evaluate EPA tracking metric and alternatives | Most impaired dataset for all Class I areas | Collaborate/conduct metric options analysis
WRAP 2018-2019 WorkPlan #: 1.2; WRAP 2018-2019 WorkPlan Task: Analyze monitor data (trends, ranges, linkages) | Recommendations for western tracking metric Reconstructed glideslope Adjust 2064 end point for fire and int'l contributions Trend analyses | Draft report Collaborate on new NC estimates Collaborate on adjustments Collaborate/conduct analyses
WRAP 2018-2019 WorkPlan #: 1.3; WRAP 2018-2019 WorkPlan Task: Identify dominant visibility-impairing pollutants for each CIA | Report summarizing results of monitor data analysis | Review draft report
2 | Emissions Inventory
WRAP 2018-2019 WorkPlan #: 2.1; WRAP 2018-2019 WorkPlan Task: Process and evaluate 2014 NEI and refinements | Refined base year inventory | Review 2014 NEI
WRAP 2018-2019 WorkPlan #: 2.2; WRAP 2018-2019 WorkPlan Task: Evaluate use of 2016 EPA modeling platform | Model year representativeness evaluation | Colloborate on analysis, review draft report
WRAP 2018-2019 WorkPlan #: 2.3; WRAP 2018-2019 WorkPlan Task: Develop and refine 2028 emission inventories | Report detailing projection methodologies for 2028 Refined 2028 inventory with control measures | Collaborate on methodologies, review draft report Review 2028 inventory
WRAP 2018-2019 WorkPlan #: 2.4; WRAP 2018-2019 WorkPlan Task: Develop screening tools | Pivot tables with Q/d, WEP plots, trajectory analysis | Colloborate on development, review implementation
3 | Air Quality Modeling
3.1 | Prepare modeling plan
3.2 | Prepare and evaluate meteorological data
3.3 | Perform dynamic model evaluations
3.4 | Conduct sensitivity testing
3.5 | Evaluate use of 2016 EPA modeling platform
3.6 | Conduct/Evaluate AQ Modeling for BY and 2028 inventories
4 | Analyzing Future Year Modeling Results
4.1 | Resolve tracking metric and model output issue
4.2 | Sensitivity/control strategy evaluation modeling for 2028
4.3 | Evaluate BY & 2028 source apportionment modeling results
4.4 | Evaluate change in visibility from BY to 2028
5 | Control Measure Analysis
5.1 | Develop criteria for source identification & 4-factor analysis
5.2 | Determine whether to use visibility as "fifth" factor
5.3 | Conduct regional/state source screening
5.4 | States conduct control measure analysis
5.5 | Identify 2028 control strategies & add to 2028 inventory
6 | Embedded Progress Report
6.1 | Access visibility conditions and changes
6.2 | Analyze changes in emissions over the past 5 years
6.3 | Prepare progress report
7 | Technical Support System TSS.v2
7.1 | CIRA staff to reach out to RHPWG to review TSSv1 & v2
7.2 | Populate TSS with monitor data
7.3 | Populate TSS with emissions data
7.4 | Populate TSS with base year modeling results
7.5 | Provide TSS training
7.6 | Populate TSS with 2028 on-the-books modeling results
7.7 | Populate TSS with 2028 ARC scenario modeling results
8 | State Planning and Adoption Process
8.1 | Identify SIP planning target dates
8.2 | Establish consultation framework
8.3 | Consulation with WRAP member agencies
8.4 | Public comment period (30 days)
8.5 | SIP Submission to USEPA
Note on B11: (Q/d and weighted emission potential) -Lexie Wilson
Note on B16: boundary conditions, fire emissions, grid size, climate change -Lexie Wilson
Note on B18: Using source apportionment and sensitivity methods -Lexie Wilson BY = base year -Lexie Wilson
Note on B22: (OTW/OTB) Also - identify source sectors and facilities for control measures evaluation -Lexie Wilson BY = base year -Lexie Wilson
Note on B23: BY = base year -Lexie Wilson
Note on B25: a.k.a. "how to identify sources and move through the 4-factor analysis process" -Lexie Wilson based on monitor, emissions, screening, and modeling data -Lexie Wilson
Note on B26: for control measure analysis and identify threshold -Lexie Wilson
Note on B29: (Additional Reasonable Control scenario) -Lexie Wilson
Note on B41: ARC = Additional Reasonable Control -Lexie Wilson
Note on B45: including Federal Land Managers and Tribes, both formal and informal consulations -Lexie Wilson

## Other WG Draft Templates
| WRAP 2018-2019 WorkPlan | 2018
# | Task | J | F | M | A | M | J | J | A | S | O | N | D | Deliverable Description | Work Group Involvement | Weeks FTE
9 | Technical Steering Committee (TSC) Progress Calls and Meetings
Planning/Oversight/Coordination/Direction calls
Board/TSC/Co-Chairs meetings at Business Meetings
Biannual Planning/Progress/Informational Meetings
10 | Regional Technical Operations Work Group (RTOWG)
10.1 | BY Emissions Processing, Modeling
10.2 | Dynamic model evaluations for ozone/PM/nitrogen
10.3 | IWDW-WAQS AQ modeling for...
10.4 | 2028 Emissions projections
10.5 | IWDW-WAQS 2028 On-the-Books Air Quality Modeling
10.6 | IWDW-WAQS FY Source Apportionment/Sensitivity Modeling
10.7 | IWDW-WAQS 2028 Control Scenarios’ Air Quality Modeling
11 | Fire and Smoke Work Group (FSWG)
WRAP Tools/FETS Update and Operation
Historic and Future Fire Activity and Emissions
Evaluation of Smoke Management Plans
Exceptional Events: ID key data to collect for demonstrations
Coordination on wildfire response and smoke management
12 | Oil and Gas Work Group (OGWG)
Regional and local air quality planning needs
ID and review of member agency oil and gas programs
ID and review of member agency emissions managagement
Assess impacts from oil and gas production
Develop oil and gas tool box
Member agency collaboration on sub-regional oil and gas management
13 | Tribal Data Development Work Group (TDDWG)
13.1 | Help Tribes understand WRAP/WESTAR product benefits
13.2 | Solicit Tribal membership in WRAP and participation in TDWG
13.3 | Help Tribes understand monitoring data and use of AQS
13.4 | Help Tribes understand the EI process and NEI capability and use
13.6 | Ensure availablility of monitoring/emissions data from Tribes
13.7 | Coordinate to facilitate support of TIPs and tribal programs
13.8 | Provide educational opportunities for WRAP member Tribes
14 | Regional Haze Planning Work Group (RHPWG)
10.2 | BY Emissions Processing, Modeling
10.3 | Dynamic model evaluations for ozone/PM/nitrogen
10.4 | IWDW-WAQS AQ modeling for...
10.5 | 2028 Emissions projections
10.6 | IWDW-WAQS 2028 On-the-Books Air Quality Modeling
10.7 | IWDW-WAQS FY Source Apportionment/Sensitivity Modeling
10.8 | IWDW-WAQS 2028 Control Scenarios’ Air Quality Modeling
WRAP Tools/FETS Update and Operation
Historic and Future Fire Activity and Emissions
Evaluation of Smoke Management Plans
ID action items requiring coordination with others
Note on B8: Meteorological modeling/MPE, Global Modeling/MPE, Regional Air Quality Modeling/MPE -Lexie Wilson
Note on B10: ...Planning/4 Corners Study/coordinate with EPRI International Haze Study -Lexie Wilson
Note on B11: (contributions from OGWG, FSWG, rules on the books, and states) -Lexie Wilson
Note on B37: Meteorological modeling/MPE, Global Modeling/MPE, Regional Air Quality Modeling/MPE -Lexie Wilson
Note on B39: ...Planning/4 Corners Study/coordinate with EPRI International Haze Study -Lexie Wilson
Note on B40: (contributions from OGWG, FSWG, rules on the books, and states) -Lexie Wilson

## Other WG Gantt
WRAP 2018-2019 WorkPlan | [7 empty] | 2018 | [11 empty] | 2019 |  |  |  | 2020 |  |  |  | 2021
RHP | RTO | F&S | O&G | TD | CON | # | Task | January | February | March | April | May | June | July | August | September | October | November | December | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3
Critical Milestones for Associated Regional Analysis Technical Support in 2018-2019
[6 empty] | 10.1 | BY Emissions Processing, Modeling
[6 empty] | 10.4 | 2028 Emissions projections
[6 empty] | 10.5 | IWDW-WAQS 2028 On-the-Books Air Quality Modeling
[6 empty] | 10.7 | IWDW-WAQS 2028 Control Scenarios’ Air Quality Modeling
WRAP tools / FETS update and operation
historic and future fire activity and emisisons
evaluation of smoke management plans
ongoing Exceptional Events analysis and coordination
WRAP member-agency coordination on wildfire response &...
Review Existing Oil and Gas Work Products
ID regional and local air quality planning needs
[6 empty] | 13.1 | Help Tribes understand WRAP/WESTAR product benefits
[6 empty] | 13.2 | Solicit Tribal membership in WRAP and participation in TDWG
[6 empty] | 13.7 | Coordinate to facilitate support of TIPs and tribal programs
Detailed Timeline by Work Group
[6 empty] | 9 |  | Technical Steering Committee (TSC) Progress Calls and Meetings
Planning/Oversight/Coordination/Direction calls
Board/TSC/Co-Chairs meetings at Business Meetings
Biannual Planning/Progress/Informational Meetings
[6 empty] | 10 |  | Regional Technical Operations Work Group (RTOWG)
[6 empty] | 10.1 | BY Emissions Processing, Modeling
[6 empty] | 10.2 | Dynamic model evaluations for ozone/PM/nitrogen
[6 empty] | 10.3 | IWDW-WAQS AQ modeling for...
[6 empty] | 10.4 | 2028 Emissions projections
[6 empty] | 10.5 | IWDW-WAQS 2028 On-the-Books Air Quality Modeling
[6 empty] | 10.6 | IWDW-WAQS FY Source Apportionment/Sensitivity Modeling
[6 empty] | 10.7 | IWDW-WAQS 2028 Control Scenarios’ Air Quality Modeling
[6 empty] | 11 |  | Fire and Smoke Work Group (FSWG)
WRAP Tools/FETS Update and Operation
Historic and Future Fire Activity and Emissions
Evaluation of Smoke Management Plans
Exceptional Events: ID key data to collect for demonstrations
Coordination on wildfire response and smoke management
[6 empty] | 12 |  | Oil and Gas Work Group (OGWG)
Regional and local air quality planning needs
ID and review of member agency oil and gas programs
ID and review of member agency emissions managagement
Assess impacts from oil and gas production
Develop oil and gas tool box
Member agency collaboration on sub-regional oil and gas management
[6 empty] | 13 |  | Tribal Data Development Work Group (TDDWG)
[6 empty] | 13.1 | Help Tribes understand WRAP/WESTAR product benefits
[6 empty] | 13.2 | Solicit Tribal membership in WRAP and participation in TDWG
[6 empty] | 13.3 | Help Tribes understand monitoring data and use of AQS
[6 empty] | 13.4 | Help Tribes understand the EI process and NEI capability and use
[6 empty] | 13.6 | Ensure availablility of monitoring/emissions data from Tribes
[6 empty] | 13.7 | Coordinate to facilitate support of TIPs and tribal programs
[6 empty] | 13.8 | Provide educational opportunities for WRAP member Tribes
[6 empty] | 14 |  | Regional Haze Planning Work Group (RHPWG)
[6 empty] | 10.2 | BY Emissions Processing, Modeling
[6 empty] | 10.3 | Dynamic model evaluations for ozone/PM/nitrogen
[6 empty] | 10.4 | IWDW-WAQS AQ modeling for...
[6 empty] | 10.5 | 2028 Emissions projections
[6 empty] | 10.6 | IWDW-WAQS 2028 On-the-Books Air Quality Modeling
[6 empty] | 10.7 | IWDW-WAQS FY Source Apportionment/Sensitivity Modeling
[6 empty] | 10.8 | IWDW-WAQS 2028 Control Scenarios’ Air Quality Modeling
WRAP Tools/FETS Update and Operation
Historic and Future Fire Activity and Emissions
Evaluation of Smoke Management Plans
ID action items requiring coordination with others
Note on H4: Meteorological modeling/MPE, Global Modeling/MPE, Regional Air Quality Modeling/MPE -Lexie Wilson
Note on H5: (contributions from OGWG, FSWG, rules on the books, and states) -Lexie Wilson
Note on H12: & smoke management -Lexie Wilson
Note on H24: Meteorological modeling/MPE, Global Modeling/MPE, Regional Air Quality Modeling/MPE -Lexie Wilson
Note on H26: ...Planning/4 Corners Study/coordinate with EPRI International Haze Study -Lexie Wilson
Note on H27: (contributions from OGWG, FSWG, rules on the books, and states) -Lexie Wilson
Note on H53: Meteorological modeling/MPE, Global Modeling/MPE, Regional Air Quality Modeling/MPE -Lexie Wilson
Note on H55: ...Planning/4 Corners Study/coordinate with EPRI International Haze Study -Lexie Wilson
Note on H56: (contributions from OGWG, FSWG, rules on the books, and states) -Lexie Wilson

## State Staffing from TSM
KEY State Regional Haze Leads (as of June 28, 2018)
These individuals, identified by State, are the primary contact for all Regional Haze announcements (e.g. Work Group Calls, Surveys, Info Dissemination)
STATE KEY RH CONTACT | Name | Agency | WRAP Regional Haze Planning Work Group (RHPWG) | RHPWG Emissions & Modeling Subcommittee | RHPWG Monitoring & Glide Slope Subcommittee | RHPWG Shared Database Subcommittee | RHPWG Control Measures Subcommittee | RHPWG Consultation & Coordination Subcommittee
California | Tina Suarez-Murias | California ARB | Co-Chair |  | x | x | x
Utah | Jay Baker | Utah DEQ | Co-Chair | x |  |  |  | x
Alaska | Molly Birnbaum | Alaska DEC | x | x
Arizona | Ryan Templeton | Arizona DEQ | x | x | Lead | x | x | x
Local Air Agency | Ed Merta | City of Albuquerque | x |  |  |  | x
Colorado | Curtis Taipale | Colorado DPHE | x | x |  |  | Lead
Hawaii | Mike Madsen | Hawaii DOH | x
Idaho | Carl Brown | Idaho DEQ | x |  |  |  |  | x
Montana | Rebecca Harbage | Montana DEQ | x |  | x |  |  | Lead
Nevada | Brenda Harpring | Nevada DEP | x | x
New Mexico | Cindy Hollenberg | New Mexico AQB | x | x | x | Lead
North Dakota | Rob White | North Dakota DOH | x
Oregon | Jeffrey Stocum | Oregon DEQ | x
South Dakota | Rick Boddicker | South Dakota DENR | x
Washington | Jean-Paul Huys | Washington DOE | x
Wyoming | Amber Potts | Wyoming DEQ | x
Also, every State, FLM, some Tribal representatives, Local jurisdictions, and Regions 6, 8, 9, 10 call in to bi-monthly RHPWG conference calls. (About 85 persons invited.)
Additionally, those listed below participate in one or more bi-weekly or monthly calls, and do in-kind work, to develop tasks and protocols for western RH SIPs &TIPs.
Other Active Participants | Name | Other WRAP Work Group Member | Regional Haze Planning Work Group Member | RHPWG Emissions & Modeling Subcommittee | RHPWG Monitoring & Glide Path Subcommittee | RHPWG Shared Database Subcommittee | RHPWG Control Measures Subcommittee | RHPWG Consultation & Coordination Subcommittee
Alaska | Molly Birnbaum | Oil & Gas | Key State Contact |  |  |  |  | x
Albuquerque | Ed Merta |  | Key Local SIP Contact |  |  |  | x
Arizona | Elias Toon | Fire & Smoke | x | x | x | x | x | x
Arizona | Natalie Muilenberg |  | x |  |  |  | x | x
Arizona | Ryan Templeton |  | Key State Contact | x | Lead | x | x | x
California | Tina Suarez-Murias | co-Chair RHPWG | co-Chair RHPWG |  | x | x | x
Colorado | Jeremy Neustifter |  | x | x |  |  | x
Colorado | Kevin Briggs | Regional Tech. Ops. | x | x
Colorado | Curt Taipale |  | Key State Contact | x |  |  | Lead
Idaho | Carl Brown |  | x |  |  |  |  | x
Idaho | Pascale Warren |  | x |  | x |  | x
Montana | Rebecca Harbage |  | Key State Contact |  | x |  |  | Lead
Montana | Craig Henrikson |  | x |  |  |  | x
Montana | Rhonda Payne |  | x | x
Montana | Stephen Coe |  | x | x
Montana | Kristen Martin |  | x |  | x | x
Nevada | Brenda Harpring |  | Key State Contact | x
Nevada | Frank Forsgren | Tech. Steer. Comm. | x | x | x | x | x | x
New Mexico | Neal Butt |  | x |  |  |  |  | x
New Mexico | Kerwin Singleton |  | x |  |  |  | x
New Mexico | Mark Jones | RTO; O&G | x | x
New Mexico | Roslyn Higgin | O&G | x | x
New Mexico | Cindy Hollenberg |  | Key State Contact | x | x | Lead
Oregon | Phil Allen | TSC; RTO | x |  | x
Utah | Jay Baker |  | co-Chair RHPWG | x |  |  |  | x
Washington | Caroline Sun |  | x |  |  |  | x
Washington | Gary Huitsing | RTO | x |  |  |  | x
Washington | Farren Herron-Thorpe |  | x | Lead
Washington | Jean-Paul Huys |  | x | x | x
Wyoming | Rob Leteff |  | x |  |  |  | x
Wyoming | Amber Potts |  | x |  | x
Albuquerque | Ed Merta |  | Key Local SIP Contact |  |  |  | x
Denver | Amanda Brimmer | O&G | Key Local SIP Contact | x |  |  | x
NPS (DOI) | Pat Brewer | TSC; RTO | x | x | x | x | x | x
Nez Perce | Julie Simpson | TSC; Tribal Data | x |  |  |  |  | x
WRAP-WESTAR | Tom Moore | TSC | x | x | x | x | x | x
WESTAR | Bob Lebens |  | x |  | x
Hawaii* | Mike Madsen |  | Key State Contact
North Dakota* | Rob White |  | Key State Contact
South Dakota* | Rick Boddicker |  | Key State Contact
* These key state contacts, and 1-2 others from the same state, call in to RHPWG bi-monthly calls. No one from their state participates in a RHPWG subcommittee.